## Slide 1: REVme Closing Report – January 2024
Date: 2024-01-18
Authors:

## Slide 2: Work Completed
Completed comment resolution for initial SA Ballot on D4.0
Recirculation will begin once P802.11bc has been published and rolled in along with comment resolutions.

## Slide 3: Plans for March
Teleconferences scheduled
  will be announced on 10 days notice
Details of an Adhoc meeting on April 16-18 in San Diego, CA
Continue comment resolution from SA Ballot recirculation on REVme D5.0.

## Slide 4: TGme Timeline (No changes)
Feb 2021 – PAR Approval
March 2021– Initial meeting, issue comment collection on IEEE Std 802.11-2020 (if published)
March 2021 – Draft 0.00 available
May 2021 – Process CC input, 11ax, 11ay, 11ba integration begins
Nov 2021 – Initial D1.0 WG Letter ballot
Sep 2022 – D2.0 Recirculation LB
Mar 2023 – D3.0 Recirculation LB
July 2023 – D4.0 Recirculation
Sep 2023 – D5.0 Initial SA Ballot
Feb 2024 – D6.0 Recirculation SA Ballot (roll-in of published amendment 11az, 11bd, 11bc, 11bb)
May 2024 – D7.0 Recirculation SA Ballot
Jul 2024 – D8.0 Recirculation SA Ballot (clean recirculation)
Sep 2024 – RevCom/SASB Approval