## Slide 1: TGbi Closing Report
Date: 2024-01-18
Authors:
Name | Affiliation | Address | Phone | Email
Carol Ansley | Cox Communications |  | +1 404 229 1672 | carol@ansley.com

## Slide 2: IEEE 802.11 TGbi
Carol Ansley (Cox)
TGbi met 4 times during this interim session.
We reviewed text submissions, and discussed how to get to an initial draft suitable for a Comment Collection.
We continue to call for submissions of text that address requirements.
For the Feb. 1st teleconference, we plan to run a motion to include additional content into our working draft.
We now plan an initial draft for comment collection in March.

## Slide 3: Timeline
TG use case start: March 2021
Use case completion: February 2022
Features identified: September 2022
Comment collection: January 2024 March 2024
LB initial: May 2024 July 2024
LB re-circ: December 2024
Ballot Pool: January 2025
MDR: January 2025
SA ballot: May 2025
SA re-circ: July 2025
802.11/EC approval: January 2026
RevCom/SASB approval: March 2026

## Slide 4: IEEE 802.11 TGbi
Carol Ansley (Cox)
Upcoming teleconferences will be on Thursdays at 10amET.
  Feb. 1
  Feb. 8
  Feb. 15
  Feb. 29
  Mar. 7