## Slide 1
Task Group BF January 2024 Closing Report
Date: 2024-01-18
Authors:
Name | Affiliation | Address | Phone | Email
Tony Xiao Han | Huawei Technologies Co., Ltd. | F3, Huawei Base, Shenzhen, China |  | Tony.hanxiao@huawei.com

## Slide 2: Abstract
This document is the closing report for Task Group BF for the January 2024 session.

## Slide 3: TGbf (WLAN Sensing)– January 2024
Progress during January 2024 session
  3 slots scheduled for TGbf
  Comment resolution for D3.0 (LB281)
    the Comment resolution for 54 CID are newly approved or marked as “ready for motion”
    17.53% of all LB281 comments are now resolved or marked as “ready for motion”
    (54 /308, Please refer to the figure)
Goals for the next two months
  Continue comment resolution for D3.0 (LB281)
  Requested 2 calls per week
Chart: P802.11bf D3.0 CR Status
| Technical | General | Editorial
Received | 153 | 15 | 140
Resolved | 29 | 2 | 23

## Slide 4: TGbf Timeline
  PAR approved Sep 2020
  First TG meeting Oct 2020
  Comment Collection (D0.1) Jan 2022Mar 2022  April 2022
  Initial Letter Ballot (D1.0) Jul 2022 Sep 2022 Nov 2022 Jan 2023
  Recirculation LB (D2.0) Jan 2023  Mar 2023  July 2023
  Recirculation LB (D3.0) May 2023  Nov 2023
  Conditional EC Approval–SA Ballot Mar 2024
  Recirculation LB (D4.0) July 2023 à Jan 2024à Apr 2024
  SA Ballot pool formation Apr 2024
  Initial SA Ballot (D4.0) Sep 2023 à Mar 2024à May 2024
  1st SA Ballot Recirculation (D5.0) Sep 2024
  2nd SA Ballot Recirculation (D6.0) Jan 2025
  3rd SA Ballot Recirculation (D7.0) Mar 2025
  Final 802.11 WG approval July 2024à Jan 2025à Mar 2025
  802 EC approval July 2024à Jan 2025à Mar 2025
  RevCom and SASB approval Sep 2024à Mar 2025à Jun 2025
PAR modification approved by the WG Nov 2023
802EC approval Mar 2024
NesCom/SASB approval Mar 2024

## Slide 5
Teleconference Times (plan after January Interim)
  Confirmed:
    Jan 25 (Thursday) 22：00 - 00:00 ET
    Jan 30 (Tuesday) 9：00 - 11:00 ET
    Feb 1 (Thursday) 22：00 - 00:00 ET
    Feb 5 (Monday) 9：00 - 11:00 ET
    Feb 6 (Tuesday) 9：00 - 11:00 ET
    Feb 19 (Monday) 9：00 - 11:00 ET --- Cancel?
    Feb 26 (Monday) 9：00 - 11:00 ET
    Feb 27 (Tuesday) 9：00 - 11:00 ET
    Feb 29 (Thursday) 22：00 - 00:00 ET
    Mar 4 (Monday) 9：00 - 11:00 ET
    Mar 5 (Tuesday) 9：00 - 11:00 ET
  ** Note:
  When conflict with CAC, the call may be changed.
  (Sept 2023 – Nov 2023 CAC calls: Oct 9, Oct 30)
  Thursday 23:00 - 01:00am ET (Thursday 20：00 – 22:00 PT, Friday 11am-13:00 in China, Friday 6am-8am in Israel, Friday 5am – 7am in Central Europe), and Sang Kim will help to take the minutes for these slots.
10 Mar 2024 - Daylight Saving Time Starts
Sunday, 10 March 2024, 02:00:00 clocks are turned forward 1 hour to Sunday, 10 March 2024, 03:00:00 local daylight time instead.