## Slide 1: P802.11bf report to EC on Conditional Approval to go to SA Ballot
Date: 2024-03-05
Authors:
Name | Affiliation | Address | Phone | Email
Tony Xiao Han | Huawei Technologies Co., Ltd. | F3, Huawei Base, Shenzhen, China |  | Tony.hanxiao@huawei.com

## Slide 2: Introduction
This document contains the report to the IEEE 802 Executive Committee in support of a request for conditional approval to send P802.11bf to SA Ballot.
This document was approved during the plenary session of the 802.11 working group on XX March 2024
  Passed in the Working Group: XX – Yes; XX – No; XX – Abstain.

## Slide 3: Status Summary
802.11bf completed one comment collection and 3 WG Letter Ballots
Draft 1.0 achieved > 75% needed for an approved draft
2155 comments received on drafts 1.0 to 3.0

## Slide 4
802.11 WG Letter Ballot Results – P802.11bf
Ballot ID | Ballot Close Date | Title | Ballot Type | Pool | Return | %Return | Abstain | %Abstain | Approve | Disapprove | %Approve
LB272 | Mar 02 2023 | Technical Letter Ballot for P802.11bf Draft 1.0 | Technical | 491 | 360 | 76.37% | 46 | 9.37% | 244 | 70 | 77.71%
LB276 | Aug 20 2023 | First Recirculation Ballot for P802.11bf Draft 2.0 | Recirculation | 491 | 388 | 81.67% | 49 | 9.98% | 291 | 48 | 85.84%
LB281 | Jan 04 2024 | Second Recirculation Ballot for P802.11bf Draft 3.0 | Recirculation | 491 | 404 | 83.71% | 42 | 8.55% | 335 | 27 | 92.54%
LB281.1 |  | Post ballot vote change (13 changed from disapprove to approve) |  | 491 | 404 | 83.71% | 42 | 8.55% | 348 | 14 | 96.13%

## Slide 5: 802.11 WG Letter Ballot Comments – P802.11bf
Ballot ID | Ballot Close Date | Title | Total Number of Comments received (Yes and No votes)
LB272 | Mar 02 2023 | Technical Letter Ballot for P802.11bf Draft 1.0 | 1302 (815 T, 459 E, 28 G)
LB276 | Aug 20 2023 | First Recirculation Ballot for P802.11bf Draft 2.0 | 545 (257 T, 269 E, 19 G)
LB281 | Jan 04 2024 | Second Recirculation Ballot for P802.11bf Draft 3.0 | 308 (153 T, 140 E, 15 G)

## Slide 6: Unsatisfied Technical comments by commenter
Voter name | LB272 | LB276 | LB 281 | Total
Debashis Dash |  |  | 2 | 2
Hongyuan Zhang |  | 1 | 1 | 2
Mahmoud Kamel |  |  | 1 | 1
Osama Aboulmagd | 10 |  |  | 10
Ankit Sethi |  | 1 | 1 | 2
Benedikt Schweizer | 5 | 7 | 1 | 13
Firouz Behnamfar | 2 |  |  | 2
Hsin-De Lin |  |  |  | 0
Jing Guo |  | 3 | 1 | 4
Niranjan Grandhe |  | 1 | 1 | 2
Sudhir Srinivasa |  | 3 |  | 3
Ying Liu |  | 2 | 1 | 3
Yongho Seok |  | 2 |  | 2
Zinan Lin |  | 8 |  | 8
Total | 17 | 28 | 9 | 54

## Slide 7: Unsatisfied Technical Comments – Topics
Debashis Dash – TB sensing measurement exchange
Hongyuan Zhang – CSI reporting (make it optional)
Mahmoud Kamel – SBP
Osama Aboulmagd – Access category for sensing frames, PICS, terminology, sensing procedure, and other various topics
Ankit Sethi* – CSI reporting (make it optional)
Benedikt Schweizer* – SBP (make it mandatory), sensing measurement session, TB sensing measurement exchange
Firouz Behnamfar* – SBP (2 comments for LB272 which had been satisfied during LB276)
Hsin-De Lin* – Did not receive any comment during any LB
Jing Guo* – CSI reporting (make it optional)
Niranjan Grandhe* – CSI reporting (make it optional)
Sudhir Srinivasa* – CSI reporting (make it optional)
Ying Liu* – CSI reporting (make it optional)
Yongho Seok* – CSI reporting (make it optional)
Zinan Lin* – Sensing capability exchange, sensing measurement session, unassociated STA, and other various topics
Did not receive Email response regarding the list of unsatisfied comments.

## Slide 8: Unsatisfied comments
The composite of all unsatisfied comments and the resolutions approved by the comment resolution committee received during working group ballot may be found in the embedded document on the right:
  Double click on the icon to the right to open this.

## Slide 9: TGbf Projected Timeline
 | Open | Close
First SA Ballot | May, 2024 | Jun, 2024 (30 days)
Second SA Ballot | Sep 2024 | Oct 2024
Third SA Ballot | Jan 2025 | Feb 2025
Fourth SA ballot (unchanged draft) | Mar 2025 | Mar 2025
EC to RevCom (RevCom submittal deadline: XXX XX, 2024) | Mar 2025 | 
RevCom to SASB | June 2025 |