## Summary Stats
CID RESOLUTION STATUS 2022-03 LB279 |  |  | 24-11/13r5
Comment Type | Ballot Total | JAN | FEB | MAR | SEP | OCT | NOV | DEC | TOTAL Motioned | PERCENTAGE
Technical | 163 | JAN: 13; 24-11/13r5 FEB: 2; 24-11/13r5 MAR: 99 | 114 | 69.9387
General | 12 | 24-11/13r5 MAR: 2 | 2 | 16.6667
Editorial | 226 | JAN: 207 | 207 | 91.5929
TOTAL | 401 | 220 | 2 | 101 | 0 | 0 | 0 | 0 | 323
PLAN | JUL | AUG | SEP | OCT | NOV | DEC | JAN
Goal
SUMMARY | NOT ASSIGNED | ASSIGNED | MOTIONED | NOT MOTIONED | TODO
Technical CIDS | 0 | 163 | 114 | 49 | 49
General CIDs | 0 | 2 | 2 | 10 | 10
Editorial CIDs | 0 | 226 | 207 | 19 | 19
Includes Withdrawn CIDs as Rejects

## CID Leaderboard
TECH CID Resolver | JAN | FEB | MAR | APR | MAY | JUN | JUL | TOTAL Motioned | Total Assigned | Total Outstanding | Duplicates | Strawpolled | Withdrawn | TODO | Explanation: Additions to Outstanding [motions only]
Assaf Kasher | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Christian Berger | JAN: 11; FEB: 2 | 13 | 32 | 19 | 0 | 9 | 0 | 10
Jonathan Segev | JAN: 2; MAR: 12 | 14 | 44 | 30 | 0 | 19 | 0 | 11
Ali Raissinia | MAR: 41 | 41 | 63 | 22 | 0 | 13 | 0 | 9
Shuling Feng | [7 empty] | 0 | 4 | 4 | 0 | 0 | 0 | 4
Stephan Sand | [7 empty] | 0 | 5 | 5 | 0 | 0 | 0 | 5
Qi Wang | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tianyu Wu | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Dibakar Das | [7 empty] | 0 | 10 | 10 | 0 | 0 | 0 | 10
Steve Shellhammer | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Niranjan Grandhe | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
ChaoChun | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Roy Want | [7 empty] | 0 | 17 | 17 | 0 | 0 | 0 | 17
Qinghua Li | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Jerome Henry | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
TOTAL TECH CIDS | 13 | 2 | 53 | 0 | 0 | 0 | 0 | 68 | 175 | 107 | 0 | 41 | 0 | 66
[8 empty] | NOT ASSIGNED | 0 |  |  |  | NET TODO= | 66
Negative likely indicates a duplicate resolution

## Motions
DB Action | DRAFT | MOTION | Date | DOC # | AUTHORS | NOTES | #Tech SP | #Gen SP | #Ed SP | #Tech CIDs | #Gen CIDs | #Ed CIDs | CIDs/Text
JAN(M) | [12 empty] | KEY: Blue: indicates duplicates, Red Removed, Green: Supersedes corresponding red.
| D1.0 | 202401-02 |  | 38r1 | Christian Berger |  |  |  |  | 1 |  |  | 1044
| * | 202401-03 |  | 165r1 | Christian Berger |  |  |  |  | 5 |  |  | 1296, 1300, 1304, 1312, and 1316
| * | 202401-04 |  | 152r1 | Jonathan Segev |  |  |  |  | 2 |  |  | 1282, 1331
| * | 202401-05 |  | 183r1 | Christian Berger |  |  |  |  | 5 |  |  | 1345, 1350, 1351, 1354, and 1355
FEB | * | 202402-01 |  | 182r1 | Christian Berger |  |  |  |  | 2 |  |  | 1341, 1161
| * | 202402-02 |  | 223r0 | Roy Want | [6 empty] | 207 | see summary document 223r0. (207 CIDs)
MAR | * | 202403-01 |  | 212r3 | Ali Raissinia |  |  |  |  | 16 |  |  | 1098, 1099, 1383, 1135, 1023, 1024, 1071, 1385, 1025, 1028, 1386, 1190, 1192, 1131, 1026, and 1073
| * | 202403-02 |  | 213r2 | Ali Raissinia |  |  |  |  | 15 | 2 |  | 1193, 1196, 1198, 1400G, 1074, 1027, 1388, 1207, 1389, 1212G, 1041, 1366, 1216, 1217, 1109, 1019, and 1075
| * | 202403-03 |  | 214r2 | Ali Raissinia |  |  |  |  | 8 |  |  | 1110, 1147, 1011, 1076, 1220, 1221, 1222, and 1226
| * | 202403-04 |  | 155r2 | Jonathan Segev |  |  |  |  | 7 |  |  | 1357, 1006, 1089, 1119, 1120, 1127, 1369
| * | 202403-05 |  | 257r1 | Jonathan Segev |  |  |  |  | 5 |  |  | 1358, 1090, 1121, 1128, 1129
MAR(D1) | * | 202403-07 |  | 285r1 | Christian Berger |  |  |  |  | 8 |  |  | 1323, 1329, 1332, 1333, 1337, 1395, 1396, and 1340 (total of 8 CIDs)
| * | 202403-08 |  | 215r2 | Ali Raissinia |  |  |  |  | 13 |  |  | 1136, 1010, 1045, 1046, 1165, 1229, 1231, 1243, 1244, 1246, 1247, 1249, and 1250 (13 total)
| * | 202403-09 |  | 225r2 | Christian Berger |  |  |  |  | 1 |  |  | 1085
| * | 202403-10 |  | 272r4 | Jonathan Segev |  |  |  |  | 19 |  |  | 1081, 1234, 1278, 1156, 1279, 1034, 1082, 1137, 1138, 1367, 1368, 1083, 1035, 1084, 1287, 1288, 1391, 1158, 1159 (total of 19)
| * | 202403-11 |  | 285r1 | Christian Berger |  |  |  |  | 1 |  |  | 1330 (left out from original 285r1 CID list)
| * | 202403-12 |  | 278r3 | Julia Feng |  |  |  |  | 1 |  |  | 1016
| * | 202403-13 |  | 288r1 | Stephan Sand |  |  |  |  | 5 |  |  | 1059, 1080, 1113, 1123, 1125
MAR(D2)
NOTE: E=Editorial, G=General, W=Withdrawn&Technical (No label is Technical)
TOTAL | [6 empty] | 0 | 0 | 0 | 114 | 2 | 207
TOTAL + SPs | [9 empty] | 114 | 2 | 207 | 323
TASK and TOTAL | [9 empty] | 163 | 12 | 226 | 401
TODO and TOTAL TODO | [9 empty] | 49 | 10 | 19 | 78
20
14

## ToDo Itemized
TECH/GENERAL CIDS TODO
| UNASSIGNED | Roy Want | Ali Raissinia | Qi Wang | Tianyu Wu | Assaf Kasher | Christian Berger | Jonathan Segev | Niranjan Grandhe
TECH-TODO | 0
EDITORIAL CIDS TODO
| Roy Want | Ali Raissinia | Shuling Feng
ALL OTHERS
| 1359 | 1106 | 1016
| 1144 | 1105
| 1384 | 1104
| 1038 | 1100
| 1107 | 1101
| 1108 | 1102
| 1364 | 1103
1373
1390
1130
1365
1111
TOTAL | 12 | 7 | 1