## Slide 1: REVme Closing Report – March 2024
Date: 2024-03-14
Authors:

## Slide 2: Work Completed
Started resolving comments received in the SA Ballot recirculation on REVme D5.0
Bit assignment to resolve conflict between IEEE 802.11 Std 802.11az-2023 and P802.11be D5.0.
  In response to the issue describe in https://mentor.ieee.org/802.11/dcn/24/11-24-0563-01-000m-dmg-positioning-bit.docx, the REVme CRC debated the solution and agreed in a motion to modify the draft as proposed.
  There was a request to make a public announcement of the bit assignment change, as it changes the publish value in IEEE 802.11az-2023

## Slide 3: Plans for May
Teleconferences scheduled
  March 25, April 8, 29, May 6
Reminder on Adhoc meeting on April 16-18 in San Diego, CA
  Details are provided in https://mentor.ieee.org/802.11/dcn/24/11-24-0618-00-000m-invitation-letter-for-april-revme-adhoc-san-diego.docx
Continue comment resolution from SA Ballot recirculation on REVme D5.0.

## Slide 4: TGme Timeline (No changes)
Feb 2021 – PAR Approval
March 2021– Initial meeting, issue comment collection on IEEE Std 802.11-2020 (if published)
March 2021 – Draft 0.00 available
May 2021 – Process CC input, 11ax, 11ay, 11ba integration begins
Nov 2021 – Initial D1.0 WG Letter ballot
Sep 2022 – D2.0 Recirculation LB
Mar 2023 – D3.0 Recirculation LB
July 2023 – D4.0 Recirculation
Sep 2023 – D5.0 Initial SA Ballot
Feb 2024 – D6.0 Recirculation SA Ballot (roll-in of published amendment 11az, 11bd, 11bc, 11bb)
May 2024 – D7.0 Recirculation SA Ballot
Jul 2024 – D8.0 Recirculation SA Ballot (clean recirculation)
Sep 2024 – RevCom/SASB Approval