## Slide 1: TGbh Closing Report
Date: 2024-03-14
Authors:

## Slide 2: Abstract
This document is the closing report for TGbh
“Randomized and Changing MAC addresses” (RCM)
March 2024 Session (mixed-mode)

## Slide 3: Work Completed
Agenda is here: 11-24/0262r7
Motions: 11-22/0651r39
Completed resolution of all comments on D3.0 LB283
Comment resolution on D3.0 spreadsheet: 11-24/0380r2
Added ANA assignments, modified a bit assignment that conflicted with 802.11be, completed MDR/MEC and approved changes to draft
Will produce D4.0, with the above
Will bring motions later in today’s agenda for recirc LB on D4.0, and conditional approval for Initial SA ballot

## Slide 4: Timeline
PAR approved Feb 2021
First TG meeting Mar 2021
D0.2 CC May 2022
Initial WG Letter Ballot (D1.0) May 2023
Recirculation LB (D2.0) Nov 2023
SA ballot pool open Jan 2024
Recirculation LB (D3.0) Jan 2024
Recirculation LB (D4.0) Mar 2024
Initial SA Ballot (D4.0) Apr 2024
Final 802.11 WG approval Jul 2024
802 EC approval Jul 2024
RevCom and SASB approval Sep 2024

## Slide 5: Teleconference (as CRC)
Tuesday, April 9, 9:30am ET, 2 hours
Complete WG LB process on D4.0
Request SA ballot on D4.0
May plans
5 slots
Comment resolution on Initial SA ballot
SA first recirc D5.0