## Slide 1
NOTE: Update all red fields replacing with your information; they are required. This is a manual update in appropriate
fields. All Blue fields are informational and are to be deleted. Black stays. After updating delete this box/paragraph.
15-11-0119-01-004k

## Slide 2: Task Group 802.15.4k Timeline (draft)
January 20, 2011
Shu Kato (NICT)

## Slide 3: Purpose
Draft TG4k Timeline assuming following
  Working in parallel for CFA and CFP
  Less than 300 technical comments as the outcome of the Letter Ballot
  Two recirculation for Letter Ballot comment resolution over 6 months
  One Sponsor Ballot recirculation over 4 months

## Slide 4: Important Time Frames for TG Timeline - Depending on how many technical comments received at the first Letter Ballot -
1. Examples taken
i. Completed: TG3c (from March 2005 to September 2009: 4.5 years)
ii. In progress: TG4f (12, 2008~ ), TG4g (12, 2008~ ),
2. Important time frames
Time TG formed
Time for CFA
Time for Tech Guidelines
Time for CFP
Time for Final Proposal
Time for Baseline Document completion
Time for Letter Ballot resolution
Time for Sponsor Ballot resolution
Time for Revcom approval

## Slide 5: Past /Current Task Group Performance Examples TG3c (2005/3 – 2009/9) / TG4f (2008/12~) / TG4g (2008/12~)
Important time frames to be considered: TG3c / TG4f / TG4g
Time for CFA: - / 2 / -
Time for Tech Guidelines: - / 6 / 4
Time for CFP issued: 22 / 6 / 2
Time for Final Proposal: 4 / 4 / 6
Time for Baseline Doc. completion: 10 / 14 / 6
Time for Letter Ballot resolution:
14 (about 500 tech. comments, 3 recirculation) /
Nov., 2010 ~ (first LB comment (134 Tech. comments) resolution be completed in Jan., 2011) /
Mar., 2010~ (first LB failed(about 1400 tech. comments), 2nd LB comment (713 tech. comments) resolution be completed in Mar., 2011)
vii. Time for Sponsor Ballot resolution: 4 ( 1 recirculation) / - / -
viii. Time for Revcom approval: 2 / - / -

## Slide 6: 802.15.4k Timeline (draft) Assumptions: two LB recirculation and one SB recirculation