## Slide 1
Project: IEEE P802.15 Working Group for Wireless Specialty Networks (WSN)
Submission Title: TG 15.4ab May 2023 Interim Session Closing Report
Date Submitted: 14 May 2023
Source: Benjamin A. Rolfe (Blind Creek Associates)
Contact:
Voice: [deprecated], E-Mail: ben.rolfe @ ieee.org
Re: Task Group 4ab: 802.15.4 UWB Next Generation
Abstract: Mixed-mode interim session closing report
Purpose: Emulate organization, encourage participation and make further progress
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.
Notes: Jul 12, 2010
Page 1

## Slide 2: Task Group 15.4ab Next Generation UWB Amendment
Objective: enhancements to 802.15.4 Ultra Wideband (UWB) physical layers (PHYs) medium access control (MAC) and associated ranging techniques while retaining backward compatibility with enhanced ranging capable devices (ERDEVs).
Mixed Mode Wireless Interim, May 2023
Live from Orlando FLA USA

## Slide 3: Task Group Organization
Chair: Benjamin Rolfe (BCA)1
Vice Chair: Clint Powell (Meta)
Vice Chair: Clint Chaplin (SRA) [Remote]
Vice Chair and Recording Secretary: David Xun Yang (Huawei)
Lead Technical Editor: Billy Verso (Qorvo)
  Thank you to all the volunteers!
1 Affiliation Details here: https://mentor.ieee.org/802-ec/dcn/22/ec-22-0061-00-00EC-rolfe-affiliations-by-802-activity.pdf

## Slide 4: Useful Links
Agenda: https://mentor.ieee.org/802.15/dcn/23/15-23-0205-08-04ab-tg4ab-agenda-may-2023.xlsx
Meeting Slides: https://mentor.ieee.org/802.15/dcn/23/15-23-0245-02-04ab-tg4ab-may-meeting-slides.pptx

## Slide 5: Session Objectives
Refine and adopt proposed text for draft
Map the path to a technically complete draft

## Slide 6: Project Schedule (working baseline)
Notes: SASB/RevCom schdule for 2024 a guess
Proposed project schedule |  | May-22 | Jun-22 | Jul -22 | Aug-22 | Sep-22 | Oct-22 | Nov-22 | Dec-22 | Jan-23 | Feb-23 | Mar-23 | Apr-23 | May-23 | Jun-23 | Jul-23 | Aug-23 | Sep-23 | Oct-23 | Nov-23 | Dec-23 | Jan-24 | Feb-24 | Mar-24 | Apr-24 | May-24 | Jun-24 | Jul-24 | Aug-24 | Sep-24 | Oct-24 | Nov24 | Dec 25 | Jan 26 | Feb 26 | Mar 26 | Apr 26 | 
Hear and evaluate proposals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cut-off for new proposals, PHY features |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cut-off for new proposals, MAC features |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Integrate poposals/contributions into TFD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Develop draft from TFD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Draft 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
TG draft review and revision |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Working group pre-ballot review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pre-ballot review and comment resolution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
First letter ballot |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
LB Comment Resolution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WG Recirculatoin |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Comment resolution, 1st recirc |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Conditional approval for SA ballot |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WG Recirculatoin |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Comment resolution, 2nd recirc and final recirc |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
First SA ballot |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Comment resolution, first SA ballot |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SA Resirculation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Comment resolution, SA recirculation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SA Resirculation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Comment resolution, 2nd SA recirc |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Conditional or unconditional approval to RevCom |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Optional 3rd SA recirc if needed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
RevCom meets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | `
You are Here

## Slide 7: Schedule Major Milestones
 | Original Schedule | Current Schedule
Call for proposals | November 2021 | 
Cut-off for new features (high level feature set), PHY | May 2022 | 
Cut-off for new features (high level feature set), MAC | July 2022 | 
Draft 0 | Post-January 2023 | Post March May 2023
TG draft review and revision complete | February - March 2023 | Mar-June 2023
Working group pre-ballot review commence | March – May 2023 (following March meeting) | July 2023
First letter ballot | June 2023 (following meeting) | Oct 2023
… |  | 
Near Term Working Milestones

## Slide 8: TFD updates
Updates to send to the TE:
Non-coherent PHY | 15-22-0514 | https://mentor.ieee.org/802.15/dcn/22/15-22-0514-05-04ab-non-coherent-phy-layer-proposal-for-15-4ab-tfd.docx
MMS MAC | 15-22-0381 | https://mentor.ieee.org/802.15/dcn/22/15-22-0381-04-04ab-nba-uwb-ranging-text-proposal-for-15-4ab-tfd.docx
Data Com | 15-22-0649 | https://mentor.ieee.org/802.15/dcn/22/15-22-0649-03-04ab-coherent-phy-layer-proposal-for-15-4ab-tfd.docx
Sensing | 15-22-0538 | https://mentor.ieee.org/802.15/dcn/22/15-22-0538-04-04ab-proposal-of-sensing-framework.docx
Hyperblock | 15-23-0215 | https://mentor.ieee.org/802.15/dcn/23/15-23-0215-02-04ab-block-assignment-in-hyper-block-tfd.docx

## Slide 9: Next Steps

## Slide 10: Interim Webex Schedule
Proposed: Usual time and interval: Alternate Tuesdays, 06:00 PT commencing 28-March
Now
Next
July Plenary

## Slide 11: Thanks