## Comments
Comment ID | Comment # | Name | Style | Index # | Vote | Affiliation | Category | Page | Sub-clause | Line # | Comment | File | Proposed Change | Must Be Satisfied? | Disposition Status (Accepted, Rejected, Revised) | Disposition Detail | Category | Notes | Editor Status DONE, Ready, N/A) | Editor Notes | Assignee
|  | Xiliang Luo |  | 123 |  | Apple | Editorial | 13 | 3.2 | 13 | Follow original agreed tech framework: 15-23-0100-02-04ab |  | "multi-millisecond ranging symbol" to "multi-millisecond ranging sequence" | Yes | Accepted
|  | Libra Xiao |  | 57 |  | NewRadio Technologies Co., Ltd. | Editorial | 13 | 3.2 | 7 | The spelling of "AOA" should be changed to "AoA" in the 7th line of Page 13, and the related edited errors in the draft should be corrected, such as Line 12 of Page 72, Line 14 of Page 77, Line 1 of Page 80, Line 3 of Page 81. |  | "AOoA" | Yes | Rejected | "AOA" is correct
|  | Xiliang Luo |  | 124 |  | Apple | Editorial | 13 | 3.2 | 15~16 | For clarification and aligning with agreed NBA-UWB TFD |  | add the following acronyms: NBA NBA-UWB RSF-RMARKER RIF-RMARKER | Yes | [6 empty] | Editor
|  | Pooria Pakrooh |  | 145 |  | Qualcomm | Editorial | 16 | 6.2.2.2 | 9 |  |  | Change to: "the channel access attempt is the first attempt or a retransmission." |  | Accepted
|  | Li-Hsiang Sun |  | 10 |  | MediaTek | Technical | 17 | 6.6.3.3 | 17 | "For HRP UWB PHY, Imm-Ack shall commence AIFS after the reception of the last symbol of Data frame or MAC command." does this apply to data frame like RCM? Time slot definition should be updated to include time needed for an Imm-Ack |  | as in comment | Yes | [6 empty] | Carlos
|  | Pooria Pakrooh |  | 146 |  | Qualcomm | Technical | 17 | 6.6.3.3 | 17 | Apply arguments about new AIFS value to IMM Ack for new 4ab devices |  | Change to: " The transmission of an Ack frame in a nonbeacon-enabled PAN or in the CFP shall commence AIFS after the reception of the last symbol of the Data frame or MAC command. The transmission of an Ack frame in the CAP shall commence either AIFS after the reception of the last symbol of the Data frame or MAC command or at a backoff period boundary. In the latter case, the transmission of an Ack frame shall commence between AIFS and (AIFS + macUnitBackoffPeriod) after the reception of the last symbol of the Data frame or MAC command. The value of AIFS is 1 ms for the SUN PHYs, LECIM PHYs, or TVWS PHYs. The value of AIFS is equal to macSifsPeriod for all other PHYs. For HRP-EMDEV device, Imm-Ack shall commence AIFS after the reception of the last symbol of Data frame or MAC command. The duration of AIFS period is equal to macHrpEMDEVUwbAifsPeriod for HRP-EMDEV device. Support for the default value (64 μs) for macHrpEMDEVUwbAifsPeriod is mandatory and support for the other values (16 μs and 32 μs) is optional." | [7 empty] | Carlos
|  | Pooria Pakrooh |  | 147 |  | Qualcomm | Technical | 19 | 8.4.3 | 7 | First row of the table, under Attribure, change the AIFS attribute |  | First row of the table, under attribute, change to: "macHrpUwbEMDEVAifsPeriod" | [7 empty] | Carlos
|  | Pooria Pakrooh |  | 148 |  | Qualcomm | Technical | 19 | 8.4.3 | 7 | First row of the table, under Description, change the AIFS description |  | First rtow of the table, under Description, change the AIFS description to: "The minimum time in μs forming a AIFS period for the HRP UWB EMDEV PHY." | [7 empty] | Carlos
|  | Li-Hsiang Sun |  | 41 |  | MediaTek | Technical | 20 | 10.29.1 | 2 | It seems AC IE can replace ARC IE, whether definition of RCM needs to be changed if there is no lefgacy device that needs ARC IE? |  | as in comment | Yes |  |  |  | Need detailed text |  |  | Li-Hsiang Sun
|  | Li-Hsiang Sun |  | 4 |  | MediaTek | Technical | 20 | 10.29.2 | 13 | Where "controller transmit diversity nodes" is defined? |  | define the term and have reference to related clauses | Yes | Revised | Delete entire e.g. phrase
|  | Mingyu Lee |  | 80 |  | Samsung Electronics | Technical | 22 | 10.29.3.5 | 1 | Color of figure needs to be removed |  | Use 15-23-0482-00-04ab | Yes | Accepted
|  | Taeyoung Ha |  | 79 |  | Samsung Electronics | Technical | 21 | 10.29.3.5 | 3 | some of the individual ranging blocks can have same ranging block duration, ranging round duration, or ranging slot duration |  | Change "different configuration for their ranging block duration, ranging round duration, and ranging slot duration" to "different configuration for their ranging block duration, ranging round duration, or ranging slot duration" | Yes | Accepted
|  | Li-Hsiang Sun |  | 5 |  | MediaTek | Technical | 21 | 10.29.3.5 | 8 | "The Hyper Block Structure IE (HBS IE), as defined in 7.4.4.56, can be used to signal the durations of each of the ranging blocks in the hyper block. The HBS IE specifies the index of the corresponding ranging block and includes a list of the durations of all the ranging blocks within the hyper block" Does a controllee which always stays in the same block within a hyper block need to know every other block's duration/indicex and its own block index? It seems the only info needed is the total hyperblock duration so it knows when its raging round (or the beginning of current block if using round hopping) will repeat. Suggest to add an optional field which indicates the total hyperblock duration in HBS IE |  | as in comment | Yes | Rejected | All the necessary information to calculate the value is present; issue if both types of info are present and don't match
|  | Li-Hsiang Sun |  | 7 |  | MediaTek | Technical | 22 | 10.29.3.5 | 13 | for round hopping between heterogenous blocks, is this entirely controller's decision or is it based on the selection of suitable blocks from controllee? |  | specify procedures to allow controllee to select suitable blocks to participate in hopping | Yes | [6 empty] | Rojan
|  | Li-Hsiang Sun |  | 9 |  | MediaTek | Technical | 22 | 10.29.3.5 | 13 | It is not very clear whether bitmap-based block scheduling or block assignment scheduling are always tied to a round hopping procedure, otherwise how does the scheduled device knows which round it is assigned within the assigned block? |  | specify bitmap-based block scheduling or block assignment scheduling are always tied to a round hopping procedure. Devices participating in the ranging exchange have either (a) pre-negotiated a hopping sequence that is known to all devices, or (b) have exchanged all the information necessary such that each device can generate the hopping sequence. | Yes | [6 empty] | Rojan
|  | Pooria Pakrooh |  | 149 |  | Qualcomm | General | 21 | 10.29.3.5 | 16 | Support of hyper-block mode is optional for all device types |  | Change line to: "The hyper block-based mode is optional for all device types." |  | Revised | Change line to: "The hyper block-based mode is optional for all devices."
|  | Taeyoung Ha |  | 81 |  | Samsung Electronics | Technical | 22 | 10.29.3.5 | 16 | ERR IE may not located at the current ranging block. |  | Remove "in the current ranging round." | No | [6 empty] | Rojan
|  | Taeyoung Ha |  | 82 |  | Samsung Electronics | Editorial | 22 | 10.29.3.5 | 20 | typo |  | Change "the controlee next higher layer" to "the next higher layer of the controlee " | Yes | Accepted
|  | Libra Xiao |  | 58 |  | NewRadio Technologies Co., Ltd. | Editorial | 33 | 10.29.3.5 | 20 | The figure4 is not clear and should be redrew, and a clear figure with the black and white color is suggested. |  | A clear figure with black and white colors is suggested to instead of the old figure. Please referring the contribution 15-23-xxxx-4ab-comment-for-figure-4-in-p802.15.4ab-pre-ballot-a | Yes | Revised | Use 15-23-0482-00-04ab
|  | Mingyu Lee |  | 76 |  | Samsung Electronics | Editorial | 21 | 10.29.3.5 | 21 | "as well" may not be a proper word for specification |  | Remove "as well" | No | Accepted
|  | Mingyu Lee |  | 78 |  | Samsung Electronics | Technical | 21 | 10.29.3.5 | 22 | hypber blocks shall have same structure to be aligned with the decsription in the page. It's already mentioned above in the page. It's better to start with hopping |  | Replace the first sentence by "Hopping is optional in hypber block-based mode" | Yes | [6 empty] | Mingyu
|  | Mingyu Lee |  | 77 |  | Samsung Electronics | Editorial | 21 | 10.29.3.5 | 24 | Since the hopping of controlee is optional, "should" change to "may" |  | Change from "should " to "may" | Yes | [6 empty] | Rojan
|  | Pooria Pakrooh |  | 150 |  | Qualcomm | Technical | 21 | 10.29.3.6 | 22 | The structure of hyper blocks are "always" repeating. |  | Change to: "Hyper block keeps the same structure repeated in every hyper block." |  | Revised | Change to: "Hyper block keeps the same structure repeated in every hyper block."
|  | Taeyoung Ha |  | 83 |  | Samsung Electronics | Technical | 27 | 10.29.9.10 | 5 | trigger step is not defined |  | Change "The Starting Slot Index field indicates the first slot of the RSF transmission" | Yes | [6 empty] | Mingyu
|  | Pooria Pakrooh |  | 153 |  | Qualcomm | General | 28 | 10.29.9.10 | 10 | "Ehnahnced HPRF" mode is not defined in the draft. |  | Clarify what "Enhanced HPRF" mdoe is. | [7 empty] | Editor
|  | Taeyoung Ha |  | 85 |  | Samsung Electronics | Technical | 27 | 10.29.9.10 | 12 | For RSF, Ipatov sequence also can be used |  | Change "The Sequence Index field indicates the code index of MMRS" to "The Preamble Code Index field indicates the preamble code index of RSF" | Yes | [6 empty] | Mingyu
|  | Libra Xiao |  | 59 |  | NewRadio Technologies Co., Ltd. | Editorial | 36 | 10.29.9.10 | 18 | Spelling is wrong for the word of schedule, such as "sche dule" in the 36th line. |  | "The Scheduling IE is used by the controller to sche dule blocks or slots to be used by intended device. " | Yes | Rejected | Already corrected
|  | Pooria Pakrooh |  | 152 |  | Qualcomm | Editorial | 27 | 10.29.9.10 | 23 | Editorial |  | Change "Table 3" |  | Accepted
|  | Pooria Pakrooh |  | 151 |  | Qualcomm | Editorial | 23 | 10.29.9.10 | 26 | "Content Control" is used instead of "Scheduling List Field" |  | Change "Content Control" to "Scheduling List Field" |  | Accepted
|  | Pooria Pakrooh |  | 154 |  | Qualcomm |  | 29 | 10.29.9.12 | 6 | Is HBS sent every hyperblock? |  | Specify how often HBS is sent. | [7 empty] | Mingyu
|  | Li-Hsiang Sun |  | 6 |  | MediaTek | Technical | 23 | 10.29.9.3 | 10 | when assignment scheduling is used and in case of hyperblock-based mode, what is the meaning of the ranging block index field? |  | change to "The Ranging Block Index field specifies the index of the ranging block, in case of block-based mode or when assignment scheduling is used in hyper block-based mode" | Yes | [6 empty] | Rojan
|  | Li-Hsiang Sun |  | 8 |  | MediaTek | Technical | 23 | 10.29.9.3 | 19 | "The RR IE is only used in block-based mode." does not seem correct |  | change to "The RR IE is only used in block-based mode or hyber bloc-based mode" | Yes | [6 empty] | Rojan
|  | Xiliang Luo |  | 125 |  | Apple | Editorial | 32 | 10.35 | 8 | "UWB MMS" should be made consistent to emphasize MMS is in the scope of UWB. |  | "10.35 Multi-millisecond (MMS) UWB operation" to "10.35 UWB Multi-millisecond (MMS) UWB operation" | Yes | Revised | 10.35 UWB Multi-millisecond (MMS) operation
|  | Xiliang Luo |  | 126 |  | Apple | Editorial | 32 | 10.35.1 | 17 | "NBA-UWB" should be made consistent in the spec to emphase the tight coupling between NB and UWB. |  | "Narrowband assisted (NBA) MMS." to "Narrowband assisted (NBA) UWB MMS." | Yes | Accepted
|  | Pooria Pakrooh |  | 155 |  | Qualcomm | General | 32 | 10.35.1 | 24 | OOB mechanism will be described as "OOB" mode further in the document. |  | Change to: " This alternative is considered OOB, and it is labeled as OOB below. | [7 empty] | Editor
|  | Xiliang Luo |  | 127 |  | Apple | Editorial | 32 | 10.35.1 | 25 | "UWB MMS" should be made consistent to emphasize MMS is in the scope of UWB. |  | "The NBA-MMS and the UWB driven MMS …" to "The NBA-UWB MMS and the UWB driven MMS …" | Yes | [6 empty] | Editor
|  | Xiliang Luo |  | 128 |  | Apple | Editorial | 32 | 10.35.1 | 27 | "UWB MMS" should be made consistent to emphasize MMS is in the scope of UWB. |  | "…, the term MMS Control (PHY) is used to mean either. " to "…, the term UWB MMS Control (PHY) is used to mean either." | Yes | [6 empty] | Editor
|  | Alex Krebs |  | 251 |  | Apple | Technical | 32 | 10.35.1 | 21-27 | Formally: Feature not approved by TG. Technically: Control transfer via OOB or UWB is contradicting consensus NBA MMS PHY (DCN 100) and MAC (DCN 381+412) TFDs, where only UWB SYNC+SFD or NB+DATA is allowed during control phase slots. |  | Remove lines. (Provide input to TG on how to enable control via UWB/OOB data packets in terms of PHY/MAC operating parameters, modulation, timings, data fields, and control flows) | Yes | [6 empty] | Breakout
|  | Riku Pirhonen |  | 258 |  | NXP Semiconductors | Technical | 70 | 10.35.10.1 | 4 | In Table 8, add values 15 and 16 for control phase mode and 16 for report phase mode Value range / options. Add default mode 1. |  | control phase mode: 1-9 (Table 28),15, 16 : default 1 report phase mode: 1-9 (Table 28), 16 : default 1 | Yes | [6 empty] | Breakout
|  | Pooria Pakrooh |  | 156 |  | Qualcomm | General | 33 | 10.35.2 | 6 | "UWB packets with data" configurations are not defined in this draft. |  | Intended data configurations need to be defined. | [7 empty] | Breakout
|  | Xiliang Luo |  | 129 |  | Apple | Editorial | 32 | 10.35.2 | 28 | "UWB MMS" should be made consistent to emphasize MMS is in the scope of UWB. (Should change other places similarly) |  | "10.35.2 MMS ranging overview" to "10.35.2 UWB MMS ranging overview" | Yes | [6 empty] | Editor
|  | Alex Krebs |  | 252 |  | Apple | Technical | 33 | 10.35.2 | 5-9 | see before comment |  | see before change | Yes | [6 empty] | Breakout
|  | Li-Hsiang Sun |  | 19 |  | MediaTek | Technical | 34 | 10.35.3.2 | 5 | "After the initiator has confirmed receipt of the RESP from the responder during control phase, and unless initialization of further devices is required, the initiator shall discontinue ranging initialization and cease transmission of ADV-POLL packets." |  | If initiator has not received RESP from responder after session initialization, and because there is no ack to RESP, the responder may have sent RIFs OTA. before statring session re-initialization. In the next session re-initialization, the V counter for RIF should be re-initilalized to a different value than the higher layer configured phyHrpUwbStsVCounter | Yes | [6 empty] | Alex
|  | Pooria Pakrooh |  | 157 |  | Qualcomm | Technical | 34 | 10.35.3.2 | 16 | What is the default UWB channel referring to? Have we defined a "default UWB coordination channel"? |  | Clarify what "the default UWB channel" refers to. | [7 empty] | Mingyu
|  | Pooria Pakrooh |  | 158 |  | Qualcomm | Technical | 35 | 10.35.3.2.1 | 4 | IFS between slots is not defined. |  | Remove: "Channel access during initialization phase shall be conducted using back-to-back transmission slots with no IFS between slots. Packet transmissions shall start at the beginning of an initialization slot only." |  | Accepted
|  | Li-Hsiang Sun |  | 11 |  | MediaTek | Technical | 35 | 10.35.3.2.1 | 9 | what is this slot number used for? |  | specify related procedure | Yes | [6 empty] | Alex
|  | Youngwan So |  | 86 |  | Samsung Electronics | Editorial | 37 | 10.35.3.3 | 1 | The texts in figure 22 and figure 23 are too small to recognize. |  | Need to enlarge or redraw | Yes | [6 empty] | Editor
|  | Li-Hsiang Sun |  | 12 |  | MediaTek | Technical | 35 | 10.35.3.3 | 24 | For 1 to many case using CAP, What is IdentityResolvingKey used in ADV_POLL and ADV_RESP? How does initiator selects one of the responders if all their RPA hash the same (corresponding to the RPA hash of ADV_POLL)? |  | clarify the addressing in this case | Yes | [6 empty] | Alex
|  | Li-Hsiang Sun |  | 14 |  | MediaTek | Technical | 38 | 10.35.3.5.1 | 34 | "The responder (controlee) may indicate the supported message control commands for each of SOR, POLL and REPORT messages in ADV-RESP." Should also add whether responder support ADV-CONF and its message controls |  | as in comment | Yes | [6 empty] | Alex
|  | Pooria Pakrooh |  | 159 |  | Qualcomm | General | 39 | 10.35.3.6 | 3 | The use of word 'discovery" is misleading here. The coordination is not used for the typical "discovery" purpose. |  | Change to:"This coordination mechanism may be used to coordinate with UWB sessions nearby and the avoidance of collisions resulting from the overlap of blocks." | [7 empty] | Mingyu
|  | Pooria Pakrooh |  | 160 |  | Qualcomm | Technical | 39 | 10.35.3.6 | 4 | Optional support. |  | Add: "Support for coordination is optional for all device types." | [7 empty] | Mingyu
|  | Mingyu Lee |  | 87 |  | Samsung Electronics | Technical | 39 | 10.35.3.6 | 10 | The NB AP and the UWB AP can use compact format with different value of message control |  | Refer 10.35.9.20 for both NB AP and UWB AP 10.35.9.20, 10.35.9.21, and 10.35.9.22 need to be replaced by the contents of 15-23-0482-00-04ab | Yes | [6 empty] | Mingyu
|  | Mingyu Lee |  | 88 |  | Samsung Electronics | Technical | 39 | 10.35.3.6 | 10 | The reference "table 1.2.3.1" is incorrect. The reference for default UWB ranging channel needs to be replaced. |  | MMS UWB ranging channel in Table 8 of section 10.35.10.1 needs to be referred | Yes | [6 empty] | Mingyu
|  | Pooria Pakrooh |  | 161 |  | Qualcomm | Editorial | 39 | 10.35.3.6 | 10 | Sub-clause numbers need to be updated |  | Update subclause numbers to correspond to draft subclauses. | [7 empty] | Mingyu
|  | Taeyoung Ha |  | 89 |  | Samsung Electronics | Editorial | 39 | 10.35.3.6 | 14 | AP already include 'packet' |  | Change "AP packets" to "APs" | Yes | Accepted
|  | Li-Hsiang Sun |  | 16 |  | MediaTek | Technical | 39 | 10.35.4 | 25 | even if no LBT, there is still a Tx/Rx turnaound time needed for the initiator/responder, so initiator cannot extend its transmission of the poll message up to macMmsRcpPollNSlots |  | as in comment | Yes | [6 empty] | Alex
|  | Li-Hsiang Sun |  | 15 |  | MediaTek | Technical | 39 | 10.35.4 | 27 | "The responder that receives the poll message successfully shall transmit a response message back to the initiator beginning in the ranging slot following the poll period. " |  | change to "The responder that receives the poll message successfully should transmit a response message back to the initiator beginning in the ranging slot following the poll period subject to LBT " | No | [6 empty] | Alex
|  | Li-Hsiang Sun |  | 17 |  | MediaTek | Technical | 39 | 10.35.4 | 40 | " The poll message is transmitted at long-term NB PHY configuration." however, it is not clear if NB Channel select is included in the previous REPORT message from responder, is it counted as short term config? It is not clear what is the protocol to change Allowed channel list in the middle of the session |  | NB channel select is not counted as short term operating parameters because it cannot be applied to the next round just for messages other than POLL There should be a protocol that based on suggested NB channel select to update allowed channel list. However, initiator may need to stay on the channels for additional rounds based on the current alowed list if it does not receive a responding message to resend the new list. | Yes | [6 empty] | Lei
|  | Pooria Pakrooh |  | 162 |  | Qualcomm | General | 39 | 10.35.4 | 40 | editorial: Line 40 is a duplicate. |  | Remove line 40: "The poll message is transmitted using the long-term NB PHY configuration." |  | Accepted
|  | Li-Hsiang Sun |  | 13 |  | MediaTek | Technical | 41 | 10.35.5 | 8 | "The responder may start transmitting a first RIF fragment at RpRifOffset into the ranging phase if no RSF fragments were transmitted," should be RpRifOffset+600RSTU |  | as in comment | Yes | Accepted
|  | Pooria Pakrooh |  | 163 |  | Qualcomm | General | 40 | 10.35.5 | 28 | A table of attributes and range of values is needed |  | Add atable of attributes and range of values. | [7 empty] | Editor
|  | Li-Hsiang Sun |  | 20 |  | MediaTek | Technical | 54 | 10.35.6 | 25 | In NBA MMS, the clock drift is corrected using NB msg, whether the value in the REPORT, i.e reply time and turnaround time, are also corrected, or they are reported based on sender's uncorrected clock (let receiver of the report to do correction)? |  | specify the procedure how to come up with the reported value | Yes | [6 empty] | Alex
|  | Xiliang Luo |  | 130 |  | Apple | Technical | 43 | 10.35.7.3 | 10 | The requirement for CCA is >= 9usec. It is not clear if it is an average over more than 9usec or it is a peak. If it is an average, the CCA result could be different for different average length. So it is unclear how CCA should perform. Is it described somewhere else? Which TFD is this from? |  |  | Yes | Revised | Add reference
|  | Carlos Aldana |  | 234 |  | Meta | Technical | 43 | 10.35.7.3 | 12 | Given that there are no a) duty cycle limitations, b) <500 MHz frequency band allocations, c) eDAA algorithm specified, it is best for Narrowband technologies to use LBT to ensure good coexistence with other technologies using that band. |  | Change the "may be " to "shall be" | Yes | [6 empty] | Breakout
|  | Li-Hsiang Sun |  | 22 |  | MediaTek | Technical | 44 | 10.35.7.4.1 | 8 | This paragraph should also describe that responder can make inputs of the allowed channel list in ADV_RESP |  | as in comment | Yes | [6 empty] | Alex, Carlos
|  | Li-Hsiang Sun |  | 21 |  | MediaTek | Technical | 44 | 10.35.7.4.1 | 17 | Which message updates macMmsNbChannelAllow List? Is it NB channel select in control message can we unify the format of NB channel select and macMmsNbChannelMap? |  | unify the format of the representation of allowed channel list | Yes | [6 empty] | Alex
|  | Carlos Aldana |  | 237 |  | Meta | Technical | 44 | 10.35.7.4.2 | 1 | What happens if all the channels are deemed unavailable or unusable? |  | Please specify expected behavior | Yes | [6 empty] | Alex
|  | Carlos Aldana |  | 239 |  | Meta | Technical | 44 | 10.35.7.4.2 | 2 | How does the initiator determine whether a channel is unavailable, unusable, or inefficient? Is it via scanning? If so, how long is the scanning duration? This should be specified so that it can be tested to achieve predictable behavior among chip vendors |  | As in comment | Yes | [6 empty] | Carlos
|  | Pooria Pakrooh |  | 164 |  | Qualcomm | General | 44 | 10.35.7.4.2 | 17 | Scaling factor needs to be defined. |  | Add the scaling factor defenition. | [7 empty] | Lei
|  | Carlos Aldana |  | 238 |  | Meta | Technical | 44 | 10.35.7.4.2 | 20 | When does the responder employ the list of available channels? Is it immediate, or after X ms? If X ms, what is X? |  | Please specify expected behavior | Yes | [6 empty] | Alex
|  | Li-Hsiang Sun |  | 24 |  | MediaTek | Editorial | 45 | 10.35.7.4.3 | 1 | RangingBlockIndex should be macMmsNbChannelAllowList |  | as in comment | Yes | Accepted
|  | Pooria Pakrooh |  | 165 |  | Qualcomm | General | 45 | 10.35.7.4.3 | 1 | "RangingBlockIndex" should be replaced with "SelectedChannel". |  | Replace "RangingBlockIndex" with "SelectedChannel". |  | Rejected | See Index #24
|  | Li-Hsiang Sun |  | 23 |  | MediaTek | Technical | 44 | 10.35.7.4.3 | 31 | macMmsPrngSeed is only 8 bits not 128 bits, use the description as in 10.35.9.2.1 that MSBs are padded 0 |  | as in comment | Yes | [6 empty] | Alex
|  | Libra Xiao |  | 60 |  | NewRadio Technologies Co., Ltd. | Editorial | 59 | 10.35.8.3 | 26 | The message content is missing and should be filled in with the correct content. |  | Octets: 1 ¦ variable ¦ Message Control ¦ Message content ¦ | Yes | Accepted
|  | Mingyu Lee |  | 94 |  | Samsung Electronics | Editorial | 48 | 10.35.8.4.1 | 1 | The color of figure needs to be removed |  | Use 15-23-0482-00-04ab | Yes | Accepted
|  | Mingyu Lee |  | 90 |  | Samsung Electronics | Editorial | 47 | 10.35.8.4.1 | 5 | Acronyms of ranging sequence fragments, i.e., RSF is already showed in the above |  | Remove "ranging sequence fragments", "(" , ")" , and "]" | Yes | Accepted
|  | Mingyu Lee |  | 95 |  | Samsung Electronics | Editorial | 48 | 10.35.8.4.1 | 10 | The color of figure needs to be removed |  | Use 15-23-0482-00-04ab | Yes | Accepted
|  | Mingyu Lee |  | 93 |  | Samsung Electronics | Editorial | 47 | 10.35.8.4.1 | 11 | The color of figure needs to be removed |  | Use 15-23-0482-00-04ab | Yes | Accepted
|  | Taeyoung Ha |  | 91 |  | Samsung Electronics | Editorial | 47 | 10.35.8.4.2 | 19 | "unnecessary" is ambiguous |  | Remove "Control and measurement report phase of multiple RSF transmissions can be omitted if unnecessary." | Yes | Accepted
|  | Taeyoung Ha |  | 92 |  | Samsung Electronics | Editorial | 47 | 10.35.8.4.3 | 26 | the conditions for the omitted control phase is ambiguous |  | Remove "If there is no change in scheduling (tbd.), the control phase of RSF transmissions (i.e., control message in the UWB channel) can be omitted." | Yes | Accepted
|  | Taeyoung Ha |  | 97 |  | Samsung Electronics | Editorial | 48 | 10.35.8.4.4 | 8 | the conditions for the omitted control phase is ambiguous |  | Remove "If there is no change in scheduling (tbd.), the control phase of the RSF transmissions (i.e., a control message in the NB channel) can be omitted." | Yes | Accepted
|  | Mingyu Lee |  | 96 |  | Samsung Electronics | Technical | 48 | 10.35.8.4.4 | 12 | To refer message format, section number needs to be included |  | Change "The REPORT message with message id 0x12 " to "The REPORT message in Section 10.35.9.15". | Yes | Accepted
|  | Youngwan So |  | 112 |  | Samsung Electronics | Editorial | 49 | 10.35.9.1 | 10 | Seems reference is missing. |  | Add table or figure listing Compact Message ID field values. | Yes | Accepted | See document 481
|  | Youngwan So |  | 120 |  | Samsung Electronics | Editorial | 58 | 10.35.9.10 | 11 | Wrong reference number to Figure |  | Change "Figure 46" to "Figure 53" | Yes | Accepted
|  | Li-Hsiang Sun |  | 27 |  | MediaTek | Technical | 59 | 10.35.9.11 | 7 | Not sure what are the Responder Address when RPA is used |  | as in comment | Yes | [6 empty] | Lei
|  | Mingyu Lee |  | 102 |  | Samsung Electronics | Technical | 59 | 10.35.9.11 | 7 | MessageControl = 0x10 is absent |  | Change from 0x20 to 0x10 | Yes | Accepted
|  | Youngwan So |  | 121 |  | Samsung Electronics | Editorial | 59 | 10.35.9.12 | 14 | Octets are missing from 2nd column of the table |  | Add appropriate Octet numbers | Yes
|  | Youngwan So |  | 122 |  | Samsung Electronics | Editorial | 60 | 10.35.9.13 | 33 | Typo |  | Change "This is the response message is sent by.." to "This is the response message sent by.." | Yes | [6 empty] | Editor
|  | Youngwan So |  | 113 |  | Samsung Electronics | Editorial | 49 | 10.35.9.2.1 | 14 | Acronyms are missing from Acronyms section (Section3.2) |  | Add acronyms to Section 3.2 (e.g. RPA, IRK, etc.) | Yes
|  | Mingyu Lee |  | 103 |  | Samsung Electronics | Technical | 64 | 10.35.9.20 | 19 | Merge with 10.35.9.21 and 10.35.9.22 Change the contents by using 15-23-0482-00-04ab |  | 10.35.9.20, 10.35.9.21, and 10.35.9.22 need to be replaced by the contents of 15-23-0482-00-04ab | Yes
|  | Pooria Pakrooh |  | 167 |  | Qualcomm | Editorial | 67 | 10.35.9.22.2 | 14 | Editorial |  | Change "Session CH" to "UWB channel" | [7 empty] | Editor
|  | Youngwan So |  | 115 |  | Samsung Electronics | Editorial | 53 | 10.35.9.3.10 | 6 | Seems no definition or descriptions about fieds |  | Please add definition and description | Yes
|  | Mingyu Lee |  | 100 |  | Samsung Electronics | Technical | 54 | 10.35.9.3.14 | 1 | 15-23-0372-01-04ab is missing |  | Add the contents of 15-23-0372-01-04a. The referenece in the document, i.e., [Table in slide 14 of 15-23-0307-00-04ab] , replaced by Table 28 of Section 13.2.5 | Yes
|  | Riku Pirhonen |  | 255 |  | NXP Semiconductors | Technical | 54 | 10.35.9.3.14 | 1 | Control and report phase configurations are set with this control field on NB. If control and report are done using UWB, the field can be used to define that the default UWB parameters are used instead of NB control and report. |  | The Report Phase Config field specifies the PHY Config in the Report Phase. Valid NB values are 1 to 9, as per Table 28. If value is set to 16, a UWB SP0 packet with data rate 1.95 and CC K=7 is used. | Yes
|  | Riku Pirhonen |  | 256 |  | NXP Semiconductors | Technical | 54 | 10.35.9.3.14 | 1 | Preamble sequence used by UWB in control and report phase needs to be defined |  | Add paragraph after line 1: When NBA-MMS uses UWB in control and report phase, preamble is the same as used by RSF, if RSF uses Ci 9 - 32. If RSF code is 33-48, preamble code Ci is (RSF code modulo 8) + 24. | Yes
|  | Riku Pirhonen |  | 257 |  | NXP Semiconductors | Technical | 69 | 10.35.9.3.14 | 4 | Table 7 allows only one Initialization Channel. This is vulnerable for multipath fading and could become a capacity bottleneck. Rename macMmsNbiInitChannel to macMmsNbiInitChannel1 and add macMmsNbiInitChannel2 and macMmsNbiInitChannel3 for total of up to three initialization channels. Use of more than one channels is optional. |  | macMmsNbInitChannel1:0-249;Initialization channel 1:2 macMmsNbInitChannel2:0-249; Optional Initialization channel 2:- macMmsNbInitChannel3:0-249;Optional Initialization channel 3:- | Yes
|  | Riku Pirhonen |  | 254 |  | NXP Semiconductors | Technical | 53 | 10.35.9.3.14 | 20 | NBA-MMS control and report phase configurations are set with the control fields defiend in Figure 41. If control and report are done using UWB, the field is used to indicate it. |  | The Control Phase Config field specifies the PHY Config in the Control Phase. Valid NB values are 1 to 9, as per Table 28. If value is set to 15, a UWB SHR is used. If value is set to 16, a UWB SP0 packet with data rate 1.95 Mbit/s, PHR as defined in 16.2.7.3, and CC K=7 is used. | Yes
|  | Youngwan So |  | 98 |  | Samsung Electronics | Editorial | 50 | 10.35.9.3.2 | 16 | Typo |  | Change MessageConten to MessageContent | Yes | [6 empty] | Editor
|  | Youngwan So |  | 114 |  | Samsung Electronics | Editorial | 50 | 10.35.9.3.2 | 16 | Typo |  | Change "ofg" to "of" | Yes | [6 empty] | Editor
|  | Pooria Pakrooh |  | 166 |  | Qualcomm | General | 50 | 10.35.9.3.6 | 26 | Clarification questions: 1. Is the NBAllowed list the reference for "the NB Channel Select field"? If yes, which message contains the Allowed list? It is not specified. 2. Is this flexible enough to signal reasonable selection possibilities? |  | Clarifications as per comment.
|  | Li-Hsiang Sun |  | 25 |  | MediaTek | Technical | 51 | 10.35.9.3.9 | 1 | for countries do not have UNII-3 band, how to use this field to block the entire band? |  | as in comment | Yes
|  | Youngwan So |  | 99 |  | Samsung Electronics | Editorial | 52 | 10.35.9.3.9 | 13 | Not enough definition or decription on fields |  | Looks to need some definition or description. | Yes
|  | Youngwan So |  | 101 |  | Samsung Electronics | Editorial | 54 | 10.35.9.4 | 16 | The table is empty |  | Looks need to fill something | Yes
|  | Youngwan So |  | 116 |  | Samsung Electronics | Editorial | 55 | 10.35.9.5 | 3 | Something missing from after colon mark |  | Please make sentence complete. | Yes
|  | Youngwan So |  | 119 |  | Samsung Electronics | Editorial | 58 | 10.35.9.8 | 4 | Seems typo or incomplete sentence |  | Revise appropriately if needed. | Yes
|  | Li-Hsiang Sun |  | 28 |  | MediaTek | Technical | 58 | 10.35.9.8 | 6 | NbaChannelMap is not defined and in this message it is NB channel select |  | as in comment | Yes
|  | Youngwan So |  | 117 |  | Samsung Electronics | Editorial | 57 | 10.35.9.8 | 7 | "NB PHY Configuration Present" appears two times in the format. |  | Revise appropriately if needed. | Yes
|  | Youngwan So |  | 118 |  | Samsung Electronics | Editorial | 57 | 10.35.9.8 | 12 | Wrong reference number to Figure |  | Change "Figure 48" to "Figure 52" | Yes
|  | Li-Hsiang Sun |  | 26 |  | MediaTek | Technical | 57 | 10.35.9.8 | 15 | what is the reason that message content must have at least 5 bytes? |  | as in comment | Yes
|  | Pooria Pakrooh |  | 168 |  | Qualcomm | Editorial | 71 | 10.36.1 | 5 | Do not have to mention "support for sensing is optional". The next sentence clarifies that an SDEV supports sensing. |  | Remove "Support for sensing is optional". | [7 empty] | Bin
|  | Pooria Pakrooh |  | 169 |  | Qualcomm | Editorial | 71 | 10.36.1 | 9 | Line 6-8 are duplicate of lines 9-12. |  | Remove lines 6-8. | [7 empty] | Bin
|  | Pooria Pakrooh |  | 170 |  | Qualcomm | Technical | 72 | 10.36.2 | 21 | Proxy mode needs to be added. |  | Add a line after line 21: "Sensing by proxy" | [7 empty] | Bin
|  | Pooria Pakrooh |  | 171 |  | Qualcomm | General | 72 | 10.36.3 | 23 | Make the definition clear |  | Change to: "Frequency stitching combines CIR measurements over multiple carrier frequencies, to improve sensing link budget and accuracy." | [7 empty] | Bin
|  | Li-Hsiang Sun |  | 30 |  | MediaTek | Technical | 73 | 10.36.4.2 | 1 | Is the session being setup here same as the session with ID advertised in AC IE? However The session ID in AC IE is defined by controller here the session is between initiator and responder which may not be the controller |  | clarify the relationship between the sensing session here and the session advertised by the controller | Yes | [6 empty] | Bin
|  | Pooria Pakrooh |  | 172 |  | Qualcomm | Technical | 73 | 10.36.4.2 | 7 | 1. Mode/role can be represend as "mode", defined in 10.36.2. 2. Porocessed target is not complete yet, unless it is defined, it can not be requested during setup phase. 3. Other parameters listed from TFD. 4. Sections need to be added |  | Change to "sensing mode (subclause 10.36.2), packet format (subclause 16.2.1), CIR report parameters (subclause 10.36.7.2), operating channel, and use of frequency stitching." | [7 empty] | Bin
|  | Li-Hsiang Sun |  | 29 |  | MediaTek | Technical | 73 | 10.36.4.2 | 10 | Where sensing session setup request and response messages are defined? |  | define the message | Yes | [6 empty] | Bin
|  | Li-Hsiang Sun |  | 31 |  | MediaTek | Technical | 73 | 10.36.4.3 | 18 | What is the protocol in sensing measurement phase for the sensing initiator to request resource to the controller for sensing transmitters to send SENS PPDU and for sensing receiver to send report? Is there an assumption that sensing initiator is the controller |  | Either define the resource request protocol and how sensing initiator uses controller to relay sensing parameters to the controllees/responders, or define controller as sensing initiator | Yes | [6 empty] | Bin
|  | Li-Hsiang Sun |  | 33 |  | MediaTek | Technical | 73 | 10.36.4.3 | 18 | for multi-static sensing, are all responders tx/rx in the same round? |  | define in multi-static sensing all responders tx/rx in the same round | Yes | [6 empty] | Bin
|  | Pooria Pakrooh |  | 173 |  | Qualcomm | Editorial | 73 | 10.36.4.3 | 19 | Replacement of instance with round is fine to me. |  | As per comment. | [7 empty] | Bin
|  | Li-Hsiang Sun |  | 32 |  | MediaTek | Technical | 73 | 10.36.4.3 | 22 | What defines the start of a round? Is it a data frame with AC IE? |  | define the start of sensing round as the round where a data frame with AC IE is transmitted | Yes | [6 empty] | Bin
|  | Pooria Pakrooh |  | 174 |  | Qualcomm | General | 74 | 10.36.4.4 | 9 | Clarifying the "window" refers to a duration of time. |  | Change to "An SDEV shall support a window-based CIR measurement report which carries the CIR in a specified time duration window." | [7 empty] | Bin
|  | Pooria Pakrooh |  | 176 |  | Qualcomm | Technical | 74 | 10.36.4.4 | 23 | Bitmap offset and length are fixed during a session, |  | Change to "The bitmap length and bitmap offset are is negotiated and determined through other means, and it is they are fixed during sensing session." | [7 empty] | Bin
|  | Pooria Pakrooh |  | 179 |  | Qualcomm | Technical | 75 | 10.36.4.5 | 2 | The optional mode is already supported based on mode 2 in control message (section 10.36.7.1). |  | Change line to: "Support for a variable bitmap mode in which the bitmap varies from packet to packet is optional." | [7 empty] | Bin
|  | Pooria Pakrooh |  | 180 |  | Qualcomm | Technical | 75 | 10.36.4.5 | 2 | We have details from the consensus regarding how the bitmap is specied in the optional mode. |  | Change the pragraph to "An SDEV may optionally support a variable bitmap mode in which the bitmap varies from packet to packet. In this mode,the responder reports CIR taps whose magnitude are above a prespecified threshold, and the associated bitmap. The threshold value "T" shall be determined by the initiator, and it is defined relative to the strongest detected tap. The responder reports taps whose magnitude are no more than T dB below magnitude of the strongest tap. If initiator does not want the CIR report to be thresholded, it specifies a very high value for T." | [7 empty] | Bin
|  | Pooria Pakrooh |  | 181 |  | Qualcomm | Technical | 75 | 10.36.4.5 | 10 | Optional bitwidth values are not added. |  | Add a line at the end of line 10: "An SDEV may optionally reduce the bitwidth of the CIR I/Q values to 10, 12 and 14 bits. The bitwidth reduction shall be achieved by power of two scaling and quantization of the CIR values as described below. Assuming the CIR values as h(k), k=1, 2, …K, and m is the largest absolute value of the real or imaginary components: m = max(max(abs(h_R (k)), abs(h_I (k))) ) ∀k∈{1, 2, …K} For a desired number of bits, N_b, power-of-two scaling is achieved by choosing α to be the smallest integer such that: 2^α ≥ m/(2^(Nb-1)−1) The new quantized real and imaginary value would be round ((h_R (k))/2^α ), and ((h_I (k))/2^α ), respectively." | [7 empty] | Bin
|  | Pooria Pakrooh |  | 175 |  | Qualcomm | Editorial | 74 | 10.36.4.5 | 17 | Changing the caluses to preserve hierarchy of topics. |  | Add a subclause "10.36.4.5.1 General" for the contents in lines 17-26. | [7 empty] | Bin
|  | Li-Hsiang Sun |  | 35 |  | MediaTek | Technical | 74 | 10.36.4.5 | 21 | “earliest CIR tap above threshold” as reference point, is this reference tap common among all tx/rx pairs? |  | Clarify the reference tap to be common among all tx/rx pairs, i.e. “Earliest tap above threshold among all tx/rx anttenna pairs” | Yes | [6 empty] | Bin
|  | Li-Hsiang Sun |  | 36 |  | MediaTek | Technical | 74 | 10.36.4.5 | 25 | In the mandatory mode, does initiator also propose BM_offset and whether it is fixed during the session |  | add BM_offset as initiator and it is fixed throughout the session | Yes | [6 empty] | Bin
|  | Pooria Pakrooh |  | 177 |  | Qualcomm | Editorial | 74 | 10.36.4.5 | 25 | Thi should be a subclause of 10.36.4.5 |  | Change the numbering of this clause to "10.36.4.5.2: Mandatory baseline bitmap configurations" | [7 empty] | Bin
|  | Pooria Pakrooh |  | 178 |  | Qualcomm | Editorial | 74 | 10.36.4.5 | 26 | Refer to a subclause for mandatory bitmap configs. |  | Change to "In the mandatory mode, initiator proposes the bitmap, based on its sensing area of interest, from a limited set of bitmap options defined in sublause 10.36.4.5.2." | [7 empty] | Bin
|  | Li-Hsiang Sun |  | 37 |  | MediaTek | Technical | 75 | 10.36.4.6 | 23 | what are the messages to terminate the session? |  | define the messages to terminate session | Yes | [6 empty] | Bin
|  | Li-Hsiang Sun |  | 38 |  | MediaTek | Technical | 76 | 10.36.6.1 | 7 | “ A device supporting SBP shall set the SBP field of the UWB HRP Capability Information field in the HRP UWB Association Request command to one.” Is this the capability of performing as proxy and initiator? SBP requesting device does not seem need to indicate SBP capability How does a SBP requesting device discover which address has the capability of being the proxy? |  | clarify this is the capability of being a sensing initiator, i.e. the proxy Controller may need to announce controllee’s SBP capability to other controlees | Yes | [6 empty] | Bin
|  | Li-Hsiang Sun |  | 39 |  | MediaTek | Technical | 76 | 10.36.6.1 | 7 | whether controller also need a capability indication of SBP? |  | add SBP capability in association response command | Yes | [6 empty] | Bin
|  | Pooria Pakrooh |  | 182 |  | Qualcomm | Technical | 76 | 10.36.6.1 | 7 | Support of SBP is optional for an SDEV. |  | Change to: :Support of sensing by proxy is optional for an SDEV". | [7 empty] | Bin
|  | Li-Hsiang Sun |  | 40 |  | MediaTek | Technical | 76 | 10.36.6.3 | 19 | what is the message/IE used to send report? |  | add an address field in CIR report IE for initiator identity different responders to the SBP requesting device | Yes | [6 empty] | Bin
|  | Pooria Pakrooh |  | 183 |  | Qualcomm | Editorial | 77 | 10.36.7 | 1 |  |  | AC IE is not dediceted to sensing only and it includes parameters for ranging and data comm as well. Suggesting to move it to the chapter where IEs are defined. | [7 empty] | Bin
|  | Pooria Pakrooh |  | 191 |  | Qualcomm | Technical | 82 | 10.36.7.1 | 1 | Reordering the IE fields: Change the order of fields in Figure 60 to show the more common fields earlier. |  | Change the order of fields to: "CIR IQ number of bits/Bitmap Mode/Length/Bitmap offset/Bitmap Gap/ Btimap/Compression/Process for Range/Process for velocity/Process for AoA/Reserved" | [7 empty] | Bin
|  | Pooria Pakrooh |  | 196 |  | Qualcomm | General | 83 | 10.36.7.1 | 1 | Adding field descriptions |  | Change to: "The Proces CIR report for Range field indicates if the responder should estimate ranges of the objects and include them in the report." | [7 empty] | Bin
|  | Pooria Pakrooh |  | 192 |  | Qualcomm | General | 82 | 10.36.7.1 | 2 | Adding field descriptions |  | Change to: "The CIR IQ number of bits fields indicates the number of bits for the representation of each of I and Q taps in CIR report, as per table x." Insert table x to show the following mapping: "0: 10 bits, 1: 12 bits 2: 14 bits 3: 16 bits" | [7 empty] | Bin
|  | Pooria Pakrooh |  | 197 |  | Qualcomm | General | 83 | 10.36.7.1 | 2 | Adding field descriptions |  | Change to: "The Proces CIR report for Velocity field indicates if the responder should estimate velocities of the objects and include them in the report." | [7 empty] | Bin
|  | Li-Hsiang Sun |  | 45 |  | MediaTek | Technical | 85 | 10.36.7.1 | 2 | there should be a capability for responder to indicate if it support Feedback control value 2 |  | as in comment | Yes | [6 empty] | Bin
|  | Pooria Pakrooh |  | 193 |  | Qualcomm | General | 82 | 10.36.7.1 | 3 | Adding field descriptions |  | Change to: "The Bitmap Mode field defines how the CIR bitmap is determined, and shall have one of the values specified in Table 11." | [7 empty] | Bin
|  | Pooria Pakrooh |  | 198 |  | Qualcomm | General | 83 | 10.36.7.1 | 3 | Adding field descriptions |  | Change to: "The Proces CIR report for AoA field indicates if the responder should estimate azimuth and elevation anglea of arrival of the objects and include them in the report." | [7 empty] | Bin
|  | Pooria Pakrooh |  | 203 |  | Qualcomm | Technical | 85 | 10.36.7.1 | 3 | Nonsensing Tx CIR report field is not added in AC IE. |  | Add Nonsensing Tx CIR report field is not added in AC IE. | [7 empty] | Bin
|  | Pooria Pakrooh |  | 204 |  | Qualcomm | Technical | 85 | 10.36.7.1 | 3 | The source of CIR report should be removed from the fields as one source is mapped to one packet per agreement. |  | Remove source of CIR report and add the mapping table between packets and CIR report source. | [7 empty] | Bin
|  | Pooria Pakrooh |  | 199 |  | Qualcomm | General | 83 | 10.36.7.1 | 4 | Adding field descriptions |  | Change to: "The Bitmap Offset field indicates the number of CIR taps between the CIR reference point and the start of the CIR window, represented a BM_offset in Fiugure 48." | [7 empty] | Bin
|  | Pooria Pakrooh |  | 200 |  | Qualcomm | General | 83 | 10.36.7.1 | 5 | Adding field descriptions |  | Change to: "The Bitmap Gap field is only used if bitmap mode is zeo. It indicates the gap between two strings of all ones, defined as "G" in subclause 10.36.4.5." | [7 empty] | Bin
|  | Pooria Pakrooh |  | 201 |  | Qualcomm | General | 83 | 10.36.7.1 | 5 | Adding field descriptions |  | Change to: "The Bitmap Gap field is only used if bitmap mode is zeo. It indicates the gap between two strings of all ones, defined as "G" in subclause 10.36.4.5." | [7 empty] | Bin
|  | Pooria Pakrooh |  | 205 |  | Qualcomm | Technical | 86 | 10.36.7.1 | 5 | One bit is needed for compression in CIR report IE. |  | Add a compression bit as bit 14 in Figure 88 to indicate whether the CIR report is compressed. | [7 empty] | Bin
|  | Pooria Pakrooh |  | 206 |  | Qualcomm | General | 87 | 10.36.7.1 | 6 | RSSI representation needs to be defined. |  | Refer to section 10.25.2.8 of 802.15.4me, for RSSI range and resolution. | [7 empty] | Bin
|  | Pooria Pakrooh |  | 184 |  | Qualcomm | Technical | 77 | 10.36.7.1 | 7 | All "TBD"s in Figure 74 need to be replaced with "variable". |  | Change "TBD"s to "variable". | [7 empty] | Bin
|  | Li-Hsiang Sun |  | 34 |  | MediaTek | Technical | 81 | 10.36.7.1 | 7 | are CIR Report Parameters, Frequency Stitch parameters, Non-sensing TX CIR report parameters same for all sensing responders? |  | if these parameters can be different then add address field before the parameter subfields/ sensing control field | Yes | [6 empty] | Bin
|  | Li-Hsiang Sun |  | 43 |  | MediaTek | Technical | 81 | 10.36.7.1 | 7 | CIR tap threshold config should it be in the sensing control |  | add a field for this info | Yes | [6 empty] | Bin
|  | Pooria Pakrooh |  | 186 |  | Qualcomm | Technical | 81 | 10.36.7.1 | 8 | In Figure 82, number of octes for "common sensing control" should be "0/variable". |  | In Figure 58, change the number of octes for "common sensing control" to "0/variable". | [7 empty] | Bin
|  | Pooria Pakrooh |  | 194 |  | Qualcomm | General | 82 | 10.36.7.1 | 8 | Adding field descriptions |  | Change to "When the Bitmap Mode field is zero, the Length field specifies the number of taps in each string of ones, represented by L in subclause 10.36.4.5.1. | [7 empty] | Bin
|  | Li-Hsiang Sun |  | 44 |  | MediaTek | Technical | 84 | 10.36.7.1 | 9 | whether frequency stitching is allowed for aggregate BW not multiple of 500MHz? |  | the formula may need to be updated if aggregate BW can be not multiples of 500MHz | Yes | [6 empty] | Bin
|  | Youngwan So |  | 104 |  | Samsung Electronics | Editorial | 77 | 10.36.7.1 | 10 | RSDB field in Figure 75 seems to be RSDP. |  | RSDB to RSDP | Yes | [6 empty] | Bin
|  | Youngwan So |  | 105 |  | Samsung Electronics | Editorial | 77 | 10.36.7.1 | 10 | R field in Figure 75 seems to need more explanation. No description about it. |  | Looks to need some definition or description. | Yes | [6 empty] | Bin
|  | Pooria Pakrooh |  | 187 |  | Qualcomm | General | 81 | 10.36.7.1 | 11 | Adding field descriptions |  | Change to: "The CIR Report Parameters Present field when one indicates the presence of the CIR Report Parameters field, or not present when zero." | [7 empty] | Bin
|  | Pooria Pakrooh |  | 188 |  | Qualcomm | General | 81 | 10.36.7.1 | 12 | Adding field descriptions |  | Change to:"The Frequency Stitching Parameters Present field when one indicates the presence of the Frquency Stitching Parameters field, or not present when zero." | [7 empty] | Bin
|  | Youngwan So |  | 106 |  | Samsung Electronics | Editorial | 82 | 10.36.7.1 | 12 | The second row content is missing. |  | Looks need to fill something | Yes | [6 empty] | Bin
|  | Pooria Pakrooh |  | 195 |  | Qualcomm | Technical | 82 | 10.36.7.1 | 13 | Values in Table 12. |  | The lengh values for the second column are : 2, 4, 8, 16. The lengh values for the third column are : 4, 8, 16, 32. | [7 empty] | Bin
|  | Pooria Pakrooh |  | 202 |  | Qualcomm | General | 84 | 10.36.7.1 | 13 | Adding field descriptions |  | Change to: "The Bitmap field is present if Bitmap Mode=1. It indicated the respnder's bitmap for the CIR report." | [7 empty] | Bin
|  | Pooria Pakrooh |  | 189 |  | Qualcomm | General | 81 | 10.36.7.1 | 15 | Adding field descriptions |  | Change to: "The Sensing Mode field when zero incidates monostaitc sensing, or bistatic sensing when 1, or multistatic sensing when 2, or sensing by proxy when 3." | [7 empty] | Bin
|  | Pooria Pakrooh |  | 190 |  | Qualcomm | General | 81 | 10.36.7.1 | 17 | Adding field descriptions |  | A table is needed to list the possible formats: "0: SENS0, 1: SENS1, 2:SENS2" | [7 empty] | Bin
|  | Libra Xiao |  | 61 |  | NewRadio Technologies Co., Ltd. | Technical | 82 | 10.36.7.1 | 18 | Figure 62 is missing and should be redrew. |  | A new figure 62 should be fiiled in the line18 of Page 82. | Yes | [6 empty] | Bin
|  | Li-Hsiang Sun |  | 42 |  | MediaTek | Technical | 79 | 10.36.7.1 | 24 | RIF STS length, and RSF to RIF gap seems to be missing from MMS ranging config IE Whether we need to have different preamble code/gap size for initiator and responder? |  | add missing info and make tx/rx config to be the same | Yes | [6 empty] | Bin
|  | Pooria Pakrooh |  | 185 |  | Qualcomm | Technical | 80 | 10.36.7.1 | 28 | "Ehnahnced HPRF" mode is not defined in the draft. |  | Clarify what "Enhanced HPRF" mdoe is. | [7 empty] | Bin
|  | Li-Hsiang Sun |  | 48 |  | MediaTek | Technical | 87 | 10.36.7.2 | 1 | if the reference tap if common among all tx/rx CIR reports, then the Timing offset field should have +/- values or a value indicating not within the range that can be specified by the field |  | as in comment | Yes | [6 empty] | Bin
|  | Li-Hsiang Sun |  | 47 |  | MediaTek | Technical | 87 | 10.36.7.2 | 3 | The normalization factor description needs to describe that this is the power of two number CIR tap value needs to be divided by, in order to compare with CIR values with other TX/RX pairs |  | as in comment | Yes | [6 empty] | Bin
|  | Li-Hsiang Sun |  | 46 |  | MediaTek | Technical | 86 | 10.36.7.2 | 6 | Antennas field plus 1 should be the number of number of tx/rx antenna pairs |  | as in comment | Yes | [6 empty] | Bin
|  | Li-Hsiang Sun |  | 49 |  | MediaTek | Technical | 88 | 10.36.7.3 | 5 | why the sensing initiator Address is needed in SBP request IE if this IE is sent to sensing initiator? |  | as in comment | Yes | [6 empty] | Bin
|  | Li-Hsiang Sun |  | 50 |  | MediaTek | Technical | 90 | 10.36.7.5 | 9 | not clear why destination address is in IE not in MAC header |  | remove destination address field | Yes | [6 empty] | Bin
|  | Li-Hsiang Sun |  | 51 |  | MediaTek | Technical | 90 | 10.37.1 | 17 | “To discover and make association with controlees, a controller may send the Control Message with the Application Control IE (AC IE) whose Association Availability field is set to one.” What is the Control Message |  | change control message to a data frame | Yes
|  | Li-Hsiang Sun |  | 52 |  | MediaTek | Technical | 91 | 10.37.3 | 16 | If two devices associate with the same short address in the same round, how does controller tell one of them (by using the short address) the new short address in association response? |  | clarify the procedure. Controller should reject both and let them rety with different short addresses or with long addresses | Yes
|  | Li-Hsiang Sun |  | 18 |  | MediaTek | Technical | 92 | 10.37.4.1 | 9 | "The Supported AIFS field specifies the AIFS time supported by the controlee. The Supported AIFS field 9 shall have one of the values specified in Table 18." |  | change to "The Supported AIFS field specifies the AIFS time supported by the controlee. The Supported AIFS field shall have one of the values <=2 specified in Table 18." | Yes
|  | Li-Hsiang Sun |  | 54 |  | MediaTek | Technical | 93 | 10.37.4.1 | 16 | Ack to association req/resp shall use AIFS=64 |  | as in comment | Yes
|  | Pooria Pakrooh |  | 207 |  | Qualcomm | General | 91 | 10.37.4.1 | 27 | The source addressing mode filed and the destination addressing mode fileds are not shown in the Association request command content in Figure 69. |  | Add the source addressing mode filed and the destination addressing mode fileds to the Association request command content in Figure 69.
|  | Pooria Pakrooh |  | 208 |  | Qualcomm | General | 91 | 10.37.4.1 | 29 |  |  | Remove (or add for Figure 94) Frame pending field, as it is not included in the Association Request command
|  | Li-Hsiang Sun |  | 53 |  | MediaTek | Technical | 91 | 10.37.4.1 | 30 | If short address are used by both sides and PAN ID compression is 1 seems contradict with settings allowed in baseline table 7-2 |  | as in comment | Yes
|  | Pooria Pakrooh |  | 209 |  | Qualcomm | General | 91 | 10.37.4.1 | 30 |  |  | Remove (or add for Figure 94) PAN ID compression field, as it is not included in the Association Request command
|  | Pooria Pakrooh |  | 210 |  | Qualcomm | General | 91 | 10.37.4.1 | 32 |  |  | Remove (or add for Figure 94) the Destination Address field, as it is not included in the Association Request command
|  | Libra Xiao |  | 62 |  | NewRadio Technologies Co., Ltd. | Editorial | 91 | 10.37.4.2 | 2 | In Tabel 16, the upper and lower table rows have been misaligned. |  | To align the Table 16 | Yes | [6 empty] | Editor
|  | Libra Xiao |  | 63 |  | NewRadio Technologies Co., Ltd. | Editorial | 91 | 10.37.4.2 | 9 | In Tabel 17, the upper and lower table rows have been misaligned. |  | To align the Table 17 | Yes | [6 empty] | Editor
|  | Li-Hsiang Sun |  | 56 |  | MediaTek | Technical | 101 | 10.40,2 | 17 | If there is already NBA, the NB REPORT has defined Ptdata, so it seems the scenario described here is not a NBA ranging. In this case how does initiator know the responder’s capability and willingness to use NB for data exchange? |  | as in comment | Yes
|  | Li-Hsiang Sun |  | 55 |  | MediaTek | Technical | 101 | 10.40.2 | 17 | “At the end of time offset, initiator shall transmit NB packet on the allocated NB channel. “ |  | suggest to perform a LBT before transmission | Yes
|  | Mingyu Lee |  | 107 |  | Samsung Electronics | Technical | 102 | 10.40.3.1 | 2 | Options according to the value of the address size field needs to be presented |  | Add a table with Value column and description column. 0 - Size of Address field is 2 octets. 1 - Size of Address field is 3 octets. 2 - Size of Address field is 8 octets. 4 - reserved | Yes
|  | Mingyu Lee |  | 108 |  | Samsung Electronics | Technical | 102 | 10.40.3.1 | 6 | Reference for NB PHY Configuration needs to be added |  | Add Table 28 of Section 13.2.5 as reference | Yes
|  | Youngwan So |  | 109 |  | Samsung Electronics | Editorial | 102 | 10.40.3.1 | 7 | Seems a certain word is missing |  | "The transmission offset field specifies the remaining until..." to "The transmission offset field specifies the remaining time until..." | Yes | [6 empty] | Editor
|  | Xiliang Luo |  | 131 |  | Apple | Editorial | 103 | 11.1.3.15 | 4 | Typo |  | "250 channels" to "200 channels" | Yes
|  | Carlos Aldana |  | 235 |  | Meta | Technical | 103 | 11.1.3.15 | 6 | The span of the channels should be limited to reduce the effect on other unlicensed technologies. In 2.4 GHz, only 80 MHz of unlicensed spectrum is used. |  | Reduce the 500 MHz span in 6GHz to a reasonable value ( < TBD MHz) | Yes
|  | Carlos Aldana |  | 236 |  | Meta | Technical | 103 | 11.1.3.15 | 6 | in 6 GHz, there is a list of Preferred Scanning channels where discovery happens for 802.11. Those channels (in 802.11 nomenclature) are: 5, 21, 37, 53, 69, 85. Narrowband should exclude those 20 MHz channels from the allowed channel list. |  | As in comment | Yes
|  | Youngwan So |  | 110 |  | Samsung Electronics | Editorial | 104 | 12.3.2 | 2 | The table is empty |  | Looks need to fill something | Yes
|  | Libra Xiao |  | 64 |  | NewRadio Technologies Co., Ltd. | Editorial | 102 | 13.1.2.3 | 2 | In the seconde line, the "Figure 13-3" is not found in IEEE 802.15.4-2020 and there is only Figure 12-3 for O-QPSK. |  | "As per Figure 123-3" | Yes
|  | Run Chen |  | 1 |  | NewRadio Technologies Co., Ltd. | Editorial | 101 | 13.1.2.3 | 12 | Edit error: "SDF" |  | To change "SDF" to "SFD" | Yes | [6 empty] | Editor
|  | Youngwan So |  | 111 |  | Samsung Electronics | Editorial | 105 | 13.1.2.3 | 12 | Seems typo |  | Change "SDF" to "SFD" | Yes | [6 empty] | Editor
|  | Run Chen |  | 2 |  | NewRadio Technologies Co., Ltd. | Editorial | 101 | 13.1.2.3 | 13 | Edit error: "SDF" |  | To change "SDF" to "SFD" | Yes | [6 empty] | Editor
|  | Xiliang Luo |  | 132 |  | Apple | Editorial | 105 | 13.1.2.3 | 13 | Typo |  | "The SDF for optional dynamic …" to "The SFD for optional dynamic …" | Yes | [6 empty] | Editor
|  | Pooria Pakrooh |  | 211 |  | Qualcomm | Editorial | 105 | 13.1.2.3 | 13 | Editorial |  | Change to: "The SFD for optional dynamic signaling…" | [7 empty] | Editor
|  | Vinod Kristem |  | 67 |  | Apple | Editorial | 105 | 13.1.2.3 | 12,13 | "...this is being employed the SDF pattern format defined by Figure 13-3 (Format of the SFD field) shall signal the default 250 kb/s modulation rate, i.e., Config #1 in Table 28. The SDF for optional dynamic….". It should have been SFD. |  | Replace SDF with SFD | [7 empty] | Editor
|  | Xiliang Luo |  | 133 |  | Apple | Editorial | 106 | 13.2.3 | 6~7 | Typo: In P802.15.4me/D00, Chapter 16 is HRP UWB PHY |  | "…, the haft-rate K=7 convolutioncal code described in 15.3.3.3, …" to "…, the haft-rate K=7 convolutioncal code described in 16.3.3.3, …" | Yes
|  | Xiliang Luo |  | 135 |  | Apple | Editorial | 107 | 13.2.5 | 1 | Only need to add one more row to indicate the mode of dynamic signaling of modes with SFD. |  | Remove row #9 in Table 28 | Yes
|  | Xiliang Luo |  | 134 |  | Apple | Editorial | 106 | 13.2.5 | 15 | For clarification in the spec. Old spec does not reveal this info clearly. |  | Add: Note that 1 chip is of duration 0.5us and 1 symbol carries 4 bits. These 4 bits are coded ones if FEC is applied. Meanwhile, the number of chips within 1 symbol is referred to as the Spreading Factor (SF). | Yes
|  | Xiliang Luo |  | 136 |  | Apple | Editorial | 109 | 13.3.14 | 13 | 1. Typo 2. MMS -> UWB MMS for clarify in spec" |  | "Where the O-QPSK is being employed as the MMS Control PHY, it is …" to "Where the O-QPSK is employed as the UWB MMS Control PHY, it is …" | Yes
|  | Vinod Kristem |  | 68 |  | Apple | Technical | 110 | 16 | 5 to 26 | This section defines the HRP devices HRP-EMDEV, HRP-ARDEV, and HRP-SDEV. This is different from the consensus reached on device types, as captured in the consensus document (15-23-0308-03-04ab-4ab-devices-and-feature-set). |  | Update the HRP devices as HRP-ERPDEV, HRP-ARDEV, HRP-LLDDEV and HRP-SDEV, and the corresponding mandatory and optional features, as listed in the consesus document 15-23-0308-03-04ab-4ab-devices-and-feature-set
|  | Pooria Pakrooh |  | 212 |  | Qualcomm | Technical | 110 | 16.1 | 13 | Define "LLDEV", and make dynamic PHR mandatory for LLDEV. |  | Change to: "Support for this dynamic data mode PHR is mandatory for LLDEV, and for HRP-EMDEV devices that support either the optional LDPC coder or the optional 124.8 Mb/s modulation and is otherwise optional to support."
|  | Carlos Aldana |  | 232 |  | Meta | Editorial | 110 | 16.1 | 25 | Upgrade the text in NOTE so that it is no longer a NOTE. |  | Remove the word "NOTE--" | Yes
|  | Carlos Aldana |  | 233 |  | Meta | Technical | 110 | 16.1 | 25 | Clarify the text to include other conditions |  | Add the sentence "It is also possible for a device to support both HRP-EMDEV and HRP-SDEV." | Yes
|  | Vinod Kristem |  | 69 |  | Apple | Technical | 110 | 16.1 | 5 to 19 | HRP-EMDEV seem to combine the HRP-ERPDEV and HRP-LLDDEV from the consesus document. Better to be aligned with the consensus document |  | Replace HRP-EMDEV with HRP-ERPDEV and define the HRP-LLDDEV as another device with emphasis on dynamic data mode
|  | Pooria Pakrooh |  | 216 |  | Qualcomm | General | 111 | 16.2.1 | 1 | Numbering of SENS packets start from 0, to be compatible for STS packet numbering. This was also reflected in the sensing consensus. |  | Change packet configuration numbers from (one/two/three), to (zero/one/two).
|  | Pooria Pakrooh |  | 218 |  | Qualcomm | Technical | 111 | 16.2.1 | 8 | The spacing of fragments is fixed to 1ms. |  | Change to: "… fragments that have a start-to-start spacing of one millisecond ...""
|  | Pooria Pakrooh |  | 215 |  | Qualcomm | Technical | 110 | 16.2.1 | 20 | Add agreements for Advacned 4ab device |  | Add: "An advanced 4ab device shall be at least one of the ARDEV, SDEV, or LLDEV."
|  | Carlos Aldana |  | 240 |  | Meta | Technical | 110 | 16.2.1 | 30 | We probably want to enable the case for a single packet to allow for ranging, sensing, and data (e.g. simple Ack) |  | Change the sentence to "The HRP-EMDEV optionally includes a dynamic data mode employing the PHR described in 16.2.7.4, which may be used in SP0 style packets as well as SENS packet configuration two and three" | Yes
|  | Pooria Pakrooh |  | 213 |  | Qualcomm | General | 110 | 16.2.1 | 33 | Numbering of SENS packets start from 0, to be compatible for STS packet numbering. This was also reflected in the sensing consensus. |  | Change "format one" to "format zero".
|  | Pooria Pakrooh |  | 214 |  | Qualcomm | Editorial | 110 | 16.2.1 | 34 | Editorial |  | Change to: " The sensing sequence shall be constructed as described …"
|  | Carlos Aldana |  | 241 |  | Meta | Editorial | 110 | 16.2.1 | 34 | Remove the word "the" |  | As in comment | Yes | [6 empty] | Editor
|  | Pooria Pakrooh |  | 222 |  | Qualcomm | Technical | 114 | 16.2.10 | 17 | Add agreement regarding extended gap duration when frequency stitchin is enabled. |  | Change to: "The gap duration shall be one preamble symbol duration when frequency stitching feature is not enabled. When frequency stitching is enabled, the gap duration is 40 symbols."
|  | Pooria Pakrooh |  | 223 |  | Qualcomm | Technical | 114 | 16.2.10 | 21 | Gap is not meaningful when SENS segment is not followed by any other field. Gap should be dashed line in the figure. |  | Show the rightmost gap with dashed line.
|  | Pooria Pakrooh |  | 224 |  | Qualcomm | Technical | 114 | 16.2.10 | 24 | The sentence "may optionally support SENS packets constructed using BPRF mode symbols specified by the length 127 ternary codes in Table 16-8." is not accurate reflection of the agreement in TFD/consensus about length-127. |  | Change the sentence to: "An SDEV may optionally support additional mode of sensing only for SENS0 packet, where all three fields (SYNC, SFD, and SENS) use the same length 127 code from Table 16-8, with spreading factor of L=4. The SYNC and SENS field should use the same code index."
|  | Carlos Aldana |  | 249 |  | Meta | Editorial | 114 | 16.2.10 | 28 | add the word "be" after "may" instead of after "optionally" |  | As in comment | Yes
|  | Xiliang Luo |  | 137 |  | Apple | Editorial | 115 | 16.2.11 | 1 | No need to complicate things. Should maintain the ranging word. It is fine to refer to this MMS for sensing etc. |  | "Multi-millisecond channel sounding" to "Multi-millisecond ranging" | Yes
|  | Carlos Aldana |  | 250 |  | Meta | Editorial | 115 | 16.2.11 | 1 | This section seems out of place as it should come after LDPC, PHR discussion. |  | Move it after all the data comm related text | Yes
|  | Xiliang Luo |  | 139 |  | Apple | Editorial | 115 | 16.2.11.1 | 9 | 1. Should use the figure illustrated in the agreed TFD; 2. Need to have one clear figure to demonstrate both NBA and UWB-SHR for intial sync of UWB MMS |  | Update Fig. 112 to one including both NBA and UWB-SHR | Yes
|  | Xiliang Luo |  | 140 |  | Apple | Technical | 115 | 16.2.11.1 | 23 | Z=2 as the default value. Alternative Z=1 could be signaled by higher layers. |  | Clarify: Z=2 as the default value. Alternative Z=1 could be signaled by higher layers. | Yes
|  | Pooria Pakrooh |  | 225 |  | Qualcomm | Technical | 115 | 16.2.11.1 | 23 | We support adding a single option of 2ms. |  | Set Z=2ms.
|  | Pooria Pakrooh |  | 226 |  | Qualcomm | General | 115 | 16.2.11.1 | 23 |  |  | 1. Set the attribure "RpRifOffset" in page 41 to 2ms. 2. Define another attriburte to signal the gap at the end of RIFs, before report.
|  | Alex Krebs |  | 253 |  | Apple | Technical | 115 | 16.2.11.1 | 14-17 | see before comment |  | see before change | Yes | [6 empty] | Breakout
|  | Vinod Kristem |  | 72 |  | Apple | Technical | 115 | 16.2.11.1 | 27, 28 | "Where X and Y are the number of RSF and RIF fragments respectively in the MMS UWB packet, the following are the combinations that shall be supported by the HRP-ARDEV". This was dicussed and consesus reached only for NBA-MMS. The X and Y combinations for UWB-MMS still under discussion. |  | Update the text as follows "Where X and Y are the number of RSF and RIF fragments respectively in the MMS UWB packet, the following are the combinations that shall be supported by the HRP-ARDEV with Narrowband assisted MMS". This was dicussed and consesus reached only for NBA-MMS. The X and Y combinations for UWB-MMS still under discussion.
|  | Xiliang Luo |  | 138 |  | Apple | Editorial | 115 | 16.2.11.1 | 6~7 | Avoid using channel sounding CIR etc. There is no requirement that ones have to generate a CIR here. |  | "…, allowing the receiver to generate its channel sounding CIR using multiple fragments thus bringing improved security." to "…, allowing the receiver to use multiple fragments and gain improved sensitivity." | Yes
|  | Vinod Kristem |  | 71 |  | Apple |  | 115 | 16.2.11.1 | 9 | Since Figure 112 is a general illustartion of MMS packet, it should capture both NBA-MMS and UWB MMS |  | Update the picture, also showing NB as an anchor for MMS
|  | Xiliang Luo |  | 141 |  | Apple | Editorial | 116 | 16.2.11.2 | 12 | Note the delicate difference between MMRS and MMRS symbol. MMRS symbol referes to the symbol after adding gaps and spreading. |  | "Each RSF consists of a repetition of a selected multi-millisecond ranging symbol (MMRS). " to "Each RSF consists of a repetition of MMRS symbols with each MMRS symbol being constructed with a selected multi-millisecond ranging sequence (MMRS). " | Yes
|  | Xiliang Luo |  | 142 |  | Apple | Editorial | 116 | 16.2.11.2 | 12 | Note the delicate difference between MMRS and MMRS symbol. MMRS symbol referes to the symbol after adding gaps and spreading. To align with agreed TFD. Also consistent with line 20. |  | "The MMRS is formed using one of a possible …" to "One MMRS symbol is formed using one of a possible …" | Yes
|  | Xiliang Luo |  | 143 |  | Apple | Editorial | 116 | 16.2.11.2 | 21 | Plural format |  | "The same MMRS shall be used for all RSF in an MMS packet." to "The same MMRS shall be used for all RSFs in an MMS packet." | Yes | [6 empty] | Editor
|  | Xiliang Luo |  | 144 |  | Apple | Editorial | 117 | 16.2.11.3 | 7 | Agreed parameter sets for NBA-UWB operations in 15-23-0097-02-04ab 15-23-0315-01-04ab |  | Add: 1. MMRS configurations sets 2. RSF only MMS configuration sets 3. Mixed MMS configurations sets | Yes
|  | Pooria Pakrooh |  | 219 |  | Qualcomm | Technical | 111 | 16.2.6.2 | 14 | SDEV follows Same number of symbols for SFD as ERDEV. |  | Change section before 16.2.6.3 on SFD, as below: "In the HPRF mode, the HRP-ERDEV and SDEV shall support the length 4, 8, and 16 SFD specified in Table 15-7c for the phyHrpUwbSfdSelector values of 1, 2, and 3. Support of the length 32 SFD specified in Table 15-7c is optional.
|  | Vinod Kristem |  | 70 |  | Apple | Technical | 111 | 16.2.6.2 | 15 | "...mode, the HRP-ERDEV and HRP-SDEV shall support transmission and reception with PSR values of 32 and 64...". This is applicable to add HRP devices |  | Update as per the comment
|  | Carlos Aldana |  | 242 |  | Meta | Technical | 111 | 16.2.6.2 | 20 | The SYNC field should not be longer than specified |  | Add a new paragraph that states "The duration of the SYNC field shall be set to the exact value negotiated" | Yes
|  | Carlos Aldana |  | 243 |  | Meta | Editorial | 112 | 16.2.7 | 6 | Remove parenthesis |  | As in comment | Yes | [6 empty] | Editor
|  | Pooria Pakrooh |  | 217 |  | Qualcomm | Technical | 111 | 16.2.7.3 | 11 | Add agreements on PHR for SENS1 and SENS2. |  | Add this at the beginning of line 4: "The HRP-SDEV shall use the PHR format described in this subclause encoded using the K=7 convolution code and send using the data modulation (as described in 16.3.4)."
|  | Carlos Aldana |  | 248 |  | Meta | Technical | 114 | 16.2.7.4 | 1 | "shall be sent as zero" should be changed to "shall be set to 0" |  | As in comment | Yes | [6 empty] | Editor
|  | Pooria Pakrooh |  | 220 |  | Qualcomm | Editorial | 112 | 16.2.7.4 | 9 | Editorial |  | Change to: "The HRP-EMDEV dynamic data mode PHR shall consist of two fields PHR1 and PHR2"
|  | Carlos Aldana |  | 244 |  | Meta | Editorial | 112 | 16.2.7.4 | 11 | Remove redundant "and PHR2 as described in 10.26.1.2.12" |  | As in comment | Yes
|  | Pooria Pakrooh |  | 221 |  | Qualcomm | Technical | 112 | 16.2.7.4 | 15 | Support for this dynamic PHR mode is mandatory for LLDEV. |  | Change to: "Support for this dynamic data mode PHR is mandatory for LLDEV devices and for HRP-EMDEV that support either the optional LDPC coder specified in 16.3.3.4 or the optional 124.8 Mb/s modulation specified in 10.26.1.2.17 , and is otherwise optional to support."
|  | Carlos Aldana |  | 246 |  | Meta | Editorial | 112 | 16.2.7.4 | 20 | Change the word "which" to "that" |  | As in comment | Yes
|  | Carlos Aldana |  | 247 |  | Meta | Editorial | 112 | 16.2.7.4 | 23 | add the word "HRP-EMDEV" before "transmitter" |  | As in comment | Yes
|  | Carlos Aldana |  | 245 |  | Meta | Editorial | 112 | 16.2.7.4 | 18-19 | Remove first sentence as it's been said already |  | As in comment | Yes
|  | Pooria Pakrooh |  | 227 |  | Qualcomm | Technical | 118 | 16.3.3.4 | 8 | These are nominal rates |  | Change:" The supported nominal coding rates"
|  | Pooria Pakrooh |  | 228 |  | Qualcomm | Technical | 118 | 16.3.3.4 | 8 | Do we want to mention that: "Full parity is sent"? |  | Add a sentence regarding all parity bits are maintained.
|  | Pooria Pakrooh |  | 229 |  | Qualcomm | Technical | 120 | 16.3.3.4 | 9 | Range of Npld is different from agreement |  | Change line 3 lower bound and line 4 upper bound to (44x8).
|  | Pooria Pakrooh |  | 230 |  | Qualcomm | Technical | 131 | 16.4.1.2 | 15 | This has not been agreed before. So far, only frequency stitching needs defenition of overlapping channels, |  | Define some limited overlapping set of channels for stitching, not all over the 499.2MHz-12.5GHz.
|  | Vinod Kristem |  | 73 |  | Apple | Technical | 133 | 16.7 | 10 | Add the HRP-ERPDEV parameter sets, as listed in the consensus document 15-23-0308-03-04ab-4ab-devices-and-feature-set |  | As in comment
|  | Vinod Kristem |  | 74 |  | Apple | Technical | 133 | 16.7 | 11 | Add the HRP-ARDEV parameter sets with NBA-MMS, as listed in the consensus document 15-23-0308-03-04ab-4ab-devices-and-feature-set |  | As in comment
|  | Carlos Aldana |  | 231 |  | Meta | Technical | 112 | 16.7.2.4 | 15 | The conditions for dynamic data mode PHR are too limiting. |  | Remove the sentence and add a capability field for dynamic PHR in Figure 95 (UWB HRP Capability Information field format) so that we can accommodate the situation when 124.8 Mbps and LDPC are not supported. | Yes
|  | Libra Xiao |  | 65 |  | NewRadio Technologies Co., Ltd. | Editorial | 130 | 16.8.2 | 32-33 | There is a problem of repeated description between this sentence and the following paragraph, so this sentence should be deleted. |  | "If the received ID fails to match the expected ID, the WU-RXDEV returns to turning on every phyUwbWuPeriod to sample for 1 ms to await another wake up signal/ " | Yes
|  | Vinod Kristem |  | 75 |  | Apple | Technical | 136 | 33.2.2.3 | 8,9 | It is not clear how the 32 bit SFD sequence maps into symbols. What is SFD duartion? Is there a scarmbling applied on the SFD pulses? |  | The text need to be clarified as in comment
|  | Libra Xiao |  | 66 |  | NewRadio Technologies Co., Ltd. | Editorial | 135 | 33.3.4 | 14 | In Figure 101, the second "1-4 chip burst" is not clear and should be redrew clearly. Other, the same one is in the figure 102. |  | In Figure 101 & Figure 102, the second "1-4 chip burst" should be redrew clearly. | Yes
|  | Taeyoung Ha |  | 84 |  | Samsung Electronics | Technical | 27 |  | 4 | Sequence Index is ambiguous |  | Change "Sequence Index" to "Preamble Code Index" | Yes

## Progress-Status
Comments and Resolution Status | [7 empty] | Draft editing Status
Total # LB Comments | # with Blank resolution | # with non-blank resolution | # with "Rejected" resolution | # with "Accepted" resolution | # with "Revised" resolution | # Assigned | # No Resolution, not Assigned | DONE | N/A | PART | Ready | ISSUE | ASSIGNED | Blanks
257 | 221 | 36 | 4 | 26 | 6 | 132 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 258
|  | Okay | 36 |  |  |  |  | 0 | Done + N/A
|  | 14.01% | 1.556% | 10.12% | 2.335% | 51.36% | 34.63% | 0% | of total | 0% | 0% | 0% | 0% | 100.4%
0%
Note on L4: Billy Verso: i.e. a rejected comment