## 3000 WG
Working Group Name: | Engineering of I&CPS WG
Working Group Chair: | Bob Schuerger
Covers material from Color Book(s): | ALL
Summary: 1 Ballot Document (PAR) | Source Material | Project Chair | PAR Number | PAR Exp | Status | Notes
RP for the Engineering of I&CPS | All Color Books | Bob Schuerger | 3000 | 2016 | Draft development | PAR approved in Dec 2009; 3-yr ext approved in 2013
PAR

## PS Design WG
Working Group Name: |  | Power Systems Design WG
Working Group Chair: |  | Gary Fox
Covers material from Color Book(s): |  | Red, Gray, and White
Summary: 10 Ballot Documents (PARs) | Source Material |  | Project Chair | PAR Number | PAR Exp | Index # | Status | Notes | LP notes
RP for the Planning of I&CPS | Red -- Ch 1; Gray -- Ch 1, 12, 16; White -- Ch 1, 4, 9 |  | — | 3001.1 | — | 1 | No PAR (admin w/d) | PAR was active 2009-2013; Co-Chair is needed
RP for Evaluating the Electrical Service Requirements of I&CPS | Red -- Ch 15; Gray -- Ch 4, 7 |  | Barry Hornberger | 3001.2 | 2016 | 2 | WG review (ready for MEC?) | PAR approved 2008; 2-yr ext granted in 2012, 2014. Material was moved to Word, formatted in template. WG reviewing the draft - Gary sent to group in Sept using link to Mentor. Lisa to do a quick review.
RP for the Design of I&CPS | Red -- Ch 2, 3, 6, 8, 9; Gray -- Ch 2, 3; White -- Ch 1, 2, 3 |  | Dan Neeser | 3001.3 | — | 3 | No PAR | Oct 2013: Dan was ready to begin; old chapters need to be put in template. May 2014: Hold off on PAR; focus on open PARs | Need help with template?
RP for Estimating the Costs of I&CPS | Red -- Ch 16, 17 |  | Sonny Sengupta | 3001.4 | — | 4 | No PAR
RP for the Application of Power Distribution Apparatus in I&CPS | Red -- Ch 10, 12, 13; Gray -- Ch 5, 8 |  | Gary Fox | 3001.5-2013 |  | 5 | Published | Appr 11 Dec 2013; Pub 25 Apr 2014 Active through 2023
RP for the Expansion, Modernization, and Rehabilitation of I&CPS | Gray -- Ch 15; White -- Ch 9 |  | Dave Korpess | 3001.6 | — | 6 | No PAR
RP for the Application of Communication and Signaling Systems used in I&CPS | Gray -- Ch 13; White -- Ch 7 |  | — | 3001.7 | — | 7 | No PAR | Co-Chair is needed; Draft in template
RP for the Instrumentation and Metering of I&CPS | Red -- Ch 11 |  | Jim Harvey | 3001.8-2013 |  | 8 | Published | Appr 6 Feb 2013; Pub 5 Apr 2013 Active through 2023
RP for the Lighting of Industrial and Commercial Facilities | Gray -- Ch 10; White -- Ch 6 |  | Steve Townsend | 3001.9 | 2016 | 9 | Sponsor Ballot: PreBallot Invite closed 5/21/12 MEC & legal rev on D2 & D3 completed June 2010 & Mar 2012. | PAR approved in 2008; 2-yr ext approved in 2012, 2014 Copyright Issues Copyright perm needed before start of ballot. Suggest creating list and Lisa Perry to help with creating letters. | D2 - MEC 2010 D3 - MEC 2012 Need to ask Tina to delete the invitation. Complicated permissions
RP for Electric Space Conditioning of Industrial and Commercial Facilities | Gray -- Ch 11 |  |  | 3001.10 |  | 10 | Killed | PAR was never submitted
RP for the Application of Controllers and Automation to I&CPS | Gray -- Ch 6, 14 |  | Duane Leschert | 3001.11 | 2015 | 11 | Sponsor Ballot: PreBallot Review Invite closed 4/28/12 D0 - MEC & legal rev Mar 2012 D1 - MEC in Nov 2012 | PAR approved in 2009; 2-yr ext approved in 2013 Copyright Issues Copyrt perm needed to start ballot Uploaded for ballot 29 Apr 2012 | Per Gary, only three figs in need of permission. May need to recreate instead. Need to ask Tina to delete the invitation
Moved Material | PAR
APPROVED
Red -- Ch 4
Red -- Ch 5
Red -- Ch 7
Gray -- Ch 9
White -- Ch 5
White -- Ch 6

## PS Analysis WG
Working Group Name: |  |  | Power Systems Analysis WG
Working Group Chair: |  |  | Farrokh Shokooh
Covers Material from Color Book(s): |  |  | Violet and Brown
Summary: 16 Ballot Documents (PARs) |  | Source Material |  | Project Chair | PAR Number | PAR Exp | Index # | Status | Notes | LP notes
RP for the Modeling and Simulation of I&CPS as a Precursor to Conducting System Studies |  | New |  |  | 3002.1 | — | 12 | No PAR
RP for Conducting a Load Flow Analysis of I&CPS |  | Brown -- Ch 6 |  | Massimo Mitolo | 3002.2 | 2015 | 13 | Sponsor Ballot: Invitation [Click to view open invitations in myProject] New ballot group being formed, invitation to close 5/13/15 MEC completed 21 Apr 2014 | PAR approved in 2009; 1-yr ext granted in 2013, 2014 Uploaded for initial ballot 13 May 2014 Invite closed 9 May 2014; ballot group exired 9 Nov 14. Minor changes from MEC need to be made before opening the SB.
RP for Calculating AC Short Circuit Currents in I&CPS |  | Violet -- Ch 1, 2, 3 |  | Jun Q | 3002.3 | 2015 | 14 | Sponsor Ballot: Invitation [Click to view open invitations in myProject] New ballot group being formed, invitation to close 5/13/15 MEC completed 21 Apr 2014 | PAR approved in 2009; 1-yr ext granted in 2013, 2014 Uploaded for initial ballot 13 May 2014 Invite closed 9 May 2014; ballot group expired 9 Nov 14. Minor changes from MEC need to be made before opening the SB.
RP for Calculating AC Short-Circuit Currents, Both With and Without AC Decay, in I&CPS |  | Violet -- Ch 4, 5, 6, 7, 8 |  |  | 3002.4 | — | 15 | No PAR | ON HOLD Draft in template (final)
RP for Conducting an Arc-Flash Analysis of I&CPS |  | New |  |  | 3002.5 | — | 16 | No PAR
RP for Conducting a Transient Stability Analysis of I&CPS |  | Brown -- Ch 8 |  |  | 3002.6 | — | 17 | No PAR
RP for Conducting a Motor-Starting Analysis in I&CPS |  | Brown -- Ch 9 |  | Tanug | 3002.7 | 2015 | 18 | Sponsor Ballot: Invitation [Click to view open invitations in myProject] New ballot group being formed, invitation to close 5/13/15 | PAR approved in 2008; 2-yr ext approved 2012; 1-yr ext approved 2014
RP for Conducting a Harmonic-Analysis of I&CPS |  | Brown -- Ch 10 |  | JJ | 3002.8 | 2015 | 19 | Sponsor Ballot: Comment resolution Ballot closed 10 Mar 2015 | PAR approvedin 2008; 2-yr ext granted in 2012; 1-yr ext 2014 Invite closed 12 June 2014 no legal review or copyright issues
RP for Conducting a Switching-Transient Studies of I&CPS |  | Brown -- Ch 11 |  | Dave Shipp | 3002.9 | — | 20 | No PAR (admin w/d) | PAR was active 2008-2014; ext req disapproved Dec 2014 Draft in template (final) | PAR submitted by Lisa and shared with Farrokh. Farrokh to submit to NesCom
RP for Conducting a Cable-Ampacity and Sizing Analysis of I&CPS |  | Brown -- Ch 13 |  |  | 3002.1 | — | 21 | No PAR | Issue PAR Draft in template (final)
RP for Conducting a Cable Grounding / Earthing Analysis of I&CPS |  | New |  |  | 3002.11 | — | 22 | No PAR | Issue PAR
RP for Analyzing Voltage Sags in I&CPS |  | Gold -- Ch 9 |  |  | 3002.12 | — | 23 | No PAR | Draft in template (final) | Bob isn't sure this project belongs in this group.
RP for Analyzing DC Auxiliary Power Systems in I&CPS |  | Brown -- Ch 16 |  |  | 3002.13 | — | 24 | No PAR | Issue PAR Draft in template (final)
Recommended Method for Calculating AC Short-Circuit Currents, in Accordance with ANSI Standards, in I&CPS |  | Violet -- Ch 9 |  |  | 3002.14 | — | 25 | No PAR | ON HOLD Draft in template (final)
Recommended Method for Calculating Unbalanced AC Short-Circuit Currents in I&CPS |  | Violet -- Ch 11 |  |  | 3002.15 | — | 26 | No PAR | Issue PAR Draft in template (final)
Recommended Method for Calculating AC Short-Circuit Currents, Under International Standards, in I&CPS |  | Violet -- Ch 12 |  |  | 3002.16 | — | 27 | No PAR | ON HOLD Draft in template (final)
Moved Material | Inherited Material
PAR
Brown -- Ch 12 | Gold -- Ch 9
Brown -- Ch 14 | Red -- Ch 4
Brown -- Ch 15 | Buff -- Ch 2

## PS Grounding WG
Working Group Name: |  | Power Systems Grounding WG
Working Group Chair: |  | Massimo Mitolo
Working Group Vice Chair: |  | Bob Schuerger
Working Group Secretary: |  | Claudio Mardegan
Covers material from Color Book(s): |  | Green and Emerald
Summary: 8 Ballot Documents (PARS) |  | Source Material | Project Chair | PAR Number | PAR Exp | Index # | Status/comments | Additional notes | LP notes
RP for the System Grounding of I&CPS |  | Green -- Ch 1 | Sergio Panetta | 3003.1 | 2016 | 28 | WG review | PAR approved in 2008; 2-yr ext approved in 2012, 2014 Carey's intern to put material in template | [Tom Baldwin old proj chair; Sergio Panetta new Proj Chair as of Oct14.]
RP for Equipment Grounding and Bonding in I&CPS |  | Green -- Ch 2 |  | 3003.2-2014 |  | 29 | Published | Appr 21 Aug 2014; Pub 10 Oct 2014 Active through 2024
RP for Static-Discharge Protection Grounding of I&CPS |  | Green -- Ch 3 |  | 3003.3 | — | 30 | No PAR | Draft in template
RP for Lightning Protection Grounding of I&CPS |  | Green -- Ch 3 |  | 3003.4 | — | 31 | No PAR | Draft in template
RP for Connecting the Grounding System of I&CPS to Earth |  | Green -- Ch 4 |  | 3003.5 | — | 32 | No PAR | Draft in template
RP for Analyzing and Solving Power Quality Problems in I&CPS |  | Emerald -- Ch 4 |  | 3003.6 | — | 33 | No PAR | Draft in template
RP for the Powering and Grounding of Telecommunications, Information Technology and Distributed Computers in I&CPS |  | Green -- Ch 5; Emerald -- Ch 9 |  | 3003.7 | — | 34 | No PAR | Draft in template
RP for Grounding and Wiring Methods to Minimize the Impact of Noise on Control Systems in Industrial and Commercial Facilities |  | Emerald -- Ch 10 |  | 3003.8 | — | 35 | No PAR | Draft in template
RP for Grounding of Separately Derived Systems |  | Emerald -- Ch 7 |  | 3003.9 | — |  | No PAR |  | Oct14: Bob Schuerger suggested a new dot standard for Emerald Ch 7. WG will work on scope/purpose for this RP
Inherited Material | PAR
Brown -- Ch 14
Red -- Ch 7
Orange -- Ch 7
White -- Ch 6

## Protection WG
Working Group Name: |  | Protection and Coordination WG
Covers material from Color Book(s): |  | Buff and Blue
Working Group Chair: |  | Rasheek Rifaat
rasheek.rifaat@jacobs.com
Summary: 13 Ballot Documents (PARs)
Document Title |  | Source Material | Project Chair | PAR Number | PAR Exp | Index # | Status |  |  | Additional notes |  |  | LP notes
|  | (link to source material in Mentor) | (link to email address) | (link to PAR in myProject or pub std in Mentor) |  |  |  | MEC | Ballot Group |  | MEC | Ballot Group
RP for the Application of Instrument Transformers in I&CPS |  | Buff -- Ch 3 | Louie Powell | 3004.1-2013 |  | 36 | Published |  |  | Appr 6 Feb 2013; Pub 6 May 2013 Active through 2023
RP for the Application of Protective Relays in I&CPS |  | Buff -- Ch 4 | Dan Ransom/ Chuck Mozina | 3004.2 | — | 37 | No PAR |  |  | Draft in template To start project after 3004.10 is complete | Dan Ransom taking over (Mozina will help)
RP for the Application of Low-Voltage Fuses in I&CPS |  | Buff -- Ch 5 | Dan Neeser | 3004.3 | 2016 | 38 | Draft development |  |  | 1-yr ext granted in 2013; 2-yr ext 2014 May 2014: Per Dan, ready for ballot; draft to Rasheek. Per Rasheek, to circulate draft to the WG for review before ballot. | Per Rasheek (Oct14), changes were made to the first draft. Sent to WG 10/5/14. Goal to ballot in Nov. [Final WG circulation, comments through 10/15/14 then on the ballot.] Sent email w/link to Mentor, instrux to request PAR ext on 10/6/14.
RP for the Application of High-Voltage Fuses in I&CPS |  | Buff -- Ch 6 | Carey Cook | 3004.4 | 2017 | 39 | Draft development |  |  |  | Goal to send to WG review before May 2015
RP for the Application of Low-Voltage Circuit Breakers in I&CPS |  | Buff -- Ch 7; Blue -- Ch 4, 6 | Ed Larsen | 3004.5-2014 |  | 40 | Published |  |  | Appr 21 Aug 2014; Pub 6 Feb 2015 Active through 2024
RP for Ground-Fault Protection of I&CPS |  | Buff -- Ch 8 | Claudio Mardegan | 3004.6 | — | 41 | No PAR |  |  | Draft in template | Claudio sent rough draft to Rasheek. Once Claudio and Rasheek agree, will be sent to the WG review. To be circulated in early Nov. Needs PAR. SB ballot before May 2015
RP for Conductor Protection in I&CPS |  | Buff -- Ch 9 | Ed Larsen | PAR 3004.7 | 2015 | 42 | Draft development |  |  | Draft in template Ed to start on 3004.7 after 3004.5 is published | Ed activated WG as of today, 10/5/14. WG will have draft w/comment matrix (Ed's comments) by end of month. Comments back by end Nov. Schedule WG mtg in Dec. Ed will keep in the old template. Ed will use email instead of Mentor. FIGURES from BUFF that Ed wants to use
RP for Motor Protection in I&CPS |  | Buff -- Ch 10 | Lorraine Padden | 3004.8 | 2016 | 43 | Draft development |  |  | 2-yr ext granted 2014; Still in development but close to ballot. | Final revision w/sub WG for motor protection. Hopefully ready for WG circulation before the end of the year. Should be in good shape by time of WG review. Sent email w/link to Mentor, instrux to request PAR ext on 10/6/14.
RP for Transformer Protection in I&CPS |  | Buff -- Ch 11 | Dan Ransom | 3004.9 | 2015 | 44 | Draft development |  |  | Draft in template and in progress. New diagrams and photos are being developed. | Does Dan need help with graphics/template?
RP for Generator Protection in I&CPS |  | Buff -- Ch 12 | Chuck Mozina | 3004.1 | 2016 | 45 | Draft development |  |  | 2-yr ext granted in 2012, 2014 Draft is complete; to be circulated among the WG. | Per Rasheek (Oct14), Chuck says the first draft is complete, needs work. Hope to get to WG in Nov. Chuck sent Rasheek a draft a few days ago (10/5/14). Sent to the WG; to ballot before May 2015. Sent email w/link to Mentor, instrux to request PAR ext on 10/6/14.
RP for Bus and Switchgear Protection in I&CPS |  | Buff -- Ch 13 | Marcelo Valdes | 3004.11 | 2016 | 46 | Draft development |  |  | 2-yr ext granted in 2012, 2014 Draft is complete; to be circulated among the WG. | 1st draft; needs more work on medium voltage and switchgear. Looking for others to help complete draft to WG review. Not ready for WG. Sent email w/link to Mentor, instrux to request PAR ext on 10/6/14.
RP for Service Supply Line Protection in I&CPS (C37.95) |  | Buff -- Ch 14 | Bob Hoeroff | 3004.12 | — | 47 | No PAR |  |  | Draft in template | Hold off on submitting PAR request until draft is ready.
RP for Overcurrent Coordination of I&CPS |  | Buff -- Ch 15 | Claudio Mardegan | 3004.13 | 2015 | 48 | Draft development |  |  | Draft in template | Per Rasheek (Oct14), there may be a change in Project Chair. Claudio will now jump in and help since he is finished w/grounding one. [Nov14-change in Proj Chair.]
Moved Material | Inherited Material |  | Status
Buff -- Ch 2 | Orange -- Ch 6 |  | PAR
Buff -- Ch 16 | Brown -- Ch 15 |  | Published
Blue -- Ch 7 | Red -- Ch 5
Gray -- Ch 9

## EmergencyStand-By Power WG
Working Group Name: |  | Emergency, Stand-By Power and Energy Management Systems WG
Covers material from Color Book(s): |  | Orange and Bronze
Working Group Chair: |  | Joe Weber
joe.weber@emerson.com
Summary: 10 Ballot Documents (PARs)
Document Title |  | Source Material | Project Chair | PAR Number | PAR Exp | Index # | Status | Additional notes |  |  | LP notes
|  | (link to source material in Mentor) | (link to email address) | (link to PAR in myProject or pub std in Mentor) |  |  |  |  | MEC | Ballot Group
RP for Determining the Need for Emergency and Stand-By Power Systems in Industrial and Commercial Facilities |  | Orange -- Ch 3, 9 | Marcelo Algrain | 3005.1 | — | 49 | No PAR | Draft in template - click to link to draft in Mentor
RP for the Application of Generator Systems for use in Emergency and Stand-By Power Systems |  | Orange -- Ch 4 | Herb Dougherty/ Dennis Darling | 3005.2 | — | 50 | No PAR | Draft in template - click to link to draft in Mentor
RP for the Application of Stored-Energy Systems for use in Emergency and Stand-By Power Systems |  | Orange -- Ch 5 | Co-Chair is needed | 3005.3 | — | 51 | Withdrawn PAR (Dec 2014) | Draft in template - click to link to draft in Mentor |  |  | PAR was active 2008-2014; Draft 1 (June 2010) in Mentor; Kelly O'Donnell does not have time; need a new project chair.
RP for Design and Operational Considerations for Improving the Reliability of Emergency and Stand-By Power Systems |  | Orange -- Ch 10 | Co-Chair is needed | 3005.4 | — | 52 | New PAR request on the June 2015 NesCom agenda | Draft development - click to link to Mentor - IEEE P3005.4/D1 | X |  | PAR was active 2008-2014; w/d 2014. Mod PAR for title change approved Dec 2014. MEC was completed in 2013 - comments about missing content. Draft needs WG review.
RP for the Energy Management of I&CPS |  | Bronze -- Ch 2, 4 | Wei-Jen Lee | 3005.5 | — | 53 | No PAR | Draft in template - click to link to draft in Mentor |  |  | Wei-jen is working on the draft.
RP for Conducting Economic Analysis Studies to Reduce Energy Costs of I&CPS |  | Bronze -- Ch 3 | Co-Chair is needed | 3005.6 | — | 54 | No PAR | Draft in template - click to link to draft in Mentor
RP for the Application of Metering for Energy Management of I&CPS |  | Bronze -- Ch 6 | Jim Harvey | 3005.7 | — | 57 | New PAR request on the June 2015 NesCom agenda | Draft development - click to link to draft in Mentor |  |  | PAR was active 2008-2014; w/d 2014.
RP for the Energy Management of Motors and Other Electrical Equipment in I&CPS |  | Bronze -- Ch 5 | Co-Chair is needed | 3005.8 | — | 55 | No PAR | Draft in template - click to link to draft in Mentor
RP for the Energy Management of Lighting Systems in I&CPS |  | Bronze -- Ch 7 | Co-Chair is needed | 3005.9 | — | 56 | No PAR | Draft in template - click to link to draft in Mentor
RP for the Application of Distributed Generation to I&CPS |  | Bronze -- Ch 8 | Herb Wittal | 3005.10 | — | 58 | No PAR | Draft in template - click to link to draft in Mentor
Moved Material | Inherited Material |  | Status
Orange -- Ch 6 | White -- Ch 5 |  | PAR
Orange -- Ch 7 | Red -- Ch 14 |  | Published
Orange -- Ch 8

## Reliability WG
Working Group Name: |  | Power Systems Reliability WG
Covers Material from Color Book(s): |  | Gold
Working Group Chair: |  | Bob Arno
robert.arno@exelisinc.com
Summary: 9 Ballot Documents (PARs)
Document Title |  | Source Material | Project Chair | PAR Number | PAR Exp | Index # | Status | Additional notes | LP notes
|  | (link to source material in Mentor) | (link to email address) | (link to PARs in myProject or pub std in Mentor)
RP for Reliability Planning and Design of I&CPS |  | Gold -- Ch 3 |  | 3006.1 | — | 59 | No PAR | Draft in template (final check) | Should draft in template be posted to Mentor?
RP for Evaluating the Reliability of Existing I&CPS |  | Gold -- Ch 4 | Tim Coyle | 3006.2 | 2017 | 60 | WG review of draft | Click to link to Mentor: Draft 3 of IEEE P3006.2 | Draft is posted on Mentor; WG reviewing D3 as of April 2015.
RP for Determining the Impact of Preventive Maintenance on the Reliability of I&CPS |  | Gold -- Ch 5 | Bob Schuerger | 3006.3 | 2017 | 61 | Draft development | Draft in template (final check) | To be harmonized with IEEE P3006.3; what was published in 3007.2 vs what will be published in 3006.3; Bob Schuerger to handle coordination so there is no overlap. Should draft in template be posted to Mentor?
RP for Determining the Impact of Emergency and Standby Power Systems on the Reliability of I&CPS |  | Gold -- Ch 6 |  | 3006.4 | — | 62 | No PAR | Draft in template (final check) | Should draft in template be posted to Mentor?
RP for the Use of Probability Methods for Conducting a Reliability Analysis of I&CPS |  | Gold -- Ch 2 | Masoud Pourali | 3006.5-2014 |  | 63 | Published | Appr 10 Dec 2014; Pub 17 Feb 2015 Active through 2024
RP for Reliability Compliance Testing of I&CPS and Equipment |  | Gold -- Ch 9 |  | 3006.6 | — | 64 | No PAR
RP for Determining the Reliability of "7 x 24" Continuous Power Systems in Industrial and Commercial Facilities |  | Gold -- Ch 8 | Bob Schuerger | 3006.7-2013 |  | 65 | Published | Appr 6 Mar 2013; Pub 5 Apr 2013 Active through 2023
RP for Analyzing Reliability Data for Equipment Used in I&CPS |  | Gold -- Ch 10 | Bob Arno | 3006.8 | 2016 | 66 | Draft development | 2-yr ext granted in 2012, 2014 | Is this draft ready for MEC? PAR approved 2008 WG waiting for analysis of failure data to be released to public; data to be sent to committee for review.
RP for Collecting Data for Use in Reliability, Availability, and Maintainability Assessments of I&CPS |  | Gold -- Ch 11 |  | 3006.9-2013 |  | 67 | Published | Appr 6 March 2013; Pub 22 April 2013 Active through 2023
Moved Material | Inherited Material |  | Status
Gold -- Ch 9 | Brown -- Ch 12 |  | PAR
Published
Vice President - Neal Dowling

## Operations WG
Working Group Name: |  | Power Systems Maintenance, Operation, and Safety WG
Covers Material from Color Book(s): |  | Yellow
Working Group Chair: |  | Dennis Neitzel
Dennis.Neitzel@avotraining.com
Summary: 3 Ballot Documents (PARs)
Document Title |  | Source Material | Project Chair | PAR Number | PAR Exp | Index # | Status | Additional notes | LP notes
|  | (link to published source material in Mentor) |  | (link to PARs in myProject or pub std in Mentor)
RP for the Operation and Management of I&CPS |  | Yellow -- Ch 2, 3, 4 |  | 3007.1-2010 |  | 68 | Published | Appr 8 Dec 2010; Pub 19 Jan 2011 Active through 2020 | Revision must be approved by 31 Dec 2020 in order for standard to remain active. Per Dennis May 2015: WG will review standard to see if revision is needed.
RP for the Maintenance of I&CPS |  | Yellow -- Ch 5, 6 |  | 3007.2-2010 |  | 69 | Published | Appr 30 Sept 2010; Pub 10/27/2010 Active through 2020 | Revision must be approved by 31 Dec 2020 in order for standard to remain active. To be harmonized with IEEE P3006.3; what was published in 3007.2 vs what will be published in 3006.3; Bob Schuerger to handle coordination so there is no overlap. Per Dennis May 2015: WG will review standard to see if revision is needed.
RP for Electrical Safety of I&CPS |  | Yellow -- Ch 7, 8, 9, 10, 11, 12 |  | 3007.3-2012 |  | 70 | Published | Appr 6 Feb 2012; Pub 12 Apr 2012 Active through 2022 | Per Dennis May 2015: Will subit rev PAR within the next few months. Revision needed to make consistent w/OSHA 1910.269 (April 11, 2014) and NFPA 70E-2015
Inherited Material | Status
Gold -- Ch 5 | PAR
Orange -- Ch 8 | Published
Buff -- Ch 16
Blue -- Ch 7

## Summary
Working Group | Number | Proposed New Name | Count
Eng of I&CPS WG | 3000 | Recommended Practice for the Engineering of Industrial and Commercial Power Systems | 0
Working Group | Number | Proposed New Name | Count
PS Design Editorial WG | 3001.1 | Recommended Practice for the Planning of Industrial and Commercial Power Systems | 1
PS Design Editorial WG | 3001.2 | Recommended Practice for Evaluating the Electrical Service Requirements of Industrial and Commercial Power Systems | 2
PS Design Editorial WG | 3001.3 | Recommended Practice for the Design of Industrial and Commercial Power Systems | 3
PS Design Editorial WG | 3001.4 | Recommended Practice for Estimating the Costs of Industrial and Commercial Power Systems | 4
PS Design Editorial WG | 3001.5 | Recommended Practice for the Application of Power Distribution Apparatus in Industrial and Commercial Power Systems | 5
PS Design Editorial WG | 3001.6 | Recommended Practice for the Expansion, Modernization, and Rehabilitation of Industrial and Commercial Power Systems | 6
PS Design Editorial WG | 3001.7 | Recommended Practice for the Application of Communication and Signaling Systems used in Industrial and Commercial Power Systems | 7
PS Design Editorial WG | 3001.8 | Recommended Practice for the Instrumentation and Metering of Industrial and Commercial Power Systems | 8
PS Design Editorial WG | 3001.9 | Recommended Practice for the Lighting of Industrial and Commercial Facilities | 9
PS Design Editorial WG | 3001.10 | Recommended Practice for Electric Space Conditioning of Industrial and Commercial Facilities | Killed
PS Design Editorial WG | 3001.11 | Recommended Practice for the Application of Controllers and Automation to Industrial and Commercial Power Systems | 11
Working Group | Number | Proposed New Name | Count
PS Analysis Editorial WG | 3002.1 | Recommended Practice for the System Modeling and Simulation of Industrial and Commercial Power Systems as a Precursor to Conducting System Studies | 12
PS Analysis Editorial WG | 3002.2 | Recommended Practice for Conducting a Load Flow Analysis of Industrial and Commercial Power Systems | 13
PS Analysis Editorial WG | 3002.3 | Recommended Practice for Calculating AC Short Circuit Currents in Industrial and Commercial Power Systems | 14
PS Analysis Editorial WG | 3002.4 | Recommended Practice for Calculating AC Short-Circuit Currents, Both With and Without AC Delay in Industrial and Commercial Power Systems | 15
PS Analysis Editorial WG | 3002.5 | Recommended Practice for Conducting an Arc-Flash Analysis of Industrial and Commercial Power Systems | 16
PS Analysis Editorial WG | 3002.6 | Recommended Practice for Conducting a Transient Stability Analysis of Industrial and Commercial Power Systems | 17
PS Analysis Editorial WG | 3002.7 | Recommended Practice for Conducting a Motor-Starting Analysis in Industrial and Commercial Power Systems | 18
PS Analysis Editorial WG | 3002.8 | Recommended Practice for Conducting a Harmonic Analysis of Industrial and Commercial Power Systems | 19
PS Analysis Editorial WG | 3002.9 | Recommended Practice for Conducting a Switching-Transient Analysis of Industrial and Commercial Power Systems | 20
PS Analysis Editorial WG | 3002.1 | Recommended Practice for Conducting Cable-Ampacity and Sizing Analysis of Industrial and Commercial Power Systems | 21
PS Analysis Editorial WG | 3002.11 | Recommended Practice for Conducting a Cable Grounding / Earthing Analysis of Industrial and Commercial Power Systems | 22
PS Analysis Editorial WG | 3002.12 | Recommended Practice for Analyzing Voltage Sags in Industrial and Commercial Power Systems | 23
PS Analysis Editorial WG | 3002.13 | Recommended Practice for Analyzing DC Auxiliary and Battery Systems for Industrial and Commercial Power Systems | 24
PS Analysis Editorial WG | 3002.14 | Recommended Method for Calculating AC Short-Circuit Currents, in Accordance with ANSI Standards, in Industrial and Commercial Power Systems | 25
PS Analysis Editorial WG | 3002.15 | Recommended Method for Calculating Unbalanced AC Short-Circuit Currents in Industrial and Commercial Power Systems | 26
PS Analysis Editorial WG | 3002.16 | Recommended Method for Calculating AC Short-Circuit Currents, Under International Standards, in Industrial and Commercial Power Systems | 27
Working Group | Number | Proposed New Name | Count
PS Grounding Editorial WG | 3003.1 | Recommended Practice for the System Grounding of Industrial and Commercial Power Systems | 28
PS Grounding Editorial WG | 3003.2 | Recommended Practice for Equipment Grounding and Bonding in Industrial and Commercial Power Systems | 29
PS Grounding Editorial WG | 3003.3 | Recommended Practice for Static Discharge Protection Grounding of Industrial and Commercial Power Systems | 30
PS Grounding Editorial WG | 3003.4 | Recommended Practice for Lightning Protection Grounding of Industrial and Commercial Power Systems | 31
PS Grounding Editorial WG | 3003.5 | Recommended Practice for Connecting the Grounding System of Industrial and Commercial Power Systems to Earth | 32
PS Grounding Editorial WG | 3003.6 | Recommended Practice for Analyzing and Solving Power Quality Problems in Industrial and Commercial Power Systems | 33
PS Grounding Editorial WG | 3003.7 | Recommended Practice for the Powering and Grounding of Telecommunications, Information Technology, and Distributed Computers in Industrial and Commercial Power Systems | 34
PS Grounding Editorial WG | 3003.8 | Recommended Practice for Grounding and Wiring Methods to Minimize the Impact of Noise on Control Systems in Industrial and Commercial Facilities | 35
Working Group | Number | Proposed New Name | Count
Protection and Coordination Editorial WG | 3004.1 | Recommended Practice for the Application of Instrument Transformers in Industrial and Commercial Power Systems | 36
Protection and Coordination Editorial WG | 3004.2 | Recommended Practice for the Application of Protective Relays in Industrial and Commercial Power Systems | 37
Protection and Coordination Editorial WG | 3004.3 | Recommended Practice for the Application of Low-Voltage Fuses in Industrial and Commercial Power Systems | 38
Protection and Coordination Editorial WG | 3004.4 | Recommended Practice for the Application of High-Voltage Fuses in Industrial and Commercial Power Systems | 39
Protection and Coordination Editorial WG | 3004.5 | Recommended Practice for the Application of Low-Voltage Circuit Breakers in Industrial and CommercialPower Systems | 40
Protection and Coordination Editorial WG | 3004.6 | Recommended Practice for Ground-Fault Protection of Industrial and Commercial Power Systems | 41
Protection and Coordination Editorial WG | 3004.7 | Recommended Practice for Conductor Protection in Industrial and Commercial Power Systems | 42
Protection and Coordination Editorial WG | 3004.8 | Recommended Practice for Motor Protection in Industrial and Commercial Power Systems | 43
Protection and Coordination Editorial WG | 3004.9 | Recommended Practice for Transformer Protection in Industrial and Commercial Power Systems | 44
Protection and Coordination Editorial WG | 3004.10 | Recommended Practice for Generator Protection in Industrial and Commercial Power Systems | 45
Protection and Coordination Editorial WG | 3004.11 | Recommended Practice for Bus and Switchgear Protection in Industrial and Commercial Power Systems | 46
Protection and Coordination Editorial WG | 3004.12 | Recommended Practice for Service Supply Line Protection in Industrial and Commercial Power Systems | 47
Protection and Coordination Editorial WG | 3004.13 | Recommended Practice for Overcurrent Coordination of Industrial and Commercial Power Systems | 48
Working Group | Number | Proposed New Name | Count
Emergency and Stand-By Power Editorial WG | 3005.1 | Recommended Practice for Determining the Need for Emergency and Stand-By Power Systems in Industrial and Commercial Facilities | 49 | NEW
Emergency and Stand-By Power Editorial WG | 3005.2 | Recommended Practice for the Application of Generator Systems for use in Emergency and Stand-By Power Systems | 50
Emergency and Stand-By Power Editorial WG | 3005.3 | Recommended Practice for the Application of Stored-Energy Systems for use in Emergency and Stand-By Power Systems | 51
Emergency and Stand-By Power Editorial WG | 3005.4 | Recommended Practice for Improving the Reliability of Emergency and Stand-By Power Systems | 52
Emergency and Stand-By Power Editorial WG | 3005.5 | Recommended Practice for the Energy Management of Industrial and Commercial Power Systems | 53
Emergency and Stand-By Power Editorial WG | 3006.6 | Recommended Practice for Conducting Economic Analysis Studies to Reduce Energy Costs of Industrial and Commercial Power Systems
Emergency and Stand-By Power Editorial WG | 3005.8 | Recommended Practice for the Energy Management of Motors and Other Electrical Equipment in Industrial and Commercial Power Systems
Emergency and Stand-By Power Editorial WG | 3005.9 | Recommended Practice for the Energy Management of Lighting Systems in Industrial and Commercial Power Systems | 54
Emergency and Stand-By Power Editorial WG | 3005.7 | Recommended Practice for the Application of Metering for Energy Management of Industrial and Commercial Power Systems | 55
Emergency and Stand-By Power Editorial WG | 3005.10 | Recommended Practice for the Application of Distributed Generation to Industrial and Commercial Power Systems | 56
Working Group | Number | Proposed New Name | Count
PS Reliability Editorial WG | 3006.1 | Recommended Practice for Reliability Planning and Design of Industrial and Commercial Power Systems | 59
PS Reliability Editorial WG | 3006.2 | Recommended Practice for Evaluating the Reliability of Existing Industrial and Commercial Power Systems | 60
PS Reliability Editorial WG | 3006.3 | Recommended Practice for Determining the Impact of Preventative Maintenance on the Reliability of Industrial and Commercial Power Systems | 61
PS Reliability Editorial WG | 3006.4 | Recommended Practice for Determining the Impact of Emergency and Standby Power Systems on the Reliability of Industrial and Commercial Power Systems | 62
PS Reliability Editorial WG | 3006.5 | Recommended Practice for the Use of Probability Methods for Conducting a Reliability Analysis of Industrial and Commercial Power Systems | 63
PS Reliability Editorial WG | 3006.6 | Recommended Practice for Reliability Compliance Testing of Emergency and Standby Power Systems | 64
PS Reliability Editorial WG | 3006.7 | Recommended Practice for Determining the Reliability of "7 x 24" Continuous Power Systems in Industrial and Commercial Facilities | 65 | NEW
PS Reliability Editorial WG | 3006.8 | Recommended Practice for Analyzing Reliability Data for Equipment Used in Industrial and Commercial Power Systems | 66 | NEW
PS Reliability Editorial WG | 3006.9 | Recommended Practice for Collecting Data for Use in Reliability, Availability, and Maintainability Assessments of Industrial and Commercial Power Systems | 67 | NEW
Working Group | Number | Proposed New Name | Count
PS Maintenance, Operations and Safety Editorial WG | 3007.1 | Recommended Practice for the Operation and Management of Industrial and Commercial Power Systems | 68
PS Maintenance, Operations and Safety Editorial WG | 3007.2 | Recommended Practice for the Maintenance of Industrial and Commercial Power Systems | 69
PS Maintenance, Operations and Safety Editorial WG | 3007.3 | Recommended Practice for Electrical Safety of Industrial and Commercial Power Systems | 70

## Scratch
Red | 1 Overview | Keep
2 System Planning
| 3 Voltage Considerations | Move
4 Short Circuit Current Calculations (To Analysis)
| 5 Application & Coordination of Protective Devices (To Protection) | Kill
6 Surge Voltage Protection
7 Grounding (To Grounding)
8 Power Factor & Related Considerations
9 Harmonics in Power Systems
10 Power Switching, Transformation & Motor Control Apparatus
11 Instruments & Meters
12 Cable Systems
13 Busways
14 Electrical Conservation through Energy Management
15 Industrial Substations: Plant-utility Interface Considerations
16 Cost Estimating of Industrial Power Systems
17 A Selected Sources for cost-estimating Information
Annex A Power System Device Function Numbers
Green | 1 System Grounding
2 Equipment Grounding
3 Static & Lighting Protection grounding
4 Connection to Earth
5 Sensitive Electronic Equipment Grounding
Gray | 1 Introduction
2 Load Characteristics
3 Voltage Considerations
4 Power Sources & Distribution Systems
5 Power Distribution Apparatus
6 Controllers
7 Services, Vaults, & Electrical Equipment Rooms
8 Wiring Systems
9 System Protection & Coordination (To Protection)
10 Lighting
11 Electric Space Conditioning
12 Transportation
13 Communication & Signal System Planning
14 Facility Automation
15 Expansion, Modernization, and Rehabilitation
16 Speical Requirements by Occupancy
17 Electrical Energy Management
Buff | 1 First Principles
2 Short Circuit Calculations (To Analysis)
3 Instrument Transformers
4 Selection & Appication of Protective Relays
5 Low Voltage Fuses
6 High Voltage Circuit Breakers
7 Low Voltage Circuit Breakers
8 Ground Fault Protection
9 Conductor Protection
10 Motor Protection
11 Transformer Protection
12 Generator Protection
13 Bus & Switchgear Protection
14 Service Supply Line Protection
15 Overcurrent Coordination
16 Maintenance, Testing and Calibration (To Operations)
Brown | 1 Overview
2 Applications of Power System Analysis
3 Analytical Procedures
4 System Modeling
5 Computer Soutions and Systems
6 Load Flow Studies
7 Short-Circuit Studies
8 Stability studies
9 Motor-Starting Studies
10 Harmonic Analysis Studies
11 Switching Transient Studies
12 Reliability Studies (To Reliability)
13 Cable Amacity Studies
14 Ground Mat Studies (To Grounding)
15 Coordination Studies (To Protection)
16 DC Auxiliary Power System Analysis
Orange | 1 Scope
2 Definitions
3 General Need Guidelines
4 Generator & Electric Utility Systems
5 Stored Energy Systems
6 Protection (To Protection)
7 Grounding (To Grounding)
8 Maintenance (To Operations)
9 Specific Industry Applications
10 Design & Operations Considerations for Improving the Reliability of Emergency Power Systems
Gold | 1 Introduction
2 Planning & Design
3 Summary of Equipment Reliability Data
4 Evaluating & Improving the Reliability of an Existing Plant
5 Electrical Preventive Maintenance
6 Emergency & Standby Power
7 Examples of Reliability Analysis & Cost Evaluation
8 Basic Concepts of reliability Analysis by Probability Methods
9 Voltage Sag Analysis (To Analysis)
10 Reliability Compliance Testing for Emergency and Standby Ower Systems
Appendices A -- M
Violet | 1 Introduction
2 Description of Short-Circuit Current
3 Calculating Technique
4 Calculating Short Curcuit Currents Without AC Delay
5 Calculating Short-Circuit Currents with Contributions for Synchronous Machines
6 Calculating Short-Circuit Currents with Contributions from Induction Motors
7 Capacitor Short Circuit Contribution
8 Calculating Short Curcuit Currents with Contributions from Regenerative Solid State Drivers
9 Calculating Short Circuit Currents in Accordnace with ANSI Standards
10 Short Circuit Equipment Duty Calculations
11 Calculating Unbalanced Short Circuit Currents
12 Related International Standards
Appendices A -- M
White | 1 Overview
2 Load Requirements & Energy Management
3 Electrical Power Distribution Systems
4 Planning for Patient Care
5 Emergency Power Systems (To Special PS Design)
6 Electrical Safety & Grounding (To Grounding)
7 Lighting
8 Communication & Signal Systems
9 Medical Equipment & Instrumentation
10 Health Care Renovations
Bronze
2 Organiziing for Energy Management
3 Translating Energy into Cost
4 Load Management
5 Energy Management for Motors, Systems, and Electrical Equipment
6 Metering for Energy Management
7 Energy Management for Lighting Systems
8 Congeneration
Annexes 5A -- 5I
Yellow | 1 Overview
2 Operating Diagram
3 System Management
4 System Control Responsibilities & Clearing Procedures
5 Maintenance Strategies
6 Maintenance testing Overview
7 Introduction to Electrical Safety
8 Establishing an Electrical Safety Program
9 Providing & Maintaining Electrically Safe Facilities
10 Safe Electrical Work Practices
11 Protective Equipment, Tools, and Methods
12 Safe Use of Electrical Equipment
Blue | 1 Overview
2 Definition & Acronyms
3 Rating and Testing
4 Specifi Application
5 Selective Coordination of Low Voltage circuit Breakers with Other Protective Devices
6 Special Purpose Curcuit Breakers
7 Acceptance and Maintance Requirements (To Operations)
Emerald | 1 Overview
2 Definitions
3 General Needs Guidelines
4 Fundamentals
5 Instrumentation
6 Site Survey and Site Power Analysis
7 Specification & Selection of Equipment and Materials
8 Recommended Design/Installation Practices
9 Telecommunications and Distributed Computing
Annex 9A
10 Case histories

## Sheet1 (hidden)
Choose a Color Book | Choose a Working Group
Blue Book | Blue Book Working Group
Bronze Book | Bronze Book Working Group
Brown Book | Brown Book Working Group
Buff Book | Buff Book Working Group
Emerald Book | Emerald Book Working Group
Gold Book | Gold Book Working Group
Gray Book | Gray Book Working Group
Green Book | Green Book Working Group
Orange Book | Orange Book Working Group
Red Book | Red Book Working Group
Violet Book | Violet Book Working Group
White Book | White Book Working Group
Yellow Book | Yellow Book Working Group
New

## MECs
Project Number | Editor | Staff Liaison | Mandatory Editorial Coordination (pre-ballot phase) |  | RAC Coord. Yes/No | Date Completed by Editor | GO or NO GO to ballot | Explanation for NO GO to ballot
|  |  | Date submitted | Due Date
P3001.9 | Lisa | Trish | 2010-05-31 | 2010-06-30
P3001.9 | Don | Lisa | 2012-02-28 | 2012-03-29 |  | 2012-04-05 | NO GO | Scope/Purpose/Legal/Trademarke/Ref
PC3001.11_D0 | MDT | Lisa | 2012-02-28 | 2012-03-29
PC3001.11_D1 | Don | lisa | 2012-10-19 | 2012-11-18 |  | 2012-11-26 | No Go | Title, normative references, absolute language review
P3002.2_D2 | Julie | Lisa | 2014-04-08 | 2014-05-08 |  | 2014-04-17 | No go | Possible missing content
P3002.3_D1 | Julie | Lisa | 2014-04-08 | 2014-05-08 |  | 2014-04-21 | Go? | Go only if copyright permission letters are not necessary.
P3002.8_D2 | Julie | Lisa | 2014-05-13 | 2014-06-12 |  | 2014-05-29 | Go
P3005.4 | Julie | Lisa | 2013-10-06 | 2013-11-05 |  | 2013-10-14 | No go | Missing content
P3006.5 | Julie | Lisa | 2013-09-26 | 2013-10-26 |  | 2013-09-30 | No go | Copyright, norm ref
Standard | Editor | Staff Liaison | Date to Legal | Date Due from Legal | Editor's req date | Date from Legal | Turnaround Days | < 3weeks? | year
P3001.11_D0 | MDT |  | 2012-03-06 | 2012-03-27 |  | 2012-03-26 | 20 | yes | 2012
P3001.9/D2 | CKB |  | 2010-08-12 | 2010-09-02 |  | 2010-09-15 | 34 | no | 2010
p3001.9_D3 | DM |  | 2012-04-03 | 2012-04-24 |  | 2012-04-24 | 21 | yes | 2012
Formulas:
Date Due from Legal = [Date to Legal]+21
Note on H1: NO GO to ballot should be reserved for changes to the title, scope, and purpose, if the proper draft numbering and labeling system is not used, if the proper copyright notices are not on the draft, copyright release letters not submitted or properly formatted, and/or if the draft is not complete, e.g., missing figures, missing tables, etc. See Style Manual 4.1.1, 4.1.2, 9.1, and 10.2 for further information on these areas.
Note on I1: Remember to cc the staff liaison on the comments emailed to the working group chair.
Note on E2: IEEE: This is pre programmed. DO NOT ALTER DATE!!!