## Slide 1: Executive Secretary Agenda Items March 2012
Date: 2012-03-12
Authors:

## Slide 2: Abstract
Executive Secretary had the following EC Agenda Items:
M5.13: EC Survey Results
M5.14: Status of Network Services RFP and Contract
M5.15: Future Venue Contract Status
M5.16: Geneva 2013 Expectation
M5.11: Workshop Status Update
F4.01: Network Services Contract Approval
F4.05: IEEE 802 EC Interim Teleconference
F9.01: Update on Upcoming Venues
F9.04: 802 EC November 2011 Workshop Update
F9.08: Executive Secretary Report
F9.09: 802 Membership Poll on Fees, Services, and Locations

## Slide 3: Monday EC Agenda

## Slide 4: 5.13 EC Survey Results
https://mentor.ieee.org/802-ec/dcn/12/ec-12-0014-00-00EC-802-ec-poll-fees-services-and-venue-location-workshop.ppt

## Slide 5: 5.14: Status of Network Services RFP and Contract
RFP Issued by email -- January 17, 2012
RFP Response by email – February 17, 2012
Response Review Period: February 17-24, 2012
Notification of vendor selected/notified: February 27, 2012
Contract Negotiation and Master Service Agreement: February 27-March 9, 2012
EC Executive Session -- Tues 1:30-2:30pm
3 year contract: expected to get final signatures from Verilan and IEEE Procurement by March 30, 2012

## Slide 6: 5.15: Future Venue Contract Status
Identified in Workshop spreadsheet:
https://mentor.ieee.org/802-ec/dcn/12/ec-12-0003-02-00EC-november-2011-ec-workshop-action-items.xls
See Tab WS11-2
  Trying to move a venue from 2014 to allow Singapore meeting to occur in 2014.
  Slots currently Open at
    2015 – March
    2017 – March and Nov
    2018 – March and Nov

## Slide 7: 5.16: Geneva 2013 Expectations
Draft MOU due this week
Working on Estimates for F&B:
  Do we want a Social?
  Do we use lunch to ensure a fee that all can pay?
No Hotel Block – List of Hotels on ITU List
Draft Budget next slide –
Possible choices:
  No evening meetings
  No F&B
  No Social
Possible budget reduces reserves:
  $300,000 may be needed for meeting

## Slide 8: Geneva Draft Budget:
Income: unknown – What fee to charge? Who will pay?
Shipping $ 8,000
Extra Security $ 9,000
Get 802 $ 52,500
Misc onsite $ 5,700
CCV Facility $ 39,965
CICG Facility $ 27,915
ITU Facility $ 2,255
Network $ 20,000
Mtg Planner fee $108,900
Financial Fees $ 18,288
Total expenses $288,073

## Slide 9: 5.11: Workshop Status Update
Status for Workshop has been updated and posted in EC-12:003r3
  https://mentor.ieee.org/802-ec/dcn/12/ec-12-0003-02-00EC-november-2011-ec-workshop-action-items.xls
Review Action item on Tuesday 6-7 in Waters Edge Board room.

## Slide 10: Friday, Closing EC Meeting
March 16, 2012
ExSec Agenda Items

## Slide 11: 4.01 Network Services Contract
Move to approve the Network Services Contract with Verilan
Move Rosdahl
2nd Heile
14-0-0 approved.

## Slide 12: 4.05: IEEE 802 EC Interim Teleconference
802 EC Interim Conference calls are 1-3PM ET on the first Tuesday of FEB, JUN and OCT. 2012: 02FEB, 05JUN, 02OCT 2013: 05FEB, 04JUN, 01OCT 2014: 04FEB, 03JUN, 07OCT

## Slide 13: 802 EC Interim Teleconference: June 5, 2012 1-3PM ET
Draft Agenda:
  Welcome/Intro/Approve Agenda - Nikolich 4 min
  Report: Single Sales Channel Update - Nikolich 3 min
  Report: Pending Appeal - 802.15.6 - Nikolich 3 min
  Report: Network Services Contract Status - Rosdahl 3 min
  Discussion: Meeting Manager Job Description
  and proposed rule changes - Rosdahl 30 min
  Report: July 2012 San Deigo Meeting Plans - Rosdahl 3 min
  Report: July 2013 Geneva Meeting Plans - Rosdahl 4 min
  Motion: 802.11 - Sponsor Ballot Completion - Kraemer 10 min
  Update: November Workshop Action items - Kraemer 15 min
  AOB 45 min

## Slide 14: 9.01: Update on Upcoming Venues
Geneva, July 2013
Singapore, March 2015
Future Venue Contract Status
  Identified in Workshop spreadsheet:
    https://mentor.ieee.org/802-ec/dcn/12/ec-12-0003-02-00EC-november-2011-ec-workshop-action-items.xls
  See Tab WS11-2
  Unable to get free date at Singapore – no need to move a venue from 2014 to allow Singapore meeting to occur in 2014.
  Slots currently Open at
    2017 – March and Nov
    2018 – March and Nov
  Move a 2016 Venue out in time to open a slot for a NonNA venue.

## Slide 15: 9.01 -- Site Visit for Geneva June 2012
IEEE 802 July 2013 Plenary Session – Geneva, Switzerland
Why Face To Face Events should conduct a site inspection to Geneva?
A properly conducted site inspection is a significant factor in ensuring a successful session. In particular when planning an event in a venue and location not previously used by the IEEE 802, the site inspection will accurately highlight both the positive and the negative aspects of a selected location that cannot be quantified by reviewing a facility's sales literature or meeting contracts alone.
Travelling to Geneva and meeting with the local ITU/CCIG/CCV representatives, will provide Face to Face Events the opportunity to evaluate all of the ITU/CICG/CCV facilities and services. The site inspection would include all the meeting space, meeting room layouts, network capabilities, AV/power requirements, F&B specifications, security, staffing( including special name badges coordination) , shipment arrangements and any other session considerations, including pricing and billing procedures.
By conducting meetings with facility representatives face to face we will be able to develop relationships that will be beneficial during final contract negotiations and onsite logistics as well as pinpoint potential problems and resolve them well ahead of the session, saving time and money.
Our site inspection experience and expertise act as invaluable tool in planning all aspects of the July 2013 IEEE 802 Plenary Session, we appreciate your keen consideration of this matter.

## Slide 16: 9.01 -- Motion to approve Geneva Site Inspection
Move to approve a Site inspection trip for no more than 4 people.
  The purpose of the trip includes:
    The site inspection would include all the meeting space, meeting room layouts, network capabilities, AV/power requirements, F&B specifications, security, staffing( including special name badges coordination) , shipment arrangements and any other session considerations, including pricing and billing procedures.
  Standard Travel expenses (e.g. Coach Class Air travel, local transport, food and lodging)
  Move: Rosdahl
  2nd:

## Slide 17: nNA Hosted Session Proposals
Marina Bay Sands Hotel
Singapore
March 7-13, 2015
Notes: Page <number>
        <footer>
<header>
<date/time>
<number>

## Slide 18: Singapore: March 7-13, 2015
We have hosted target for March 2015
We have finally received the STB grant payment
MBS is holding room-block & meeting rooms
Same facilities & concessions as March 2011
Modest price increase due to full operation
If STB & IDA will host again at ≥ level is t.b.d.
We have deposit in SG$ @ IEEE–Singapore
Will get formal proposals in the next weeks
Could have this plus others to decide in July
Notes: Page <number>
        <footer>
<header>
<date/time>
<number>

## Slide 19: 802 EC Next Steps Meeting Planner
Update nNA venue Host Guidelines on web
Send Host solicitation to 802-ALL & WGs
Seek active proposals for 2016, 2017, 2018
Plan for interim review to choose best 3
Invite Hosts to present their proposals in July
Plan for July member poll & selection review
Plan for venue selection by close of July EC if possible
Notes: Page <number>
        <footer>
<header>
<date/time>
<number>

## Slide 20: 9:04: 802 EC November 2011 Workshop Update
Action items that have not been completed

## Slide 21: Outstanding Action Items (1)
WS11-6--Gilb: Create a proposed plan for how the e-tools can go into open source.
  update to be provided in March plenary
WS11-7-Law: Setup a meeting to discuss with the SA–Open Application Interfaces, and Open source.
  waiting on item WS11-6
WS11-8-Diab: Identify a process with staff to prioritize and discuss Frame version transitions.
  ad hoc has been initialized in the CAG . will continue until 2 weeks after the SASB March series meetings complete March 29 .

## Slide 22: Outstanding Action Items (2)
WS11-12-ALL WG CHAIRS: Review attendance rolls and for all affiliations that are obviously not valid, should be reported to the SASB Secretary
  WG19 reports he has corrected one, still some older lists to check.
WS11-18-Gilb: Update the home page for the public vs EC information. Update the initial statement to match the Scope in the P&P.
  Feb-7-2012: Need to review intent from workshop minutes. Is this about public vs private information or providing a better website for use by the general public?

## Slide 23: Outstanding Action Items (3)
WS11-20-Kraemer: make a list of what 802 projects and standards that operate above layer 2.
  March 10-2012: More difficult and controversial than expected. Needs more discussion time in Waikoloa. Candidates include 802.21, 802.1X (management plane comprehends layer 3),others?
WS11-21-Jeffree: Internal statement – O&A about what the scope of projects in 802 are – ensure that it is consistent with P&P

## Slide 24: 9:08 Executive Secretary Report
Workshop Action items: track and push
July 2013 Geneva Plenary: Responsible for MOU
Future Venues:
  Work with Meeting Planner to find non-NA/Non-US Venues (At least one per year for 2016, 2017, 2018).
  Move a Venue in 2016 and 2018 to make space for non-NA/Non-US venue.
Find new teleconference tools for EC Interim Telecons.
Follow-up on IEEE Tools: - Tickets are tracking etc.
Follow-up on Contract completeness: tracking and pushing to get through the process.

## Slide 25: 9.09: 802 Membership Poll on Fees, Services, and Locations
See Separate Document

## Slide 26: References