## Slide 1: Proposal for IEEE 802 Nov 2020 Electronic Plenary
John D’Ambrosia,
Futurewei, U.S. Subsidiary of Huawei
ec-20-0139-02-00EC

## Slide 2: Meeting Dates (Oct- Dec)
6 Oct 2020 EC Teleconference
3 Nov 2020 EC Monthly Teleconference
Week of Nov 8 – Nov 2020 Plenary
  Normal 9 Nov EC Opening Mtg Proposed Fri, 6 Nov EC Opening Mtg
  Normal 13 Nov EC Closing Mtg Proposed Thurs, 19 Nov EC Closing Mtg
Nov 19 – Nov 21 – Technical Activities Board
1 Dec 2020 EC Monthly Teleconference
1 – 3 Dec 2020 SASB

## Slide 3: Proposed Plan
  9 October 2020 – PAR Announcement
  6 November 2020 - 802 EC Opening Mtg
  10 November 2020 - Submit comments against PARs
  17 November 2020 - Post responses to submitted comments against PARs
  19 November 2020 802 EC Closing Mtg (Consider PARs)

## Slide 4: Reference #1 Email motion, 6/10/20 -
Moved: Due to the change of the July 2020 Plenary Session due to
COVID-19 travel restrictions, suspend the following rules/procedures in the IEEE 802 LMSC Operations Manual From 11 June 2020 until 5 August 2020:
Suspend 4.1.3: Meetings
“The IEEE 802 LMSC meets in-person during plenary sessions.”
Suspend: 4.1.4 Procedure for limiting the length of the IEEE 802 sponsor meetings
d) “The opening IEEE 802 LMSC meeting shall start at 8:00 a.m. and end no later than 10:30 a.m. on Monday morning and the closing IEEE 802 LMSC meeting shall start at 1:00 p.m. and shall end no later than 6:00 p.m.
on Friday of the plenary session”
and replace with:
"For the July 2020 plenary session, the opening IEEE 802 LMSC meeting for the shall be held on 7/10/20 from 1:00-3:00 pm EDT and the closing IEEE 802 LMSC meeting shall be held on 7/24/20 from 1:00-5:00 pm EDT"
Suspend: 5. IEEE 802 LMSC sessions
"All Working Group meetings during each Plenary Session shall be exclusively in-person."
Moved: Gilb, seconded: D'Ambrosia
Background: An analysis of the rules can be found in:
https://mentor.ieee.org/802-ec/dcn/20/ec-20-0106-00-00EC-july-2020-plenary-proposal.odp
Consequences:
1) This is the first plenary of an even numbered year, so officer and appointed positions at the WG and the LMSC expire. Elections should be held and appointments made. For LMSC members, the affiliation and endorsement letters are required for confirmation.
2) Each WG and TAG Chair will determine via their agenda (already in WG P&P and by practice)
- Meetings during the plenary session that may be used for participation credit
- Number of meetings during the plenary session required to make 100% attendance
3) Note that a WG or TAG is not required to meet every day during the plenary session. Groups with many overlaps and limited "good"
teleconference time will have more days to hold meetings
4) Attendees will be able to gain, maintain and lose voting membership via attendance at the meetings during the week as if it were a face to face plenary.
5) As this is a plenary, no quorum is required for any WG meeting.
6) Study groups will need to be rechartered.
7) PARs will be handled via the process voted on during the June 2, 2020 call
8) Any IEEE 802 LMSC business not completed on 7/24/20 and PAR approvals will be taken up on the August 4, 2020 teleconference.
9) We have no ICAIDs or appeals to deal with during this meeting.

## Slide 5: Proposed #1 -
Moved: Due to the change of the Nov 2020 Plenary Session due to
COVID-19 travel restrictions, suspend the following rules/procedures in the IEEE 802 LMSC Operations Manual From 5 October 2020 until 20 November 2020:
:
Suspend 4.1.3: Meetings
“The IEEE 802 LMSC meets in-person during plenary sessions.”
Suspend: 4.1.4 Procedure for limiting the length of the IEEE 802 sponsor meetings
d) “The opening IEEE 802 LMSC meeting shall start at 8:00 a.m. and end no later than 10:30 a.m. on Monday morning and the closing IEEE 802 LMSC meeting shall start at 1:00 p.m. and shall end no later than 6:00 p.m.
on Friday of the plenary session”
and replace with:
"For the Nov 2020 plenary session, the opening IEEE 802 LMSC meeting for the shall be held on 06 November 2020 from 1:00-3:00 pm EDT and the closing IEEE 802 LMSC meeting shall be held on 19 November 2020 from 1:00-5:00 pm EDT"
Suspend: 5. IEEE 802 LMSC sessions
"All Working Group meetings during each Plenary Session shall be exclusively in-person."
Moved: D’Ambrosia, seconded: George Zimmerman
Background: An analysis of the rules can be found in:
https://mentor.ieee.org/802-ec/dcn/20/ec-20-0106-00-00EC-july-2020-plenary-proposal.odp
Consequences:
1) This is the first plenary of an even numbered year, so officer and appointed positions at the WG and the LMSC expire. Elections should be held and appointments made. For LMSC members, the affiliation and endorsement letters are required for confirmation.
2) Each WG and TAG Chair will determine via their agenda (already in WG P&P and by practice)
- Meetings during the plenary session that may be used for participation credit
- Number of meetings during the plenary session required to make 100% attendance
3) Note that a WG or TAG is not required to meet every day during the plenary session. Groups with many overlaps and limited "good"
teleconference time will have more days to hold meetings
4) Attendees will be able to gain, maintain and lose voting membership via attendance at the meetings during the week as if it were a face to face plenary.
5) As this is a plenary, no quorum is required for any WG meeting.
6) Study groups will need to be rechartered.
7) PARs will be handled via the process in “Proposed #2” - PARs to be considered for approval by the IEEE 802 LMSC during the closing IEEE 802 LMSC meeting 19 November 2020 electronic meeting
8) Any IEEE 802 LMSC business not completed on 19 November, 2020 will be taken up on the December 1, 2020 teleconference.
9) We have no ICAIDs or appeals to deal with during this meeting.

## Slide 6: Reference #2 – June 2, 2020 Teleconference – Motion #2
Due to the change of the July 2020 Plenary Session due to COVID-19 travel restrictions, suspend the following rules/procedures in the IEEE 802 LMSC Operations Manual From 11 June 2020 until 5 August 2020:
In Subclause 9.2, first paragraph
A complete proposed PAR and, if applicable, the criteria for standards development (CSD) statement, as described in Clause 14, shall be submitted to the IEEE 802 LMSC via the IEEE 802 LMSC email reflector for review no less than 30 days prior to the day of the opening IEEE 802 LMSC meeting of an IEEE 802 LMSC plenary session. The submittal message should include Internet links to the required submittal documents. Presence of the submittal message in the reflector archive (with time stamp) is evidence of delivery.
Subclause 9.3 Plenary Review
and be replaced with:
PARs to be considered for approval by the IEEE 802 LMSC during the 4 August 2020 electronic meeting shall pass through the following process:
The proposed PAR shall be available at a publicly accessible URL and an email sent to the IEEE 802 LMSC reflector that contains the URL required for viewing the PAR and associated documentation no later than 12 June 2020, AoE.
Working Groups, other than the proposing Working Group, shall express concerns to the proposing Working Group as soon as possible and shall submit comments to the proposing Working Group and the IEEE 802 LMSC by e-mail not later than 12 July 2020, AoE
The proposing Working Group shall post a response to commenting Working Group and to the IEEE 802 LMSC together with a Final PAR on a public website and circulate the relevant URL on the IEEE 802 LMSC reflector not later than 31 July 2020, AoE

## Slide 7: Proposed #2 -
Due to the change of the November 2020 Plenary Session due to COVID-19 travel restrictions, suspend the following rules/procedures in the IEEE 802 LMSC Operations Manual From 5 October 2020 until 20 November 2020:
In Subclause 9.2, first paragraph
A complete proposed PAR and, if applicable, the criteria for standards development (CSD) statement, as described in Clause 14, shall be submitted to the IEEE 802 LMSC via the IEEE 802 LMSC email reflector for review no less than 30 days prior to the day of the opening IEEE 802 LMSC meeting of an IEEE 802 LMSC plenary session. The submittal message should include Internet links to the required submittal documents. Presence of the submittal message in the reflector archive (with time stamp) is evidence of delivery.
Subclause 9.3 Plenary Review
and be replaced with:
PARs to be considered for approval by the IEEE 802 LMSC during the closing IEEE 802 LMSC meeting 19 November 2020 electronic meeting shall pass through the following process:
The proposed PAR shall be available at a publicly accessible URL and an email sent to the IEEE 802 LMSC reflector that contains the URL required for viewing the PAR and associated documentation no later than 6 October 2020, AoE.
Working Groups, other than the proposing Working Group, shall express concerns to the proposing Working Group as soon as possible and shall submit comments to the proposing Working Group and the IEEE 802 LMSC by e-mail not later than 10 November 2020, AoE
The proposing Working Group shall post a response to commenting Working Group and to the IEEE 802 LMSC together with a Final PAR on a public website and circulate the relevant URL on the IEEE 802 LMSC reflector not later than 17 November 2020, AoE
Moved: D’Ambrosia, seconded: George Zimmerman

## Slide 8: Reference #3 Email motion, 6/12/20 -
Due to the change of the July 2020 Plenary Session due to COVID-19 travel restrictions, suspend the following rules/procedures in the IEEE 802 LMSC Operations Manual From 11 June 2020 until 5 August 2020: In Subclause 10.2, first paragraph
A proposed ICAID and supporting documents shall be submitted to the Sponsor via the Sponsor email reflector for review no less than 30 days prior to the day of the opening Sponsor meeting of an IEEE 802 LMSC plenary session. The submittal message should include Internet links to the required submittal documents. Presence of the submittal message in the reflector archive (with time stamp) is evidence of delivery.
Subclause 10.3 Plenary Review and be replaced with: ICAIDs to be considered for approval by the IEEE 802 LMSC during the 4 August 2020 electronic meeting shall pass through the following process: The proposed ICAID shall be available at a publicly accessible URL and an email sent to the IEEE 802 LMSC reflector that contains the URL required for viewing the ICAID and associated documentation no later than 12 June 2020, AoE. Working Groups, other than the proposing Working Group, shall express concerns to the proposing Working Group as soon as possible and shall submit comments to the proposing Working Group and the IEEE 802 LMSC by e-mail not later than 12 July 2020, AoE The proposing Working Group shall post a response to commenting Working Group and to the IEEE 802 LMSC together with a Final on a public website and circulate the relevant URL on the IEEE 802 LMSC reflector not later than 31 July 2020, AoE
Moved: John D’Ambrosia
Second: James Gilb

## Slide 9: Proposed #3 -
Due to the change of the November 2020 Plenary Session due to COVID-19 travel restrictions, suspend the following rules/procedures in the IEEE 802 LMSC Operations Manual From 5 Oct 2020 until 20 November 2020: In Subclause 10.2, first paragraph
A proposed ICAID and supporting documents shall be submitted to the Sponsor via the Sponsor email reflector for review no less than 30 days prior to the day of the opening Sponsor meeting of an IEEE 802 LMSC plenary session. The submittal message should include Internet links to the required submittal documents. Presence of the submittal message in the reflector archive (with time stamp) is evidence of delivery.
Subclause 10.3 Plenary Review and be replaced with: ICAIDs to be considered for approval by the IEEE 802 LMSC during the closing IEEE 802 LMSC meeting 19 November 2020 electronic meeting shall pass through the following process: The proposed ICAID shall be available at a publicly accessible URL and an email sent to the IEEE 802 LMSC reflector that contains the URL required for viewing the ICAID and associated documentation no later than 6 October 2020, AoE. Working Groups, other than the proposing Working Group, shall express concerns to the proposing Working Group as soon as possible and shall submit comments to the proposing Working Group and the IEEE 802 LMSC by e-mail not later than 10 November 2020, AoE The proposing Working Group shall post a response to commenting Working Group and to the IEEE 802 LMSC together with a Final on a public website and circulate the relevant URL on the IEEE 802 LMSC reflector not later than 17 November 2020, AoE
Moved: D’Ambrosia, seconded: George Zimmerman