## Slide 1: IEEE 802 status report to ISO/IEC JTC 1/SC 6 for SC 6 meeting in June/July 2022 online (shortened version for SC6 plenary)
1 July 2022
Authors:
Name | Company | Phone | email
Andrew Myles (Chair) | Cisco | +61 418 656587 | amyles@cisco.com
Peter Yee (Vice Chair) | AKAYLA | +1 415 215 7733 | peter@akayla.com

## Slide 2: This report from IEEE 802 summarises issues of mutual interest to SC 6
Items included in this report (a summary of N17821)
  Summary of PSDO process status
  Summary of standards currently in the PSDO process
    802.1
    802.3
    803.11
    802.15
    802.22
  Views on status report

## Slide 3: IEEE 802 has sent 89 standards through the ISO/IEEE PSDO process, with 40 in-process
WG | Completed | In-process
802.1 | 41 | 11
802.3 | 27 | 6
802.11 | 12 | 9
802.15 | 3 | 13
802.16 | 0 | 0
802.19 | 0 | 0
802.21 | 3 | 0
802.22 | 3 | 1
All | 89 | 40

## Slide 4: IEEE 802.1 PSDO pipeline is progressing without difficulty, with 11 standards in progress
802 | Last draft liaised |  | 60-day pre-ballot |  | 5-month FDIS ballot |  | Comments resolved
.1Q-REV | D1.0 | Sep 21 | - | - | - | - | -
.1X-2020 | Std | Aug 20 | Passed | 14 Dec 20 | Passed | 17 Nov 21 | Mar 2022
.1CS | D3.0 | Aug 20 | Passed | 31 Jul 21 | Passed | 4 Jun 22 | n/a
.1Qcz | D1.2 | Aug 20 | - | - | - | - | -
.1ABcu | D2.0 | Jul 21 | Closes | 22 Jul 22 | - | - | -
.1CBdb | D2.0 | Sep 21 | Passed | 14 Jun 22 | Waiting | - | n/a
.1CBcv | D2.0 | Sep 21 | Passed | 14 Jun 22 | Waiting | - | n/a
.1ABdh | D2.0 | Sep 21 | Closes | 22 Jul 22 | - | - | -
.1AS/cor1 | D3.0 | Sep 21 | n/a | - | Closes | 23 Aug 22 | -
.1BA-REV | D2.0 | Sep 21 | Passed | 24 Jun 22 | Waiting | - | Waiting
.1ACct | D2.0 | Sep 21 | Passed | 10 Apr 22 | Waiting | - | Waiting

## Slide 5: IEEE 802.3 PSDO pipeline is progressing without difficulty, with 6 standards in progress
802 | Last draft liaised |  | 60-day pre-ballot |  | 5-month FDIS ballot |  | Comments resolved
.3cr | D3.1 | Oct 20 | Passed | 11 Jun 21 | Passed | 4 Jun 22 | n/a
.3cu | D3.0 | Oct 20 | Passed | 11 Jun 21 | Passed | 4 Jun 22 | n/a
.3ct | D3.1 | Jan 21 | Passed | 9 Oct 21 | Closes | 2 Sep 22 | Nov 21
.3cv | D3.0 | Jan 21 | Passed | 9 Oct 21 | Closes | 1 Sep 22 | Nov 21
.3cp | D3.0 | Feb 21 | Passed | 9 Oct 21 | Closes | 2 Sep 22 | Nov 21
.3-REV | - | - | Waiting | - | Waiting | - | n/a

## Slide 6: IEEE 802.11 PSDO pipeline is being held up by patent issues – to be resolved by ISO & IEEE SA secretariats
Std | Last draft liaised |  | 60-day pre-ballot |  | 5-month FDIS ballot |  | Comments resolved
11ax | D6.0 | Jan 20 | Passed | 10 Aug 21 | On hold | - | Nov 2021
11ay | D8.0 | Feb 21 | Failed | 9 Oct 21 | - | - | n/a
11md | D3.0 | Jan 20 | Passed | 11 Jun 21 | On hold | 13 Jun 22 | Waiting
11az | D4.0 | Apr 22 | - | - | - | - | -
11ba | D8.0 | Feb 21 | On hold | - | - | - | -
11bb | Waiting | - | - | - | - | - | -
11bc | Waiting | - | - | - | - | - | -
11bd | D4.0 | Jun 22 | - | - | - | - | -
11be | Waiting | - | - | - | - | - | -

## Slide 7: IEEE 802.1 PSDO pipeline is just starting
Std | Last draft liaised |  | 60-day pre-ballot |  | 5-month FDIS ballot |  | Comments resolved
.4-2020 | Waiting | - | - | - | - | - | -
.4w-2020 | Waiting | - | - | - | - | - | -
.4x-2019 | Waiting | - | - | - | - | - | -
.4z-2020 | Waiting | - | - | - | - | - | -
.4aa-2022 | Waiting | - | - | - | - | - | -
.3-2016 | Waiting | - | - | - | - | - | -
.3d-2017 | Waiting | - | - | - | - | - | -
.3e-2017 | Waiting | - | - | - | - | - | -
.3f-2017 | Waiting | - | - | - | - | - | -
.9-2020 | Waiting | - | - | - | - | - | -
.7 | Waiting | - | - | - | - | - | -
.13 | Waiting | - | - | - | - | - | -
.6 | Waiting | - | - | - | - | - | -

## Slide 8: IEEE 802.22 PSDO pipeline is finalising one final standard revision
802 | Last draft liaised |  | 60-day pre-ballot |  | 5-month FDIS ballot |  | Comments resolved
.22-REV | D8.0 | Nov 19 | Passed | 17 Oct 20 | Passed | 18 Mar 22 | Waiting

## Slide 9: Is reporting format suitable for SC6 and WG1?
  IEEE 802 has been providing a status report to SC6 for some years
  A few years ago, the format was changed to focus on the status of the PSDO process
  After a few more years experience, it was felt it was time to check whether the report format was suitable for SC6 and/or WG1
  The response from WG1 was positive with a couple of suggestions
    Add names of standards to report, not just alphabetical designations
    Add list of new IEEE 802 activities, summarising the reports sent after each IEEE 802 plenary session