IEEE P802-REVc Working Group Ballot #1 Result Summary

---
Ballot result summary
	TOTAL	%
Yes	37	84%
No 7 16%	7	16%
Voting Yes or No	44	100%
Abstain, lack of time	2	3 %
Abstain, lack of expertise	12	21%
Abstain, other	0	0%
Repondents	58
Voting members	56
Non-voting members	2
Number of commenters	15
Number of comments	195

---
Comments
- Uploaded to mental site at:
  - https://mentor.ieee.org/802-ec/dcn/23/ec-23-0057-04-00EC-802-revc-comments-wg-lb1.ods
- Current version is 04
- Comments marked with Suggest Accepted, Suggest Revised (with suggestion) and Suggest Rejected (with rejection reason)
  - Based solely on Technical Editors humble opinion (as a starting point).
- Comments marked Accepted, Revised or Rejected have been reviewed by the group
- Yellow background indicates the Technical Editor thinks it may require significant discussion.

---
Proposed Schedule Going Forward
- Conference calls between now and May
- Finish resolutions in May
- Roll in 802f in April-May time frame
- WG recirculation ballot in June 2023 (perhaps 20-30 days due to new content)
- Move to SA ballot in July (probably conditional)
- 1-2 WG recirculations in July-September
- SA ballot around September
- Resolve comments in November, perhaps January
- RevCom by March 2024

---
Comment status
Resolution status
Accepted	2
Revised	17
Rejected	1
Suggest Accepted	109
Suggest Revised	59
Suggest Rejected	10
# left to resolve	175
% left to resolve	90%

---
- We are in 3 locations the same week.
- Potential times are in the table
  - 1 hour mixed mode meeting
- Are all acceptable?
- Request room at all three sites for 5-10 people
Helsinki	Orlando	San Antonio
1 pm	7 am	6 am
2 pm	8 am	7 am
3 pm	9 am	8 am
4 pm	10 am	9 am
5 pm	11 am	10 am
6 pm	noon	11 am
7 pm	1 pm	noon
8 pm	2 pm	1 pm