## Slide 1: 12 AUG 2024 History Ad Hoc Agenda
Reiterate Scope/Duties/Membership/Voting
Status of planned activities
Set up meeting schedule
Solicit Volunteers – one from each WG/TAG
Begin execution

## Slide 2: 19JUL2024 Motion: Approve the formation of an 802 History Ad Hoc, with the scope, duties, membership and voting as shown in EC 24-182-01
Scope:
      Initiate electronic preservation of historical 802 documents
      Identify pertinent materials of historical interest, e.g., documents, audio recordings, video recordings, etc.
      Find a location(s) at which to store/display pertinent physical artifacts
      Capture recollections of long time 802 LMSC participants
      Develop a plan and budget for curation and presentation of materials
      Solicit support of IEEE History Center
      Review potential sources of funds, e.g., IEEE SA, IEEE Computer Society and IEEE New Initiatives
  Duties: Provide regular status reports to 802 LMSC
  Membership: Open to any interested participant
  Voting: straw polls only
  Moved: Chaplin
  Seconded: Zimmerman
  Approve by Unanimous Consent

## Slide 3: 802 History Ad Hoc Plan: 12 AUG 2024 Status Update
Prioritize preserving the first 15 years (1979-1994) of historical material
Next Steps
  Form 802 History Ad Hoc -- COMPLETE.
    Flesh out Ad Hoc logistics by 7 October 2024 EC telecon
  Geoff to investigate preservation of documents in his possession
    Obtained estimate to ship documents in his possession to NJ: $5-$7k.
    Action Item: GOT to obtain estimate to bulk digitize the documents.
    Action Item: Paul to contact InfoAge Science & History Museums https://www.infoage.org/
  Peter to investigate EA collaboration – IN PROCESS
  Paul to investigate Computer Society collaboration – IN PROCESS
    Action item: Paul to follow up with CS Staff on Charles Babbage Institute in Minnesota
    Edward to report on 12SEP2024 CS BoG decision on 2025 $50k initiative request
  Tuncer to support activity as needed -- ONGOING

## Slide 4: 802 History Ad Hoc Meeting Schedule
Establish regular meeting cadence
  Initial 1hour telecon 1pm ET Monday 12 August 2024
  Agreed on bi-monthly meetings, 1pm ET, 2nd Monday of the month August, October, December, February, April, June
    Next meeting 1pm ET 06 October 2024
  Typical Agenda
    Obtain and review status on ongoing activities
    Review ad hoc membership, recruit participants
    Any other business?

## Slide 5: 802 History Ad Hoc Volunteers
Current Membership Roster
  Interim Chair PaulN, looking for a longer term (at least until MAR2026) Chair
  Current Membership:
      802.0 Paul Nikolich, James Gilb,
      802.01 none
      802.03 Geoff Thompson, Peter Jones
      802.11 Srinivas Kandala, Al Petrick
      802.15 Joerg Robert
      802.18, 802.22 Edward Au
      802.19 Tuncer Baykas
      802.24 none
  Looking for at least one person from every WG/TAG in 802 LMSC. This includes disbanded and hibernating Groups.
      Candidates: 802.16 Roger Marks, 802.21 Subir
      Candidates: 802.5 Bob Love, Bob Grow, 802.3 Gary Robinson
      Candidates: 802.0 Maris Graube
      PaulN to circulate a list of all 802 Groups (since inception) and their chairs to the ad hoc

## Slide 6: 12 AUG 2024 Action Items
    Paul to announce next meeting scheduled for 1pm ET 06 October 2024
    GOT to obtain estimate to bulk digitize the documents by 06OCT2024
    Paul to contact InfoAge Science & History Museums https://www.infoage.org/ by 06OCT2024
    Paul (with support from Edward) to follow up with CS Staff on Charles Babbage Institute in Minnesota, provide update 06OCT2024
    Edward to report on 12SEP2024 CS BoG decision on 2025 $50k initiative request
    PaulN to circulate a list of all 802 Groups (since inception) and their chairs to the ad hoc
    Joerg to identify and locate all documents related to the founding and early operations of the 802.15 WG