## Slide 1: 21 October 2024 notes
PaulN reviewed scope, membership, action items
  Michael Fischer joined the group in September, he will focus on early 802.11 WG historical details.
    He has experience archiving and curating computer history with SAMSAT (San Antonio Computer History Museum).
    Drafting a ‘pre-history’ of LAN technology activities (i.e., pre-1980)
Al Petrick will draft a timeline for early (pre) and post establishment of 802.11 activities.
PaulN will explore collecting aural histories. MF observes the quality of the interviewer is critical. Knowledgeable interviewers are important!

## Slide 2: 12 AUG 2024 Action Items
    Paul to announce next meeting scheduled for 1pm ET 21 October 2024 -- COMPLETE
    GOT to obtain estimate to bulk digitize the documents by 06OCT2024 -- OPEN
    Paul to contact InfoAge Science & History Museums https://www.infoage.org/ by 21OCT2024 -- CLOSED
    Paul (with support from Edward) to follow up with CS Staff on Charles Babbage Institute in Minnesota, provide update 21OCT2024 –Definite interest, PaulN to follow up on specific capabilities. -- OPEN
    Edward to report on 12SEP2024 CS BoG decision on 2025 $50k initiative request. -- OPEN
    PaulN to circulate a list of all 802 Groups (since inception) and their chairs to the ad hoc --COMPLETE
    Joerg to identify and locate all documents related to the founding and early operations of the 802.15 WG – Located all historical documents, remaining task to send them to the designated repository. -- IN PROCESS

## Slide 3: 21 October 2024 History Ad Hoc Agenda
Reiterate Scope/Duties/Membership/Voting
Status of planned activities
Set up meeting schedule
Solicit Volunteers – one from each WG/TAG
Begin execution

## Slide 4: 19JUL2024 Motion: Approve the formation of an 802 History Ad Hoc, with the scope, duties, membership and voting as shown in EC 24-182-01
Scope:
      Initiate electronic preservation of historical 802 documents
      Identify pertinent materials of historical interest, e.g., documents, audio recordings, video recordings, etc.
      Find a location(s) at which to store/display pertinent physical artifacts
      Capture recollections of long time 802 LMSC participants
      Develop a plan and budget for curation and presentation of materials
      Solicit support of IEEE History Center
      Review potential sources of funds, e.g., IEEE SA, IEEE Computer Society and IEEE New Initiatives
  Duties: Provide regular status reports to 802 LMSC
  Membership: Open to any interested participant
  Voting: straw polls only
  Moved: Chaplin
  Seconded: Zimmerman
  Approve by Unanimous Consent

## Slide 5: 802 History Ad Hoc Plan: 21 OCT 2024 Status Update
Prioritize preserving the first 15 years (1979-1994) of historical material
Next Steps
  Form 802 History Ad Hoc -- COMPLETE.
    Flesh out Ad Hoc logistics by 7 October 2024 EC telecon
  Geoff to investigate preservation of documents in his possession -- OPEN
    Obtained estimate to ship documents in his possession to NJ: $5-$7k.
    Action Item: GOT to obtain estimate to bulk digitize the documents.
    Action Item: Paul to contact InfoAge Science & History Museums -- CLOSED
  Peter to investigate EA collaboration – IN PROCESS
  Paul to investigate Computer Society collaboration – IN PROCESS
    Action item: Paul to follow up with CS Staff on Charles Babbage Institute in Minnesota
    Edward to report on 12SEP2024 CS BoG decision on 2025 $50k initiative request
  Tuncer to support activity as needed -- ONGOING

## Slide 6: 802 History Ad Hoc Meeting Schedule
Establish regular meeting cadence
  Initial 1hour telecon 1pm ET Monday 12 August 2024
  Agreed on bi-monthly meetings, 1pm ET, 2nd Monday of the month August, October, December, February, April, June
    Next meeting: noon Tuesday 12 November 2024 during Vancouver BC 802 plenary
  Typical Agenda
    Obtain and review status on ongoing activities
    Review ad hoc membership, recruit participants
    Any other business?

## Slide 7: 802 History Ad Hoc Volunteers
Current Membership Roster
  Interim Chair PaulN, looking for a longer term (at least until MAR2026) Chair
  Current Membership:
      802.0 Paul Nikolich, James Gilb,
      802.01 none
      802.03 Geoff Thompson, Peter Jones
      802.11 Srinivas Kandala, Al Petrick, Michael Fischer
      802.15 Joerg Robert
      802.16 none
      802.18, 802.22 Edward Au
      802.19 Tuncer Baykas
      802.24 none
  Looking for at least one person from every WG/TAG in 802 LMSC. This includes disbanded and hibernating Groups.
      Candidates: 802.16 Roger Marks, 802.21 Subir
      Candidates: 802.5 Bob Love, Bob Grow, 802.3 Gary Robinson
      Candidates: 802.0 Maris Graube
      PaulN to circulate a list of all 802 Groups (since inception) and their chairs to the ad hoc