## Slide 1: 11 March 2025 History Ad Hoc Agenda
Introductions
Scope
Status of planned activities
Plan next steps
Schedule next meetings

## Slide 2: Introductions/Role Call: Attendees/Participants
802.0 Paul Nikolich, James Gilb, Gary Robinson, Maris Graube
802.3 Geoff Thompson, Peter Jones, Yuan Qiu Luo
802.1 Norm Fin, Mick Seaman
802.5 Bob Love
802.11 Srinvas Kandala, Al Petrick, Michael Fischer, Jon Rosdahl
802.15 Jorge Robert
802.18&22 Edward Au
802.19&Public Visibility Tuncer Baykas
IEEE History Center Nathan Brewer
IEEE Computer Society Anne Marie Kelly, Thomas Haigh
IEEE Standards Association Staff Yvette Ho Sang
IEEE 802 Meeting Planner Dawn Slykhouse
Other …

## Slide 3: 802 History Ad Hoc Potential Participants
Current Membership Roster
  Interim Chair PaulN, looking for a long term Chair (at least until MAR2026)
  Current Membership:
      802.0 Paul Nikolich (past 802 Chair), James Gilb (802 Chair), Maris Graube (founding 802 chair), Gary Robinson
      802.01 Norm Finn, Mick Seaman
      802.03 Geoff Thompson, Peter Jones
      802.05 Bob Love
      802.11 Srinivas Kandala, Al Petrick, Michael Fischer
      802.15 Joerg Robert
      802.16 none
      802.17 none
      802.18, 802.22 Edward Au
      802.19 Tuncer Baykas
      802.24 none
  Looking for at least one person from every WG/TAG in 802 LMSC. This includes disbanded and hibernating Groups.
      Candidates: 802.16 Roger Marks and Rakesh Taori, 802.21 Subir Das
      Candidates: 802.1 Bill Lidinsky
  Others
    Computer Society; Anne Marie Kelly (staff), Thomas Haigh (2025 History Committee Chair)
    Nathan Brewer, IEEE History Center, Archival & Digital Content Manager
    IEEE Standards Association Staff, Yvette Ho Sang

## Slide 4
Scope:
      Identify and locate pertinent materials of historical interest, e.g., documents, audio recordings, video recordings, etc.
      Initiate electronic preservation of historical 802 documents
      Find a location(s) at which to store/display pertinent physical artifacts
      Electronic capture of recollections of long time 802 LMSC participants
      Develop a plan and budget for curation and presentation of materials
      Solicit support of IEEE History Center
      Review potential sources of funds, e.g., IEEE SA, IEEE Computer Society and IEEE New Initiatives
  Duties: Provide regular status reports to 802 LMSC
  Membership: Open to any interested participant
  Voting: straw polls only

## Slide 5: 802 History Ad Hoc Meeting
Meeting cadence and agenda
  Approximately every 802 plenary session, noon-2pm Local Time Tuesday 2025: 11MAR (Atlanta), 29JUL (Madrid), 11NOV (Bangkok)
    Next meeting: noon Tuesday 29 JUL 2025 Madrid Spain 802 plenary
  Agenda
    Obtain and review status on ongoing activities
      Action Item Review
      Charles Babbage Institute update
    Plan next steps, identify new action items
    Recruit participants
    Any other business?

## Slide 6: IEEE 802 LMSC History Ad Hoc Pending Action Items
Attendees: James Gilb, Geoff Thompson, Peter Jones, Paul Nikolich, Tuncer Baykas, Dawn Slykhouse, Gary Robinson, Bob Love, Yvette Ho Sang, Nathan Brewer, Mario Costa, Yuan Qiu Luo
Action Items:
Peter Jones to determine if the Computer History Museum has interest in supporting this effort JULY2025
Dawn Slykhouse to contact Alpha Graphics and Don Loughry’s family for potential contributions unable to locate Alpha Graphics sources, DL family a challenge, unable to connect with their family, will reach out to Geoff Thompson. JULY2025
Yvette Ho Sang to obtain clarity on IEEE copyright permissions for old (>15yo draft and published standards) JULY2025
James Gilb and Michael Fischer to search for/identify relevant interviews (journals, magazines, aural, etc.) Due MAY2025
Geoff Thompson to draft criteria to qualify potential repositories JULY2025
Gary Robinson to inventory items of interest in his possession (original DIX doc, mementos, videos) JULY2025
Bob Love to reach out early 802.5 WG participants, Unable to reach John Messenger. inventory items Bob may possess – does not have anything left, everything on floppy disk
Paul Nikolich to contact Vic Hayes to obtain permission to use recently recorded video MAY2025

## Slide 7: 802 History Ad Hoc Plan: 11 March 2025 Status Update
Prioritize preserving the first 15 years (1979-1994) of historical material
Next Steps
  Flesh out Ad Hoc logistics – IN PROCESS
    Create a list of material to be archived – IN PROCESS
      Geoff to investigate preservation of documents in his possession -- OPEN
      Obtained estimate to ship documents in his possession to NJ: $5-$7k.
      Action Item: GOT to obtain estimate to bulk digitize the documents.
  Identify Potential Archive Repositories
    Action item: Follow up on Charles Babbage Institute in Minnesota – IN PROCESS
    Action Item: Paul to contact InfoAge Science & History Museums -- CLOSED
    Decide on a repository by JULY2025
  Peter to investigate Ethernet Alliance collaboration – IN PROCESS
  Paul to investigate Computer Society collaboration – IN PROCESS
    Action item: Paul to follow up with CS Staff on Charles Babbage Institute in Minnesota – IN PROCESS
  Initiate Accumulation of Historical Material
  Tuncer/802 Public Visibility Ad Hoc to support activity as needed -- ONGOING

## Slide 8: Charles Babbage Institute Update
CBI can store the paper files, unlike the IEEE HIstory Center. However, CBI no longer stores duplicate materials out of concern for the limit of their storage facilities.
CBI"s request is that we remove duplicate files before sending, if possible. Otherwise duplicates would be tossed and not archived. CBI also wants materials stored in binders to be removed from the binders before sending. If photos or videos are included in the donation, CBI requires that all individuals in the photo/video be identified and a date of the photo be provided.
CBI has an electronic records department and a digitization team that can digitize files. The process involves taking photos of pages, rather than copying them, which Amanda said works well for their archiving purposes.
CBI will accept hard copy materials with digital copies made by other vendors. But we discussed the pros and cons of that approach, and it seems easier to have CBI manage everything and convert materials to digital based on their specifications.

## Slide 9: Charles Babbage Institute Update
File organization - AMK asked if CBI needed a summary of the shipped materials. CBI said at a minimum, they would like a box level description, and if possible, folder titles. CBI promised to send AMK a template to enter information about the contents. It isn't mandatory to use the spreadsheet but it helps speed CBI processing and organization. AMK also told CBI that the original 802 files would come from two separate sources.
Cost - CBI's digitalization fees are charged not by page but by inch. I gave her an estimate of 10K for 802 pages. CBI asked for an estimate in linear feet for the 802 papers to determine a cost for digitization. AMK need to provide the Computer Society file linear feet estimate as well.
Timeline for digitization - there was a backlog due to a flood in the digitization department (the archives are underground and were not damaged) and CBI couldn't give me a timeline right now.

## Slide 10: Charles Babbage Institute Update
CBI will provide a current Deed of Gift agreement and I will request IEEE legal review. Question: For the 802 collection, are these mostly personal papers and committee documents? Asked because IEEE SA documents might require further approvals/releases? You and Geoff may need to sign paperwork for the donations - will let you know.
CBI doesn't charge to accept collections but donations help CBI to hire temp staff to process collections. (The digitalization fees are a direct charge). The Computer Society BoG had previously agreed to make a donation to CBI and that could be extended to include the 802 papers.
Here are examples shared of a collection donated to CBI and put online: https://archives.lib.umn.edu/repositories/3/resources/242/digitized, https://umedia.lib.umn.edu/search?facets%5Bcollection_name_s%5D%5B%5D=Alex+McKenzie+Collection+of+Computer+Networking+Development+Records&facets%5Bcontributing_organization_name_s%5D%5B%5D=University+of+Minnesota+Libraries%2C+Charles+Babbage+Institute.&q=vint
Anne Marie Kelley (AMK) from the Computer Society will coordinate another call with CBI and the 802 volunteers as needed.

## Slide 11: Background Information

## Slide 12: Noon-2pm EST 11 March 2025 Notes
Attendees: Paul Nikolich,
James Gilb, Geoff Thompson, Peter Jones, Tuncer Baykas, Dawn Slykhouse, Gary Robinson, Bob Love, Yvette Ho Sang, Nathan Brewer, Mario Costa, Yuan Qiu Luo, Al Petrick?
Action Items:
tbd
Next Meeting scheduled for noon CET 29 July 2025 via webex

## Slide 13: Noon-1pm PST 12 November 2024 Notes
Attendees: James Gilb, Geoff Thompson, Peter Jones, Paul Nikolich, Tuncer Baykas, Dawn Slykhouse, Gary Robinson, Bob Love, Yvette Ho Sang, Nathan Brewer, Mario Costa, Yuan Qiu Luo, Al Petrick?
Action Items:
Peter Jones to determine if the Computer History Museum has interest in supporting this effort
Dawn Slykhouse to contact Alpha Graphics and Don Loughry’s family for potential contributions
Yvette Ho Sang to obtain clarity on IEEE copyright permissions for old (>15yo documents)
James Gilb to search for/identify relevant interviews (journals, magazines, aural, etc.)
Geoff Thompson to draft criteria to qualify potential repositories
Gary Robinson to inventory items of interest in his possession (original DIX doc, mementos, videos)
Bob Love to reach out early 802.5 WG participants, inventory items he may possess.
Paul Nikolich to contact Vic Hayes to obtain permission for recently recorded video
Next Meeting scheduled for 13:00 EST Monday 27 January 2025 via webex

## Slide 14: 21 October 2024 notes
PaulN reviewed scope, membership, action items
  Michael Fischer joined the group in September, he will focus on early 802.11 WG historical details.
    He has experience archiving and curating computer history with SAMSAT (San Antonio Computer History Museum).
    Drafting a ‘pre-history’ of LAN technology activities (i.e., pre-1980)
Al Petrick will draft a timeline for early (pre) and post establishment of 802.11 activities.
PaulN will explore collecting aural histories. MF observes the quality of the interviewer is critical. Knowledgeable interviewers are important!

## Slide 15: 12 AUG 2024 Action Items
    Paul to announce next meeting scheduled for 1pm ET 21 October 2024 -- COMPLETE
    GOT to obtain estimate to bulk digitize the documents by 06OCT2024 -- OPEN
    Paul to contact InfoAge Science & History Museums https://www.infoage.org/ by 21OCT2024 -- CLOSED
    Paul (with support from Edward) to follow up with CS Staff on Charles Babbage Institute in Minnesota, provide update 21OCT2024 –Definite interest, PaulN to follow up on specific capabilities. -- OPEN
    Edward to report on 12SEP2024 CS BoG decision on 2025 $50k initiative request. -- OPEN
    PaulN to circulate a list of all 802 Groups (since inception) and their chairs to the ad hoc --COMPLETE
    Joerg to identify and locate all documents related to the founding and early operations of the 802.15 WG – Located all historical documents, remaining task to send them to the designated repository. -- IN PROCESS

## Slide 16: 19JUL2024 Motion: Approve the formation of an 802 History Ad Hoc, with the scope, duties, membership and voting as shown in EC 24-182-01
Scope:
      Initiate electronic preservation of historical 802 documents
      Identify pertinent materials of historical interest, e.g., documents, audio recordings, video recordings, etc.
      Find a location(s) at which to store/display pertinent physical artifacts
      Capture recollections of long time 802 LMSC participants
      Develop a plan and budget for curation and presentation of materials
      Solicit support of IEEE History Center
      Review potential sources of funds, e.g., IEEE SA, IEEE Computer Society and IEEE New Initiatives
  Duties: Provide regular status reports to 802 LMSC
  Membership: Open to any interested participant
  Voting: straw polls only
  Moved: Chaplin
  Seconded: Zimmerman
  Approve by Unanimous Consent