## Sheet1
Comment number | Commenter | Category | Page | Section | Line # | Comment | Proposed Change | URL of document relevant to Comment | Editor Proposed Resolution | Editor Proposed Resolution Detail | Tentative Resolution | Discussion notes | Agreed Resolution | Resolution details | Implementation Status
1 | Marks | Editorial | 1 | Introduction |  | Strikeout: in |  |  | Accept |  |  |  | Accept |  | done
2 | Marks | Editorial | 1 | Introduction |  | market share | the market share |  | Accept |  |  |  | Accept |  | done
3 | Marks | Editorial | 1 | Introduction |  | Strikeout: questionnaire |  |  | Accept |  |  |  | Accept |  | done
4 | Marks | Editorial | 1 | Introduction |  | for Japanese 1,033 | of 1033 Japanese |  | Accept |  |  |  | Accept |  | done
5 | Marks | Editorial | 1 | Introduction |  | by | administered by |  | Accept |  |  |  | Accept |  | done
6 | Marks | Editorial | 1 | Introduction |  | in which | , including |  | Accept |  |  |  | Accept |  | done
7 | Marks | Editorial | 1 | Introduction |  | Strikeout: were investigated |  |  | Accept |  |  |  | Accept |  | done
8 | Marks | Editorial | 2 | Introduction |  | (NEND-ICA | Nendica |  | Accept |  |  |  | Accept |  | done
9 | Marks | Editorial | 2 | Introduction |  | Strikeout: its |  |  | Accept |  |  |  | Accept |  | done
10 | Marks | Editorial | 2 | Introduction |  | End-to-End | end-to-end |  |  | Discuss |  |  | Accept |  | done
11 | Marks | Editorial | 2 | Introduction |  | which | that |  | Accept |  |  |  | Accept |  | done
12 | Marks | Editorial | 2 | Scope |  | is capturing | includes |  | Accept |  |  |  | Accept |  | done
13 | Marks | Editorial | 2 | Scope |  | Strikeout: its |  |  | Accept |  |  |  | Accept |  | done
14 | Marks | Editorial | 2 | Scope |  | network | networks |  | Accept |  |  |  | Accept |  | done
15 | Marks | Editorial | 2 | Scope |  | understand | document |  | Accept |  |  |  | Accept |  | done
16 | Marks | Editorial | 2 | Scope |  | where | in which |  | Accept |  |  |  | Accept |  | done
17 | Marks | Editorial | 2 | Scope |  | Flexible Factory | flexible factory |  |  | Discuss |  | Proposal to make propoer definition for Flexible factory in the introduction. Then it can be used ion the purpose section. Nader and Maruhashi san will propose a definition accordingly See 1-19-0041-00 | Revise | Insert the text in 1-19-0041-01 at line 1 of page 2. | done
18 | Marks | Editorial | 2 | Scope |  | Strikeout: the |  |  | Accept |  |  |  | Accept |  | done
19 | Marks | Editorial | 2 | Scope |  | time critical |  |  |  | not sure what is the proposed change |  | replace with "time-crtitical" | Revise | replace with "time-crtitical" | done
20 | Marks | Editorial | 2 | Scope |  | connectivity which | it was not clear "+H21which" refer to what? Proposal replace "report includes technical analyses of the desired 22 features and functions in wired and wireless IEEE 802 technologies for managing requirements in 23 E2E network connectivity which can be used in an IEEE 802 standard solution based on time 24 critical requirements for integrated wired and wireless connectivity within the factory 25 environment." with "report includes technical analyses of the desired 22 features and functions in wired and wireless IEEE 802 technologies for managing requirements in 23 E2E network connectivity. The results of the analysis are intended to lead to recommendations for enhancements of IEEE 802 standards." The following then needs to be captured as part of the definition for "Flexible Factory": "based on time critical requirements for integrated wired and wireless connectivity within the factory environment." To be proposed by Nader and Maruhashi san with CID 17. done as par of 1-19-0041-00 |  |  | not sure what is the proposed change |  | it was not clear "which" refer to what? Proposal replace "report includes technical analyses of the desired 22 features and functions in wired and wireless IEEE 802 technologies for managing requirements in 23 E2E network connectivity which can be used in an IEEE 802 standard solution based on time 24 critical requirements for integrated wired and wireless connectivity within the factory 25 environment." with "report includes technical analyses of the desired 22 features and functions in wired and wireless IEEE 802 technologies for managing requirements in 23 E2E network connectivity. The results of the analysis are intended to lead to recommendations for enhancements of IEEE 802 standards." The following then needs to be captured as part of the definition for "Flexible Factory": "based on time critical requirements for integrated wired and wireless connectivity within the factory environment." To be proposed by Nader and Maruhashi san with CID 17. done as par of 1-19-0041-00 | Revise | replace the whole sectio of the Purpose with the following "The purpose of this report is to document issues and challenges in managing reliable and time-sensitive connectivity in the Flexible Factory, in which various equipment is attached to the wired network via wireless connections. The report includes technical analyses of the identified features and functions in wired and wireless IEEE 802 technologies for managing requirements in E2E network connectivity. The results of the analysis lead to recommendations for enhancements of IEEE 802 standards supporting the integration of wired and wireless factory networks." | done
21 | Marks | Editorial | 2 | Factory communication network environment |  | Operation | network communication |  | Revise | communication network |  |  | Revise | replace with Communication Network | done
22 | Marks | Editorial | 2 | Factory communication network environment |  | process | processes |  | Accept |  |  |  | Accept |  | done
23 | Marks | Editorial | 2 | Factory communication network environment |  | becomes important. | has become increasingly important. |  | Accept |  |  |  | Accept |  | done
24 | Marks | Editorial | 2 | Factory communication network environment |  | given | in spite of |  | Accept |  |  |  | Accept |  | done
25 | Marks | Editorial | 2 | Factory communication network environment |  | Commutation | Communication |  | Accept |  |  |  | Accept |  | done
26 | Marks | Editorial | 2 | Factory communication network environment |  | in factory | in a factory |  | Accept |  |  |  | Accept |  | done
27 | Marks | Editorial | 2 | Factory communication network environment |  | Strikeout: The |  |  | Accept |  |  |  | Accept |  | done
28 | Marks | Editorial | 2 | Factory communication network environment |  | Strikeout: are extensively applied for industrial process control and operation. Such systems |  |  | Accept |  |  |  | Accept |  | done
29 | Marks | Editorial | 2 | Factory communication network environment |  | Strikeout: by being |  |  | Accept |  |  |  | Accept |  | done
30 | Marks | Editorial | 2 | Factory communication network environment |  | can range | , ranging in scale |  | Accept |  |  |  | Accept |  | done
31 | Marks | Editorial | 2 | Factory communication network environment |  | , by being the universal means of | providing |  | Accept |  |  |  | Accept |  | done
32 | Marks | Editorial | 2 | Factory communication network environment |  | Strikeout: enormous |  |  | Accept |  |  |  | Accept |  | done
33 | Marks | Editorial | 2 | Factory communication network environment |  | by e.g. | by, for example, |  | Accept |  |  |  | Accept |  | done
34 | Marks | Editorial | 3 | Factory communication network environment |  | Strikeout: deployed in the field |  |  | Accept |  |  |  | Accept |  | done
35 | Marks | Editorial | 3 | Factory communication network environment |  | as ‘App x’ | in Figure 2 as ‘App x’ |  | Accept |  |  |  | Accept |  | done
36 | Marks | Editorial | 3 | Factory communication network environment |  | Strikeout: several |  |  | Accept |  |  |  | Accept |  | done
37 | Marks | Editorial | 3 | Factory communication network environment |  | illustrate | indicate |  | Accept |  |  |  | Accept |  | done
38 | Marks | Editorial | 3 | Factory communication network environment |  | Strikeout: , which are supported in the factory network |  |  | Accept |  |  |  | Accept |  | done
39 | Marks | Editorial | 3 | Factory communication network environment |  | monitoring of movements and machine monitors | and machine movement monitoring |  | Accept |  |  |  | Accept |  | done
40 | Marks | Editorial | 3 | Factory communication network environment |  | concerns the | provides |  | Accept |  |  |  | Accept |  | done
41 | Marks | Editorial | 3 | Factory communication network environment |  | essential differences between | distinctive features of |  | Accept |  |  |  | Accept |  | done
42 | Marks | Editorial | 3 | Factory communication network environment |  | Strikeout: and commercial |  |  | Accept |  |  |  | Accept |  | done
43 | Marks | Editorial | 3 | Factory communication network environment |  | has resulted in an emphasis on a different set of | results in a strong emphasis on differentiated |  | Accept |  |  |  | Accept |  | done
44 | Marks | Editorial | 3 | Factory communication network environment |  | Strikeout: and |  |  |  | Discuss: if deleting "and", should delete "other" as well. But It is not just the perfromance advantages. There are other advantages ethernet has emerged as the dominant standard! |  | replace "Because of performance and other advantages," with "Due to performance and market advantages" | Revise | replace "Because of performance and other advantages," with "Due to performance and market advantages" | done
45 | Marks | Editorial | 3 | Factory communication network environment |  | Because of | Due to |  |  | resolve this together with CID#44 above. |  |  | Accept | see CID44 | done as part of CID44
46 | Marks | Editorial | 3 | Factory communication network environment |  | physical layer | physical and medium-access control layers of factory networks |  | Accept |  |  |  | Accept |  | done
47 | Marks | Editorial | 3 | Factory communication network environment |  | fieldbus | Fieldbus |  | Accept |  |  |  | Accept |  | done
48 | Marks | Editorial | 3 | Factory communication network environment |  | multiple | Ethernet multiplexes multiple |  | Accept | style change, and no change to meaning. Hence it is fine |  |  | Accept |  | done
49 | Marks | Editorial | 3 | Factory communication network environment |  | Strikeout: can run on the same Ethernet physical layer |  |  | Accept | together with CID#48 |  |  | Accept |  | done
50 | Marks | Editorial | 3 | Factory communication network environment | 13 | physical layer. | replace with "physical and medium-access control layers of factory networks" |  |  | at 2nd read it is now clear propose to accept |  |  | Accept |  | superceded by CID49
51 | Marks | Editorial | 3 | Factory communication network environment |  | It is fairly easy to interconnect several devices | thus supporting the high-speed interconnection of |  |  | Discuss: not clear and could be changing the intended meaning |  | "Unlike serial protocols such as fieldbus [3], multiple higher layer protocols 13 can run on the same Ethernet physical layer. It is fairly easy to interconnect several devices such 14 as PLCs, HMI (Human Machine Interface), etc," replace with Ethernet, unlike serial protocols such as fieldbus [3], supports multiple higher layer protocols supporting the interconnection of devices with various bandwidth requirements, including PLCs, HMI (Human Machine Interface), and devices requiring high speed communications. | Revise | "Unlike serial protocols such as fieldbus [3], multiple higher layer protocols 13 can run on the same Ethernet physical layer. It is fairly easy to interconnect several devices such 14 as PLCs, HMI (Human Machine Interface), etc," replace with Ethernet, unlike serial protocols such as fieldbus [3], supports multiple higher layer protocols supporting the interconnection of devices with various bandwidth requirements, including PLCs, HMI (Human Machine Interface), and devices requiring high speed communications. | done
52 | Marks | Editorial | 3 | Factory communication network environment |  | PLCs |  |  |  | same as CID#51 |  |  | Revise | see CID 51 | done
53 | Marks | Editorial | 3 | Factory communication network environment |  | etc, |  |  |  | same as CID#51 |  |  | Revise | see CID 51 | done
54 | Marks | Editorial | 3 | Factory communication network environment |  | Strikeout: , remaining in high speed communication |  |  |  | same as CID#51 |  |  | Revise | see CID 51 | done
55 | Marks | Editorial | 3 | Factory communication network environment |  | TSN | newer IEEE 802 standards, |  | Revise | newer IEEE 802 TSN standards, see also CID67. |  | main point this requires new paragraph introducing TSN. IEEE 802 TSN standards and standards ammendment [1Q]. For more detail son TSN project to refer to the webpage. Then we need to refer to more details that appearing further down in the this report. TSN needs to be expended. Also need to add refrence to TSN webpage. Nader to propose fix for tehnext call. | Revise | delete "Adding on the deterministic features introduced by TSN, Ethernet are now taking over more shares at the high-end industrial communication markets." add the following paragraph "In high-end industrial communication markets, the use of Ethernet has become increasing favourable due to the introduction of the determinism based on the IEEE 802 Time-Sensitive Networking (TSN) standards. This set of standards for bridges and bridged networks, developed and supported by the IEEE 802.1 TSN Task Group, supports deterministic services, such as guaranteed packet transport with bounded latency, low packet delay variation, and low packet loss. For further information about the TSN Task Group and list of approved standards and projects in development, see the TSN Task Group page [xx]." Add the following to the citation list "[xx] IEEE 802.1 Time-Sensitive Networking (TSN) Task Group web page, https://1.ieee802.org/tsn/" | replaced "Adding on the deterministic features introduced by TSN, Ethernet are now taking over more shares at the high-end industrial communication markets" with ""In high-end industrial communication markets, the use of Ethernet has become increasing favourable due to the introduction of the determinism based on the IEEE 802 Time-Sensitive Networking (TSN) standards. This set of standards for bridges and bridged networks, developed and supported by the IEEE 802.1 TSN Task Group, supports deterministic services, such as guaranteed packet transport with bounded latency, low packet delay variation, and low packet loss. For further information about the TSN Task Group and list of approved standards and projects in development, see the TSN Task Group page [xx]." added new reference to TSN TG.
56 | Marks | Editorial | 3 | Factory communication network environment |  | are | is |  | Accept |  |  |  | Accept |  | superceded by CID55
57 | Marks | Editorial | 3 | Factory communication network environment |  | more shares at | an increasing share of |  | Accept |  |  |  | Accept |  | superceded by CID55
58 | Marks | Editorial | 3 | Factory communication network environment |  | Strikeout: the |  |  | Accept |  |  |  | Accept |  | superceded by CID55
59 | Marks | Editorial | 3 | Factory communication network environment |  | Strikeout: However, much of the cost of installation of wired networks is for the wire itself. |  |  | Accept | redundant with the subsequent sentence. |  |  | Accept |  | done
60 | Marks | Editorial | 3 | Factory communication network environment |  | expecting | expected |  | Accept |  |  |  | Accept |  | done
61 | Marks | Editorial | 3 | Factory communication network environment |  | eliminate | reduce |  | Accept |  |  |  | Accept |  | done
62 | Marks | Editorial | 3 | Factory communication network environment |  | Strikeout: , |  |  | Accept |  |  |  | Accept |  | done
63 | Marks | Editorial | 3 | Factory communication network environment |  | It | Wireless |  | Accept |  |  |  | Accept |  | done
64 | Marks | Editorial | 3 | Factory communication network environment |  | The ability to transmit and receive | Transmitting and receiving |  | Accept |  |  |  | Accept |  | done
65 | Marks | Editorial | 3 | Factory communication network environment |  | always going to work with the same degree of certainty as | as reliable as with |  | Accept |  |  |  | Accept |  | done
66 | Marks | Editorial | 3 | Factory communication network environment |  | https://www.ffp-a.org/news/index.html | Change this to Citation |  | Accept |  |  |  | Accept |  | done
67 | Weber | Technical | 3 | Factory communication network environment | 14 | TSN is IEEE 802.1 Bridging extensions | chang to "...TSN, Ethernet with IEEE 802.1 bridging are now …" |  | Revise | I think this is in line 16. See CID 55. to be resolved as part of resolution for CID55. |  |  | Revise | see resolution in CID55 | implemented as part of CID55
68 | Marks | Editorial | 4 | Factory communication network environment |  | Strikeout: will |  |  | Accept |  |  |  | Accept |  | done
69 | Marks | Editorial | 4 | Factory communication network environment |  | operate | operates |  | Accept |  |  |  | Accept |  | done
70 | Marks | Editorial | 4 | Factory communication network environment |  | E2E | end to end |  |  | Discuss Why it is not ok to use the abbreviation E2E here? |  | explanined because this end to end is not an adjective | Accept |  | done
71 | Marks | Editorial | 4 | Factory communication network environment |  | the | some sort of |  | Accept |  |  |  | Accept |  | done
72 | Marks | Editorial | 4 | Factory communication network environment |  | Strikeout: is indispensable |  |  | Accept |  |  |  | Accept |  | done
73 | Marks | Editorial | 4 | Factory communication network environment |  | is required. The | may be considered to aid the |  | Accept |  |  |  | Accept |  | done
74 | Marks | Editorial | 4 | Factory communication network environment |  | priority-classes | delivery requirements |  | Accept |  |  |  | Accept |  | done
75 | Marks | Editorial | 4 | Factory communication network environment |  | These | For example, some |  | Accept |  |  |  | Accept |  | done
76 | Marks | Editorial | 4 | Factory communication network environment |  | size. | size, whereas other data types are.... |  |  | Discuss: whereas other data types are continuous stream Do we need to list all data types? |  | It is not correct to lable sensors as the main consideration. Suggestion to delete "main". Additional issue with this paragraph is the need to add other data types at least as examples. The reason for focusing on sensor is because the traffic they generate has high peak to average ratio. this paragraph is out of place. one of way forward could be after stating the issue wih sensors, we need to add something saying while sensors results in high peak to average ratio whereas other data types generated from other devices by how or what. | Revise | See agreed resolution in document <1-19-0044-01-ICne-proposed-resolution-to-cid192-conclusion> | Actually the resolution for this comment is in <1-19-0046-02-ICne-ffiot-cid76-update> implemented with slight modification to reference [P6082, D1] and added the reference to project site.
77 | Marks | Editorial | 4 | Factory communication network environment |  | Advanced | Some advanced |  | Accept |  |  |  | Accept |  | done
78 | Marks | Editorial | 4 | Factory communication network environment |  | Strikeout: typically |  |  | Accept |  |  |  | Accept |  | done
79 | Marks | Editorial | 4 | Factory communication network environment |  | commutations | communications |  | Accept |  |  |  | Accept |  | done
80 | Marks | Editorial | 4 | Factory communication network environment |  | Strikeout: stability |  |  | Revise | also strike out "and" to have a meaning |  |  | Revise | strike out " stability and" | done
81 | Marks | Editorial | 4 | Factory communication network environment |  | in | on |  | Accept |  |  |  | Accept |  | done
82 | Marks | Editorial | 4 | Factory communication network environment |  | requires | may be facilitated by |  | Accept |  |  |  | Accept |  | done
83 | Marks | Editorial | 4 | Factory communication network environment |  | QoS | QoS control |  | Accept |  |  |  | Accept |  | done
84 | Marks | Editorial | 4 | Factory communication network environment |  | Time Synchronization | time synchronization |  | Accept |  |  |  | Accept |  | done
85 | Marks | Editorial | 4 | Factory communication network environment |  | Strikeout: the |  |  | Accept |  |  |  | Accept |  | done
86 | Marks | Editorial | 4 | Factory communication network environment |  | Strikeout: in section “Gaps in existing IEEE 802 technologies” |  |  | Accept |  |  |  | Accept |  | done
87 | Marks | Editorial | 4 | Factory communication network environment |  | network | networks |  | Accept |  |  |  | Accept |  | done
88 | Marks | Editorial | 4 | Factory communication network environment |  | Strikeout: below |  |  | Accept |  |  |  | Accept |  | done
89 | Marks | Editorial | 4 | Coordination System for Factory Automation |  | standards | standards, |  | Accept |  |  |  | Accept |  | done
90 | Marks | Editorial | 4 | Coordination System for Factory Automation |  | by IEC | in |  | Accept |  |  |  | Accept |  | done
91 | Weber | Editorial | 4 | Radio Environment within Factories | 14 | There are strong demands to avoid inappropriate terms such as slaves. | Change slave to follower |  | Revise | Cannot find "slave" on page 4. however there are 2 occurance to the word "slave" on page 5. replace with "follower". Also Figure 3 needs updating according |  | during discussion it was concluded that there is no need to use Master slave and could be replaced by transmitter/receiver. | Revise | Delete "Master 14 and slave transceivers were located and". Replace "there was no obstacle by a vehicle, human body and any 15 other objects in the line between the master and slave transceivers during measurement." with "The line of sight from the transmitter to the receiver was not blocked by any obstacle during measurement." Also modify in Figure 3 by replacing Master with Transmitter and Slave with Receiver. | used instead "The line of sight between the transmitter and the receiver was not blocked by any obstacle during measurement."
92 | Marks | Editorial | 5 | Coordination System for Factory Automation |  | application in other places | applications in other environments |  | Accept |  |  |  | Accept |  | done
93 | Marks | Editorial | 5 | Coordination System for Factory Automation |  | Strikeout: (a) |  |  | Accept |  |  |  | Accept |  | done
94 | Marks | Editorial | 5 | Coordination System for Factory Automation |  | Strikeout: , |  |  | Accept |  |  |  | Accept |  | done
95 | Marks | Editorial | 5 | Coordination System for Factory Automation |  | Strikeout: (b) |  |  | Accept |  |  |  | Accept |  | done
96 | Marks | Editorial | 5 | (a) The Severe Environment for Wireless Communications |  | signal | signals |  | Accept |  |  |  | Accept |  | done
97 | Marks | Editorial | 5 | (a) The Severe Environment for Wireless Communications |  | Strikeout: that |  |  | Accept |  |  |  | Accept |  | done
98 | Marks | Editorial | 5 | (a) The Severe Environment for Wireless Communications |  | and there was no | without |  | Accept |  |  |  | Accept |  | superceded by CID91
99 | Marks | Editorial | 5 | (a) The Severe Environment for Wireless Communications |  | and | , or |  | Accept |  |  |  | Accept |  | superceded by CID91
100 | Marks | Editorial | 5 | (a) The Severe Environment for Wireless Communications |  | 54Bytes | 54 bytes |  | Accept |  |  |  | Accept |  | done
101 | Marks | Editorial | 5 | (a) The Severe Environment for Wireless Communications |  | 6Mbps | 6 Mbit/s |  | Accept |  |  |  | Accept |  | done
102 | Weber | Editorial | 5 | Radio Environment within Factories | 17 | The SI units and numbers are sometimes seperated by a space sometimes not multiple occurences | put space between number and SI unit |  | Revise | accept and apply to all occurances in the document. |  |  | Revise | insert space between 12m in figure 3. also on the same page, insert space between 54Bytes and lower case for bytes. Replace 10-ms with 10 ms. Replace 6Mbps with 6 Mb/s check the whole document for consistancy and follow SI format. Also modify the units in figure 5 (5sec to 5 s, 920MHz to 920 MHz, -65dBm/MHz to -65 dBm/MHz) | implemented pending update figure 3 and figure 5
103 | Maruhashi | Technical | 6 | Radio Environment within Factories | 9 | "the noise disappears when the AGV stop" is incorrect. | Replace with "the noise appears while the AGV is breaking" (same in the figure) |  | Accept |  |  |  | Revise | Replace with "the noise appears while the AGV is braking" (same in the figure) | done
104 | Marks | Editorial | 6 | (a) The Severe Environment for Wireless Communications |  | may | show in Figure 4 may |  | Accept |  |  |  | Accept |  | done
105 | Marks | Editorial | 6 | (a) The Severe Environment for Wireless Communications |  | as indicated | . Similar issues are reported |  | Accept |  |  |  | Accept |  | done
106 | Marks | Editorial | 6 | (a) The Severe Environment for Wireless Communications |  | Measurement | Measurements |  | Accept |  |  |  | Accept |  | done
107 | Marks | Editorial | 6 | (a) The Severe Environment for Wireless Communications |  | the | one |  | Accept |  |  |  | Accept |  | done
108 | Marks | Editorial | 6 | (a) The Severe Environment for Wireless Communications |  | 920MHz |  |  | Accept |  |  |  | Accept |  | done
109 | Marks | Editorial | 6 | (a) The Severe Environment for Wireless Communications |  | Strikeout: carrying heavy load, |  |  | Accept |  |  |  | Accept |  | done
110 | Marks | Editorial | 6 | (a) The Severe Environment for Wireless Communications |  | Strikeout: within 920MHz band |  |  | Accept |  |  |  | Accept |  | done
111 | Marks | Editorial | 6 | (a) The Severe Environment for Wireless Communications |  | 920MHz | 920 MHz |  | Accept |  |  |  | Accept |  | done
112 | Marks | Editorial | 6 | (a) The Severe Environment for Wireless Communications |  | which were above | , above |  | Accept |  |  |  | Accept |  | done
113 | Marks | Editorial | 6 | (a) The Severe Environment for Wireless Communications |  | 920MHz | 920 MHz |  | Accept |  |  |  | Accept |  | done
114 | Marks | Editorial | 6 | (a) The Severe Environment for Wireless Communications |  | Under 1 GHz band | In this example, | [5 empty] | Revise | see CID 115 | as per CID115
115 | Marks | Editorial | 6 | (a) The Severe Environment for Wireless Communications |  | Strikeout: Under 1 GHz band, noise appears to cause problems for the | [6 empty] | Accept |  | done
116 | Marks | Editorial | 7 | (a) The Severe Environment for Wireless Communications |  | Strikeout: communication with sensing systems using 920MHz band wireless communications. | [6 empty] | Accept |  | done
117 | Marks | Editorial | 7 | (a) The Severe Environment for Wireless Communications |  | Strikeout: The source of the noise is attributed to manufacturing machines that are causing interference for the wireless communication systems. | [6 empty] | Accept |  | done
118 | Marks | Editorial | 7 | (a) The Severe Environment for Wireless Communications |  | 920MHz | [6 empty] | Revise | see CID 116 | as per CID116
119 | Marks | Editorial | 7 | (b) Uncoordinated and Independent Systems |  | Strikeout: progressive |  |  | Revise | instead of deleting suggest ti replace with "evolution" |  |  | Revise | replace "The progressive factory environment leads to addition and reconfiguration of machines and 5 equipment in the factory and therefore to the requirement for coexistence of heterogeneous and 6 legacy devices and systems." with "The modernised factory environment leads to addition and reconfiguration of machines and equipment, much of which is outfited with wireless network interfaces. This new environment brings about the requirement for coexistence of heterogeneous and legacy devices and systems." | done
120 | Marks | Editorial | 7 | (b) Uncoordinated and Independent Systems |  | Strikeout: in the factory |  |  | Accept |  |  |  | Accept |  | superceded by CID119
121 | Marks | Editorial | 7 | (b) Uncoordinated and Independent Systems |  | Strikeout: the |  |  | Accept |  |  |  | Accept |  | done
122 | Marks | Editorial | 7 | (b) Uncoordinated and Independent Systems |  | Strikeout: of manufacturing systems |  |  | Accept |  |  |  | Accept |  | done
123 | Marks | Editorial | 7 | (b) Uncoordinated and Independent Systems |  | original | legacy |  | Accept |  |  |  | Accept |  | done
124 | Marks | Editorial | 7 | (b) Uncoordinated and Independent Systems |  | Strikeout: Although |  |  | Accept |  |  |  | Accept |  | done
125 | Marks | Editorial | 7 | (b) Uncoordinated and Independent Systems |  | Strikeout: Wi-Fi |  |  | Accept |  |  |  | Accept |  | done
126 | Marks | Editorial | 7 | (b) Uncoordinated and Independent Systems |  | Strikeout: nevertheless, |  |  | Accept |  |  |  | Accept |  | done
127 | Marks | Editorial | 7 | (b) Uncoordinated and Independent Systems |  | there are | but |  | Accept |  |  |  | Accept |  | done
128 | Marks | Editorial | 7 | (b) Uncoordinated and Independent Systems |  | that can be used without interference | are available |  | Accept |  |  |  | Accept |  | done
129 | Marks | Editorial | 7 | (b) Uncoordinated and Independent Systems |  | which | that |  | Accept |  |  |  | Accept |  | done
130 | Marks | Editorial | 7 | (b) Uncoordinated and Independent Systems |  | factory | factory area |  | Accept |  |  |  | Accept |  | done
131 | Maruhashi | Editorial | 8 | Wireless application | 24 | "resource management" is described as ''factory resource management" in Table 1. | Replace "resource management" with ''factory resource management". |  | Accept |  |  |  | Accept |  | done
132 | Marks | Editorial | 8 | Scope of wireless applications in factory |  | Strikeout: the use of |  |  | Accept |  |  |  | Accept |  | done
133 | Marks | Editorial | 8 | Scope of wireless applications in factory |  | currently or soon-to-be used | used currently or in the near future |  | Accept |  |  |  | Accept |  | done
134 | Marks | Editorial | 8 | Scope of wireless applications in factory |  | on | in |  | Accept |  |  |  | Accept |  | done
135 | Marks | Editorial | 8 | Scope of wireless applications in factory |  | Strikeout: cod |  |  | Accept |  |  |  | Accept |  | done
136 | Marks | Editorial | 8 | Scope of wireless applications in factory |  | have to be | are |  | Accept |  |  |  | Accept |  | done
137 | Marks | Editorial | 8 | Scope of wireless applications in factory |  | has to | must |  | Accept |  |  |  | Accept |  | done
138 | Marks | Editorial | 8 | Scope of wireless applications in factory |  | Strikeout: in a way that is able |  |  | Accept |  |  |  | Accept |  | done
139 | Marks | Editorial | 8 | Scope of wireless applications in factory |  | in the wireless applications | with wireless links |  | Accept |  |  |  | Accept |  | done
140 | Marks | Editorial | 8 | Scope of wireless applications in factory |  | the | a |  | Accept |  |  |  | Accept |  | done
141 | Marks | Editorial | 8 | Scope of wireless applications in factory |  | Section “Factory Usage Scenario” | The section entitled “Factory Usage scenarios” below |  | Accept |  |  |  | Accept |  | done
142 | Marks | Editorial | 8 | Scope of wireless applications in factory |  | Strikeout: actual |  |  | Accept |  |  |  | Accept |  | done
143 | Marks | Editorial | 8 | Scope of wireless applications in factory |  | where | in which |  | Accept |  |  |  | Accept |  | done
144 | Marks | Editorial | 8 | Scope of wireless applications in factory |  | Strikeout: Scope of |  |  | Accept |  |  |  | Accept |  | done
145 | Marks | Editorial | 8 | Scope of wireless applications in factory |  | Strikeout: in |  |  | Accept |  |  |  | Accept |  | done
146 | Marks | Editorial | 8 | Scope of wireless applications in factory |  | their | by their |  | Accept |  |  |  | Accept |  | done
147 | Maruhashi | Editorial | 9 | Wireless application | 1 | 'Other" in Table 1 is should be "Others" as the same in line 25, page 8. | Replace "Other" in Table 1 with ''Others". |  | Accept |  |  |  | Accept |  | done
148 | Marks | Editorial | 9 | Communication requirements |  | They | Wireless networks |  | Accept |  |  |  | Accept |  | done
149 | Marks | Editorial | 9 | Communication requirements |  | are | networks are |  | Accept |  |  |  | Accept |  | done
150 | Marks | Editorial | 9 | Communication requirements |  | Strikeout: being |  |  | Accept |  |  |  | Accept |  | done
151 | Maruhashi | Editorial | 10 | Communication requ… | 8 | Text fonts of "figure 9" are different. | Fix it. |  | Accept |  |  |  | Accept |  | done
152 | Marks | Editorial | 10 | Communication requirements |  | Sub- |  |  | Accept |  |  |  | Accept |  | replaced with "below"
153 | Marks | Editorial | 10 | Communication requirements |  | There are | For some |  | Accept |  |  |  | Accept |  | done
154 | Marks | Editorial | 10 | Communication requirements |  | Strikeout: , |  |  | Accept |  |  |  | Accept |  | done
155 | Marks | Editorial | 10 | Communication requirements |  | Strikeout: s |  |  | Accept |  |  |  | Accept |  | done
156 | Marks | Editorial | 10 | Communication requirements |  | Strikeout: for which |  |  | Accept |  |  |  | Accept |  | done
157 | Marks | Editorial | 10 | Communication requirements |  | hundred | 100 |  | Accept |  |  |  | Accept |  | done
158 | Marks | Editorial | 10 | Communication requirements |  | higher-frequency | higher-frequency one |  | Accept |  |  |  | Accept |  | done
159 | Marks | Editorial | 10 | Communication requirements |  | It achieves | This allows |  | Accept |  |  |  | Accept |  | done
160 | Marks | Editorial | 10 | Communication requirements |  | which | that |  | Accept |  |  |  | Accept |  | done
161 | Marks | Editorial | 10 | Communication requirements |  | band | bands |  | Accept |  |  |  | Accept |  | done
162 | Marks | Editorial | 10 | Communication requirements |  | has | have |  | Accept |  |  |  | Accept |  | done
163 | Marks | Editorial | 10 | Communication requirements |  | de facto standard | typical |  | Accept |  |  |  | Accept |  | done
164 | Maruhashi | Editorial | 11 | Details of wireless… | 12 | Text fonts between footnote 5 and 6 are different. | Use the same fonts. |  | Accept |  |  |  | Accept |  | done
165 | Marks | Editorial | 11 | Details of wireless application and communication requirements |  | Node | node |  | Accept |  |  |  | Accept |  | done
166 | Marks | Editorial | 11 | Details of wireless application and communication requirements |  | observation for | a survey involving |  | Accept |  |  |  | Accept |  | done
167 | Marks | Editorial | 11 | Details of wireless application and communication requirements |  | the | many |  | Accept |  |  |  | Accept |  | done
168 | Marks | Editorial | 11 | Details of wireless application and communication requirements |  | Strikeout: surveyed |  |  | Accept |  |  |  | Accept |  | done
169 | Marks | Editorial | 11 | Details of wireless application and communication requirements |  | 20m | 20 m (throughout) |  | Accept |  |  |  | Accept |  | done
170 | Marks | Editorial | 11 | Details of wireless application and communication requirements |  | survey | [add a Citation] |  | Accept |  |  |  | Accept |  | done
171 | Weber | Technical | 11 | Communication Requirements | 1 | There are additional information regarding delay tolerance in regards of VR demonstrated in Vancouver | Add a new bar in the 5 - 10 ms range for VR |  |  | discuss: Is VR is a valid application in Factory? |  | Clarified this is not VR but rather the wearable display which have the same side effect as VR causing sickness. Wearable display with some kind of Augmented Reality. Are these for worker instruction? Disply in the glass which display the place of the error. When teh head is moved the scene in teh display also moves to update the scene and information displayed. This will cause sickness feeling if delay is slower than 10ms as per the VR presentation in March meeting. we have aleady for worker instruction. suggest to add work instruction with wearable device. add another red box called werable devices with two applications worker instructions and xxx. Maruhashi volunteer to discuss with Karl and update Figure 9 according to outcome. See proposed updated figure from Maruhashi san | Revise | agreed to adopt option #1 in 1-19-0045. | done
172 | Maruhashi | Editorial | 13 | Details of wireless… | 1 | In Table 3, "ms", "ms."are used. To see all tables from 2 to 14, expressions of units are different, i. e., "ms", "ms.", "msec,", "s", "s.", "secs." | Fix it. |  | Revise | To ensure SI is units adopted across the whole documents |  |  | Revise | also CID 102 | done
173 | Marks | Editorial | 16 | Details of wireless application and communication requirements |  | As follows we give detail description of these | Below, we describe |  | Accept |  |  |  | Accept |  | done
174 | Marks | Editorial | 16 | Details of wireless application and communication requirements |  | Strikeout: , to within each of these manufacturing scenarios |  |  | Accept |  |  |  | Accept |  | done
175 | Weber | Editorial | 22 | Technological Enhancement of Networking for Flexible Factory IoT | 10 | large spacing in the first line | Change line breaks |  | Accept | But this will be picked up by the IEEE SA any way. Need to see the effect of inserting line break. |  |  | Accept |  | done
176 | Maruhashi | Editorial | 23 | Overview of .. | 10 | "TSN defied standard L2 technology" may be better to use "defines" | Replace with "TSN defines standard L2 technology" |  | Accept |  |  |  | Accept |  | done
177 | Weber | Technical | 23 | Overview of the standard landscape for Flexible Factory IoT | 8 | Q Standard incorporates Qat as of now | Change Qat to Q and add relevant TSN amendments Qbu, Qbv |  |  | accept in principle but need to check exact text to replace Qat. |  | Suggest to repalce 1Qat with "IEEE STD 802.1Q-2018 + clause number" the clause is listed under the protocols and can refer to that one. Karl to propose the exact text to replace in 16 for the Qat row. | Revise | replace "802.1Qat" with "IEEE Std 802.1Q-2018 Clause 35" same for page 24 line 16 and page 25 line 24 | done as well as for page 24 line 24 not page 25 line 24.
178 | Weber | Technical | 23 | Overview of the standard landscape for Flexible Factory IoT | 8 | If .1BA is relevant the Joint project IEC/IEEE 60802 is of importance as well | Add 60802 reference |  |  | P60802 is a profile standard and may not be of relevance here in the context of the table. Check views of others. |  | Agreed to add P60802 as the last entry in the table 16. | Accept |  | done
179 | Weber | Technical | 24 | Gaps analysis of existing standards and technologies for Flexible Factory network | 15 | AVB was the predecessor of TSN | Change phrase to ‘Audio/Video Bridging (predecessor of TSN) Task Group’ |  | Accept |  |  | clarified replacing "‘Audio/Video Bridging Task Group’ (former TSN)" with ‘Audio/Video Bridging (predecessor of TSN) Task Group’ | Accept |  | done
180 | Weber | Technical | 24 | Gaps analysis of existing standards and technologies for Flexible Factory network | 18 | The paragraph does not help to characterize Qat. … and others do not specify what to do (provisions for the forwarding of streams) more listeners means that it is not a path but a tree SRP is MSRP and MRP (Thus, the last sentence is a little bit misleading and not really necessary in this context). | Change paragraph to The protocol allows end stations to register their willingness to "Talk" or "Listen" to specific streams, and it propagates that information through the network to reserve resources for the streams. Network bridges between the end stations maintain bandwidth reservation records to allow one or more Listeners register their intentions for the same stream over a network tree and check the bandwidth requirements and provide the forwarding information for streams. |  |  | Check the proposed text. The last sentence is still valid and correct. |  | clarified that in this case of talker to multiple listener in which a stream delivered to multiple listener, paths is more appropriate than tree because tree is a topology. For this replace path with paths. We can also add at the end to refer to MRP used for registration of streams. Also it was commented that 1Qat needs to be placed by the corresponding clause in 1Q-2018. Karl volunteered to propose additional sentence page 24 line 22 replace "other resources" "forwarding information". page 24 line 22, no mention to network signaling, "change to first sentence in clause 35: SRP utilizes three signaling protocols, MMRP (10.9), MVRP (Clause 11) and MSRP (35.1), to establish stream reservations across a bridged network." proposal to use the first sentence in clause 35 of 1Q. | Revise | replace the last sentence "The network signaling …" with "SRP utilizes three signaling protocols, MMRP (10.9), MVRP (Clause 11) and MSRP (35.1), to establish stream reservations across a bridged network." | implemented by repalcing with the following text "SRP utilizes three signaling protocols from IEEE Std 802.1Q-2018, MMRP (Clause 10.9), MVRP (Clause 11) and MSRP (Clause 35.1), to establish stream reservations across a bridged network"
181 | Weber | Editorial | 24 | Gaps analysis of existing standards and technologies for Flexible Factory network | 30 | the cited phrase is not ended in IEEE 802.1Q C.3 | Replace " .'" by "'." |  | Accept |  |  |  | Accept |  | done
182 | Weber | Technical | 24 | Gaps analysis of existing standards and technologies for Flexible Factory network | 34 | The calculation of "the best possible solution" is a very complex problem (NP-complete). Thus, the practical solutions may not calculate the best solution. | Replace "will calculate" by "can calculate" |  | Accept |  |  |  | Accept |  | done
183 | Weber | Technical | 25 | Gaps analysis of existing standards and technologies for Flexible Factory network | 3 | The paragraph assumes, that a change in the the wireless network is propagated very quickly to the CNC and the CNC can very quickly change the configuration, which is not guaranteed. | Change the paragraph in a more neutral form stating that the change in wireless need to be reflected in a CNC and possible impact to the overall system can be calculated. |  |  | need proposed replacement text to be cnosidered |  | replace "As shown in Figure 14, CNC is a new system level entity that will calculate the best possible 34 solution" with "As shown in Figure 14, CNC is a new system level entity that may be capable of calculating the best possible solution for a set of predefined configuration" | Revise | replace "As shown in Figure 14, CNC is a new system level entity that will calculate the best possible solution" with "As shown in Figure 14, CNC is a new system level entity that may be capable of calculating the best possible solution for a set of predefined configuration" | done
184 | Weber | Technical | 25 | Gaps analysis of existing standards and technologies for Flexible Factory network | 15 | The first two sentences gives historical dates and markets which are not really correct | Change first sentence to The TSN Task Group specified seamless redundancy for streams in the IEEE 802.1CB standard, specifying “Frame Replication and Elimination for Reliability” (FRER). |  |  | accept in principle check with others for accuracy |  | roger checked and believes both sentences are accurate. Request to Karl to identify his concern raised in his comment. Proposal to standardise in the IEEE 802 TSN Task Group to seamless 16 redundancy in conjunction with TSN streams, | Reject
185 | Weber | Technical | 26 | Gaps analysis of existing standards and technologies for Flexible Factory network | 9 | The last 2 sentences are not so precise (eg. Compare "link" with "FRER" and the e2 should be square( e ) but this is denoted earlier in a more correct way. | Delete the last 2 sentences |  |  | agree e^2 should be squared. Not sure should delete the two sentences just because of this typing error which can be corrected. Check with others. |  | Proposed fix by Roger replace "FRER would be expected to have a frame loss rate of ε2." with "FRER would be expected to result in a frame loss rate of ε^2." | Revise |  | done
186 | Maruhashi | Technical | 30 | Adaptation to rapid… | 3 | In table 17, "Not only “pause” but also “discard” are acceptable depending on data attributes to express a variety of QoS requirements in factory applications. " Data attributes are not defined before this part. | Replace with "Not only “pause” but also “discard” are acceptable if QoS requirements of factory applications permit it" |  | Accept |  |  |  | Accept |  | done
187 | Maruhashi | Technical | 30 | Adaptation to rapid… | 3 | In table 17, "It is required to have negotiation function with factory applications based on data attributes. Data rate reductions is requested if the factory application indicates reduction is “acceptable” in the data attributes. " Data attributes are not defined before this part. | Replace with "It is required to have negotiation function with a factory application for data rate reductions to determine if this reduction is acceptable to the application" |  | Accept |  |  |  | Accept |  | done
188 | Maruhashi | Technical | 31 | End to end network | 19 | "Data attributes are defined based on the type of application" "characteristics" rather than "type" seems better to avoid misunderstanding with traffic type. | Replace with "Data attributes are defined based on characteristics of applications" |  | Accept |  |  |  | Accept |  | done
189 | Maruhashi | Editorial | 33 | End to end network | 2 | Font in "C)" is different from "A)" and "B)". | Fix it. |  | Accept |  |  |  | Accept |  | done
190 | Maruhashi | Technical | 33 | End to end network | 4 | "Traffic types expressed by three bits may not be sufficient for factory applications. " may be inappropriate. | Replace with "The information is helpful for transportation of various traffics by better control of flows when mapping to traffic classes, scheduling and forwarding." |  | Accept |  |  |  | Accept |  | done
191 | Maruhashi | Technical | 34 | End to end network | 16 | "some TSN features may be required to perform at the same level as they would over the wired portion of the network. " "the same level" is uncertain. | Replace with "some TSN features may be required to perform seamlessly as they would over the wired portion of the network. " "the same level" is uncertain. |  | Accept |  |  |  | Accept |  | done
192 | Maruhashi | Technical | 34 | Conclusion | 24 | Need to update conclusion | text proposal is required |  | Accept | Assign to Nader to propose new draft conclusion |  | Nader will propose a new conclusion based on the updated draft report | Revise | As per <1-19-0044-02-ICne-proposed-resolution-to-cid192-conclusion> | done
193 | Marks | Editorial | 35 | Citations |  | Citations are incomplete | Make the citation format consistent. Whenever possible, each reference should include a title, a publication date, authors, and a functioning URL. |  | Revise | when possible |  |  | Revise | update according to availble information | done
194 | Marks | Editorial | 35 | Citations |  | https://www.hms-networks.com/press/2018/02/27/industrial-ethernet-is-now-bigger-thanfieldbuses | [6 empty] | Revise | see 193 | done
195 | Marks | Editorial | 35 | Citations | 18 | http://warp.da.ndl.go.jp/info:ndljp/pid/10383604/www.meti.go.jp/press/2013/05/2013 0531001/20130531001-2.pdf |  |  |  | reference [2] |  | checked the link in the document works. Agreed to add citation deltails such as title, author and date. | Revise | Agreed to add citation deltails such as title, author and date as follows: "Summary of results, Questionnaire survey regarding production equipment holding period, etc." date of publication May 2013 Author "Ministry of Economy, Trade and Industry, Industrial Machinery Division" | done
196 | Marks | Editorial | 35 | Citations |  | woods_nea_01_0318.pdf: | [Replace with a URL] |  | Accept |  |  |  | Accept |  | done
197 | Marks | Editorial | 35 | Citations |  | IEEE 802 | [add detail] |  | Accept |  |  |  | Accept |  | done
198 | Marks | Editorial | 35 | Citations |  | NIST Report “Guide to Industrial Wireless Systems Deployments” |  |  | Revise | I guess this is reference #8. comentor wants to add details and link |  |  | Revise | Add date, author and link | done
199 | Marks | Editorial | 36 | Citations |  | Draft IEEE Std P802.1CF/D3.1, https://1.ieee802.org/omniran/802-1cf/ | [Update to reflect the approved standard.] |  | Accept |  |  |  | Accept |  | done
200 | Weber | Editorial | i | contributors/supporters | 0 | typo "Webber" | replace by "Weber" |  | Accept |  |  |  | Accept |  | done
201 | Maruhashi | Technical | 12 | Table 3 | 5 | node density need updating | replace 1 with "1 to 5" in each row of the Node density column in table 3 |  |  | Late comment during discussion |  |  | Accept |  | done