IEEE P802-REVc Working Group Ballot Recirculation #1
Comment Resolution

---
Items for 24 October, 2023

---
Status 24 October 2023
Resolution status		Editing status
Accepted	31	Open	16
Revised	22	Committee	1
Rejected	6	In work	0
Suggest Accepted	0	Ready	59
Suggest Revised	13	Applied	0
Suggest Rejected	3	Total	76
# left to resolve	17	% applied	0%
% left to resolve	23%

---
Editorials – closed at this session
- Accepted: 4, 57, 34, 39, 5, 40, 6, 62, 63, 8, 9
- Revised: 41, 7
  - Presented in order they appear in the sorted comments
- No off-line comments received
- CID 13 was mistakenly marked for acceptance, but it was Suggested Rejected. We will discuss this call.

---
Schedule of contributions
- 10/24/2023
  - 17 – Rolfe (sent to editor)
  - 15, 18, 19, 20, 21, 22, 23, 24, 25 – Marks (definition of 802 Networks)
  - 26 – Marks (EPD vs. LPD)
  - 55 – Needs assignment (review by TSN participants)
  - 65 – Hamilton (GLK for 802.11)
  - 27 – Gilb (Annex G)
- 11/1/2023

---
CID 17
- Comment: Clause 4, by virtue of its title, should cover the family of IEEE standards. However, nearly every paragraph of 4.1 and 4.2 describes properties of IEEE 802 networks, a category that excludes some networks built according to IEEE 802 standards.
- Proposed Change: Generalize Clause 4 to describe the entire family of IEEE standards. Isolate the material specific to IEEE 802 networks in Clause 6.
- Suggested resolution: Revised
  - Add to Clause 4 the statement “An IEEE 802 network is a network of devices, some of which operate according to part of an IEEE 802 standard.”

---
CID 55: Original Paragraph
TSN features are a set of protocols and mechanisms specified by IEEE 802 standards from which one can select the mechanisms that are best suited to meet the needs of the applications supported by a given network. These TSN mechanisms are add-ons to generic networking mechanisms in order to establish a common network that supports TSN Streams as well as other kinds of traffic. The goals of using TSN features typically include providing guaranteed data transport with low and bounded latency, low and bounded delay variation, and extremely low packet loss for TSN Streams. TSN features evolve and new capabilities are added as part of IEEE 802 standardization efforts. Therefore, the following list is incomplete and just provides a snapshot of TSN features

---
CID 55: Paragraph suggested by 802.1
IEEE 802 standards specify TSN capabilities to provide network protocols and mechanisms for use by applications that need data transport with low and bounded latency, low and bounded delay variation, and low packet loss. The TSN capabilities augment networking protocols and mechanisms to support both TSN traffic streams as well as other traffic. TSN capabilities include:
Suggest Revised with this text.

---
Definition of 802 Networks
  - CIDs: 15, 18, 19, 20, 21, 22, 23, 24, 25 (Marks)

---
EPD vs. LPD
  - CID 26 (Marks)

---
GLK for 802.11
  - CID 65 (Hamilton)

---
CID 13 - Editorial
- Comment: (10.2, p 79, l 3) The standard number 802 cannot be used to identify the member of the family of IEEE 802 standards because each such member shares that same number.
- Proposed Change: Change "As the standard number 802 is used to identify [the] member of the family of IEEE 802 standards" to "As the standard number 802 is used to identify <each> member of the family of IEEE 802 standards"
- Proposed Resolution: Suggest Rejected
  - The current text is correct and is unchanged from the previous draft.
  - Or Accepted?
  - Or Revised, “used to identify <a> member of the family”?

---
Annex G – CID 27
- Comment: Annex G should be nornative. The protocol therein is not specified in other standards. The IEEE Registration Authority has assigned EtherType 08-42 to IEEE 802.1 for the following protocol: "Wake-on-LAN (WoL) as described in IEEE Std. 802." It is therefore important that the standard provide a normative descrtipion.
- Proposed Change: Change Annex G to be normative.

---
Editor Opinions
- Wake on LAN (WoL) was never standardized, but has been described in some references.
- IEEE P802f added this, but the scope of the group’s work was not to define an protocol or frame format.
- The current text defines only the frame format and not a protocol
- The current definition of the frame fields is incomplete.
- Security is not discussed or considered
- WoL may be deprecated at this time
- IEEE 802 might be the right group to define this, but it requires a larger audience

---
Current Annex G

---
Suggested Annex G
- Wake-on-LAN (WoL) was intended as a protocol wake up devices from a very low power mode remotely over a wired LAN connection. The EtherType 08-42 was reserved for frames using this protocol.
- The WoL frames and protocol were also referred to as “Magic Packet” by AMD. The protocol was described in the white paper “Magic Packet Technology” [Bxy] and application note “Magic Packet Technology Application in Hardware and Software” [Bxz]. Additional information can be found on the WireShark wiki page for WakeOnLAN [Byz].
- The use of the WoL protocol is deprecated.

---
Bibliography entries for new Annex G
- [Bxy] “Magic Packet Technology,” AMD publication #20231, Rev: A, Ammendment/0, November 1995
- [Bxy] “Magic Packet Technology Application in Hardware and Software,” AMD publication #20381, Rev: A, Ammendment/0, March 1996
- [Byz] “WakeOnLAN”, WireShark wiki page, https://wiki.wireshark.org/WakeOnLAN, last retrieved 24 October, 2023

---
More for today
- CID 59 – Suggest accepted
- CID 1 – Suggest Revised, Change “unified modeling language (UML) diagrams.” to be “diagrams like unified modeling language (UML).”
- CID 60 – Suggest Accepted
- CID 30 – Suggest Revised:
  - Change “Instead, traffic between 64-bit and 48-bit MAC addressed networks needs to be routed at a layer above the DLL.” to be “To avoid this, traffic between a 64-bit MAC addressed network and a 48-bit MAC addressed network needs to be routed at a layer above the DLL.”
- CID 61 – Suggest Revised:
  - Delete the sentence “Administrators …”
- CID 42 – Suggest Accepted

---
Comments remaining
- For 1 November 2023
  - CIDs 36, 38, 37, 65, 66 – Figure 8 and associated text (Gilb)
  - Others left over from today

---
Items for 4 October 2023

---
Current Status
Resolution status		Editing status
Accepted	16	Open	11
Revised	15	Committee	29
Rejected	6	In work	0
Suggest Accepted	16	Ready	36
Suggest Revised	11	Applied	0
Suggest Rejected	5	Total	76
# left to resolve	39	% applied	0%
% left to resolve	57%

---
Agenda
- List of remaining editorials
- List of current comments requiring input
- Resolution of remaining comments

---
Editorials (comment before next session)
- Unless I hear a reason to look at these, they will be resolved as indicated below at the next session.
- Suggest Accepted: 4, 57, 34, 39, 5, 40, 6, 13, 62, 41, 63, 7, 8, 9
  - Presented in order they appear in the sorted comments
- Please review off line and

---
Technicals requiring input
- 17 – Rolfe (sent to editor)
- 15, 18, 19, 20, 21, 22, 23, 24, 25 – Marks (definition of 802 Networks)
- 26 – Marks (EPD vs. LPD)
- 55 – Needs assignment (review by TSN participants)
- 65 – Hamilton (GLK for 802.11)
- 27 – Gilb (Annex G)

---
New Technicals
- Figure 8 and text: 36, 37, 38, 64, 66,
- Clause 6 – guarantee: 59
- UML-like: 1
- MAC addresses by other networks -60
- 48-64 bit mapping: 30
- Ensure vs. enable: 61
- 802.11 architecture: 42, 65

---
Family of Standards and IEEE 802 Networks
- CIDs not previously reviewed
  - 18, 19, 20, 21, 22, 23, 24, 25
- Can any of these be resolved on their own?

---
Schedule of contributions
- 10/24/2023
  - 17 – Rolfe (sent to editor)
  - 15, 18, 19, 20, 21, 22, 23, 24, 25 – Marks (definition of 802 Networks)
  - 26 – Marks (EPD vs. LPD)
  - 55 – Needs assignment (review by TSN participants)
  - 65 – Hamilton (GLK for 802.11)
  - 27 – Gilb (Annex G)
- 11/1/2023

---
Items for 13 September 2023

---
Ballot result summary
	LB1 TOTAL	LB1 %	RC1 TOTAL	RC1 %
Yes	37	84%	45	90%
No 7 16%	7	16%	5	10%
Voting Yes or No	44	100%	50	100%
Abstain, lack of time	2	3 %	1	3 %
Abstain, lack of expertise	12	21%	12	32 %
Abstain, other	0	0%	0	0%
Repondents	58		37
Voting members	56		35
Non-voting members	2		2
Number of commenters	15		6
Number of comments	195		76

---
Current Status
Resolution status		Editing status
Accepted	0	Open	9
Revised	0	Committee	67
Rejected	0	In work	0
Suggest Accepted	32	Ready	0
Suggest Revised	21	Applied	0
Suggest Rejected	13	Total	76
# left to resolve	76	% applied	0%
% left to resolve	100%

---
Results and Comments
- Ballot results on mentor at:
  - https://mentor.ieee.org/802.1/dcn/23/1-23-0021-01-Mntg-p802-revc-d1-1-wg-ballot-results.ods
- Comment are located on mentor at:
  - https://mentor.ieee.org/802.1/dcn/23/1-23-0022-01-Mntg-p802-revc-d1-1-comments-pdis.ods
- Comments marked with Suggested Accepted, Suggested Revised (with suggestion) and Suggested Rejected (with rejection reason)
  - Based solely on Technical Editors humble opinion (as a starting point).
  - Sorted by page number (you are welcome to sort them as you wish)

---
Process
- We will go through them, generally in page order
  - I have reviewed the 802.11 comments on 9/12 with the 802.11 Architecture committee
  - Most, but not all, of the suggested resolutions have been discussed with them.
- Plan:
  - Close the easy ones today
  - Schedule a call and have contributions for the more “interesting ones” in late September, early October
  - Target recirculation in early October, finishing before November Plenary.

---
Conference calls until November
- 4 October, 2023, 8 am-10 am PDT/11 am-1pm EDT
- 25 October, 2023, 8 am-10 am PDT/11 am-1pm EDT
- 1 November, 2023, 8 am-10 am PDT/11 am-1pm EDT