IEEE P802.11
Wireless LANs

TGr Timeline

Date:	November 18, 2004

Author:	Clint Chaplin
	Symbol Technologies, Inc.
	6480 Via Del Oro
	San Jose, CA  95119-1208
	Phone: +1-408-528-2766
	e-Mail: cchaplin@sj.symbol.com

Abstract

TGr Timeline

May 2004: call for use cases, test plans to be presented in July 2004

July 2004: define selection criteria, and define performance data to be part of formal proposal

July 2004: formal scope and requirements defined

July 2004: call for formal proposals (proposals with normative text) to be posted 30 days before start of November 2004 plenary, and to be presented by November 2004 (done)

August 17, 2004: Intent to Propose deadline (done)

September 2004: Finish supporting documents

September 16, 2004: Give informal preliminary presentations (optional) (done)

October 15, 2004: preliminary presentations must be available on the server (done)

November 15, 2004: give preliminary one hour presentations; carry out first step of selection procedure (done)

December 18, 2004 (IEEE Piscataway time): have preliminary draft text and presentations available on server (need to use the new templates). (done)

If there is a merger of proposals after the December 18th deadline, the group empowered the TGr chair to use his discretion to handle the situation. (done)

January 17, 2005: give more extensive presentations (preliminary draft text), with feedback from group; carry out second step in selection procedure (done)

February 12, 2005 (IEEE Piscataway time): Have final draft text and slides available on server.

March 14, 2005: Give final proposals (final draft text and slides); carry out third step in selection procedure.

March 2005: Start draft 0

May 2005: Internal Task Group letter ballot on draft

July 2005: Address comments from letter ballot

# Text boxes

- Time from PAR approval to first Letter Ballot – average of 6.6 meetings / 13 months

- TGe-7, TGf-7, TGg-9, TGh-4, TGi-6

- Time from first Letter Ballot to first Sponsor Ballot – average of 9 meetings / 18 months

- TGe-12, TGf-9, TGg-6, TGh-8, TGi-10

- (above data compiled by Bruce Kraemer)

Historical 802.11 Project Timelines