## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-05/1580r1
Venue Date: | July 2005
First Author: | Wayne Fisher, ARINC
Subject: | P802.11p Open Issues
Full Date: | 2005-07-20
Author(s): | Wayne Fisher
ARINC
2551 Riva Road, MD 21401
Phone: 410-266-4958
email: wfisher@arinc.com
Abstract:
This document contains the open issues still to be discussed and resolved. This is version R1. It included those items identified as Closed/Accepted. These items are highlighted in light blue.
Notice: This document has been prepared to assist IEEE 802.11. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein. Release: The contributor grants a free, irrevocable license to the IEEE to incorporate material contained in this contribution, and any modifications thereof, in the creation of an IEEE Standards publication; to copyright in the IEEE’s name any IEEE Standards publication even though it may include portions of this contribution; and at the IEEE’s sole discretion to permit others to reproduce in whole or in part the resulting IEEE Standards publication. The contributor also acknowledges and accepts that this contribution may be made public by IEEE 802.11. Patent Policy and Procedures: The contributor is familiar with the IEEE 802 Patent Policy and Procedures <http:// ieee802.org/guides/bylaws/sb-bylaws.pdf>, including the statement "IEEE standards may include the known use of patent(s), including patent applications, provided the IEEE receives assurance from the patent holder or applicant with respect to patents essential for compliance with both mandatory and optional portions of the standard." Early disclosure to the Working Group of patent information that might be relevant to the standard is essential to reduce the possibility for delays in the development process and increase the likelihood that the draft publication will be approved for publication. Please notify the Chair <stuart.kerry@philips.com> as early as possible, in written or electronic form, if patented technology (or technology under patent application) might be incorporated into a draft standard being developed within the IEEE 802.11 Working Group. If you have questions, contact the IEEE Patent Committee Administrator at <patcom@ieee.org>.

## Open Issues
IEEE P802.11p July Open Issues/Comments
Name | Comment Number | Page | Sub-clause | Line Number | Type of Comment | Comment | Proposed Change | Resolution (for ballot resolution use only - comments that are in any color other than white have not yet been resolved by the TG/WG) | Comment Recirculated? (Y/N/NA) (for ballot resolution use only) | Proposed Change | Resolution (for ballot resolution use only - comments that are in any color other than white have not yet been resolved by the TG/WG) | Comment Recirculated? (Y/N/NA) (for ballot resolution use only) | WKF Notes:
P802.11p, D1.1 Issues/Comments
Minutes, JAN05 | Filip/03 | 29 | 11.9.1 |  | Technical | We need to determine when we need to prevent changing the MAC address. | ?? (Justin/Jason) |  |  |  | Closed |  | Is this not a P1609 issue?
Minutes, JAN05 | Filip/08 |  | Annex A |  | Technical | Annex A needs to be reviewed/updated. (Rick Noens) | Review/Update Annex A |  |  |  | Closed |  | Ongoing. Ariel Sharon/Rick Noens providing comments. (See Annex A comments.)
Wells, Bryan | DENSO/2 | 5 | 5.9.2 | (19-20) | Technical | Do devices operating in WAVE mode need to support association and authentication when operating on the service channels? If so, how is this managed? |  |  |  |  | Closed. This is not supported. |  | Yes, See P1609.3
Wells, Bryan | DENSO/3 | 12 | 7.3.1.1 | 20 | Technical | If a unit does not have the WAVE subfield set to true, what functions can it perform on the network? |  |  |  |  | Closed. If False, no functions are performed. |  | Only non-WAVE functions. ~Whatever is "enabled" in the Capability field.
Wells, Bryan | DENSO/1 | 20 | 10.3.17.1 | 5 | Technical | Depending on the answer to earlier comments, this may not be a problem. However, if association is allowed on the service channels, this section should be modified. |  |  |  |  | Closed. This is not supported. |  | ??
Wells, Bryan | DENSO/0 | 21 | 10.3.17.3 | 24-25 | Technical | The RSSI report is supposed to be the RSSI measured for the RSSI Request. However, the receiving unit will not be aware of the RSSI Request (and high resolution mode requirement) until after it receives the message. At that time, it will be too late to change the resolution for the measurement. |  |  |  |  | see WRSS briefing |  | ONGOING discussion (7/6/05)
Wells, Bryan | DENSO/0 | no page - spec to be added | 5.9.2 |  | Technical | There is no stated measurement reference point for RF performance characteristics. | Propose referencing all cabled RF performance measurements to the (active) exposed antenna connector on the WAVE transceiver. |  |  |  | Declined. Follow "Baseline" approach. |  | Not defined in baseline document. In many cases, must depend on MFR and his certification.
P802.11p, D1.3 Issues/Comments
McNew, Justin | TNCM/10 | 15 | 7.4.5 |  | editorial | it is easy for the term of WAVEACKNOWLEDGEMENT to be confused with the normal ACK. | change WAVEACKNOWLEDGEMENT to WAVERESPONSE throughout the standard. |  |  |  | Change to WAVERESPONSE. |  | No Change. /Discuss
Liu, Jason | TNCM/12 | 17 | 10.3.9.1 | 1 | technical | the MAC reset time requirement for 2 TU is subject to investigation. |  |  |  |  | Still Open. Under investigation. |  | Still TBD
Liu, Jason | TNCM/30 | 32 | 20 | 4-10 | technical | the typical sizes of PSDU need to be reconsidered due to security overhead. | e.g. short packet size is 200 bytes, long packet size is 1000 bytes. |  |  |  | Reword 1st Paragraph of Clause 20. [Wayne, Lee, Jason, Bob, Carl, Broady, Randy] |  | Discuss.
Liu, Jason | TNCM/31 | 32 | 20 | 4-10 | technical | the Rx performances for a PSDU of 64 bytes (or 200 bytes) are not specified anywhere. | see 802.11/802.11j specifications for 1000 bytes receiver performance |  |  |  | Reword 1st Paragraph of Clause 20. [Wayne, Lee, Jason, Bob, Carl, Broady, Randy] |  | Open
McNew, Justin | TNCM/34 | 33 | 20.1.2 | Figure 20.1.2-1 | editorial | not clear that "WME" is the proper term for this standard | replace WME with SME throughout the standard |  |  |  | Use SME in place of WME. |  | Discuss
Liu, Jason | TNCM/66 | 52 | 20.3.10.6 | 12 | technical | why over a period of 5 seconds required? | need discussion |  |  |  | No Change. Jason accepts as is. |  | ~Based on GTRI analyses See also: IEEE 802.11-04/0141r0
Liu, Jason | TNCM/67 | 52 | 20.3.10.7 | 16 | technical | why over a period of 5 seconds required? | need discussion |  |  |  | No Change. Jason accepts as is. |  | ~Based on GTRI analyses
Liu, Jason | TNCM/68 | 52 | 20.3.10.8 | 20 | technical | why over a period of 5 seconds required? | need discussion |  |  |  | No Change. Jason accepts as is. |  | ~Based on GTRI analyses
P802.11p, D0.21ssues/Comments
Motorola/s | Motorola/2 | 2 | 3.52 | 15 | Editorial | Here again the word "normally" is used. This is a value jugdgement | Strike normally and replace with 'can be' or 'may be' |  |  |  | Change "normally" to "can be"
Motorola/s | Motorola/17 | 7 | figure p5 | 23 | technical | what is the relevance of this diagram ? The standard does not address integration with the vehicle so what is the relevance | remove the diagram and references to it. |  |  |  | No Change at this time. Informative. |  | No Change. Provides additional general information on the implementation of WAVE.
Motorola/s | Motorola/25 | 9 | 5.9.8 | 12 | technical | what is a "safety message" ? This is undefined in the document | add a concise definition of a safety message |  |  |  | Recommend Delete Clause 5.9.8. |  | No Change. ~Maybe should be Open/ be discussed. Note, this is an "informative" section.
Motorola/s | Motorola/26 | 9 | 5.9.8 | 15 | technical | there is no definition of a traffic stream | add definition of a traffic stream. |  |  |  | Recommend Delete Clause 5.9.8. |  | No Change. ~Maybe should be Open/ be discussed. Note, this is an "informative" section.
Zhu, Jeffrey | Zhu/2 | 14 | 7.3.2.22.4 | 6--13 | T | Update Clause 7.3.2.22.4 with the following: | • The allowed values for the WRSS parameter shall be an 8 bit value in the range from 0 through 150, with indicated values rounded to the nearest 0.2 dB as follows: 0: Power < -60 dBm; 1: Power = -59.8 dBm; 2: Power = -59.6 dBm; and so on; 150: Power > -30 dBm; 150-255: reserved . The measurement shall assume a receiver noise equivalent bandwidth of 11 MHz. | [5 empty] | Accepted. But still open for discussion. From E-mail. Incorporated into D0.21+ draft
Koga, Keiichiro | Koga/7 | 14 | 7.3.2.25 | 16-17 | Tech | Though it says WSIE needs to support more than 255 bytes, the requirement does not seem to match the Figure 46s | Add some explanation | [5 empty] | No Change. Statements are correct. But may need to expand a bit. ???
Motorola/s | Motorola/38 | 15 | 7.4.5.1 | 16 | technical | what is the definition of service provider ? | add a definition or better yet remove this entierly as this is a notion for the upper layer protocols. |  |  |  | Rick will revisit. |  | No Change at this time. Probably should consider adding. Service Provider is used several places in the doc. It is implied in the definition of PST - but not explicitly defined.
Liu, Jason | TNCM/12 | 17 | 10.3.9.1 | 9~10 | technical | the MAC reset time requirement for 2 TU is subject to investigation. | It is one of the issues under the study of random MAC address. | [5 empty] | Open
Jason Liu | TNCM/D21-1 | 19 | 10.3.17.3 | 7 | T | Add statement to indicate that the device is already in the WRSS mode. | Add at end of 10.3.17.3: "The upper layers shall be responsible for entering / exiting the WRSS mode." | [5 empty] | Accepted. But still open for discussion. The device must already be in a WRSS mode to make a WRSS measurement.
Soranno, Robert | Soranno/37 | 31 | 11.8.2 | 12 - 26' | Technical | Shouldn't this section indicate that the response is provided on the channel designated by the beacon or announcement frame | [6 empty] | ??
Soranno, Robert | Soranno/38 | 32 | 20 |  | Editorial | Should we be using "are" or "shall be" in this section? | [6 empty] | Clause 20, in general, is “normative” so using “shall” implies a “requirement” that must be met. “Are” would imply that this is a capability but may not require compliance.
Liu, Jason | TNCM/30 | 32 | 20 | 4-10 | technical | the typical sizes of PSDU need to be reconsidered due to security overhead. | e.g. short packet size is 200 bytes, long packet size is 1000 bytes. | [5 empty] | Open. Packet size of 200 bytes have not been tested/verified. (64 has been tested/verified.)
Liu, Jason | TNCM/31 | 32 | 20 | 4-10 | technical | the Rx performances for a PSDU of 64 bytes (or 200 bytes) are not specified anywhere. | see 802.11/802.11j specifications for 1000 bytes receiver performance | [5 empty] | OPEN
McNew, Justin | TNCM/34 | 33 | 20.1.2 | Figure 20.1.2-1 | editorial | not clear that "WME" is the proper term for this standard | replace WME with SME throughout the standard | [5 empty] | OPEN. Need discussion, resolution.
Motorola/s | Motorola/63 | 35 | 20.2.3.2 | 11 | Editorial | the sentence which begins: "subsequent to a period of …." is poor english and to me anyway is un-understandable | repair the language | [5 empty] | Open. Awaiting WRSS resolutions.
Motorola/s | Motorola/64 | 35 | 20.2.3.2 | 11 | technical | what is "alert signal" | define the term | [5 empty] | Open. Awaiting WRSS resolutions.
Liu, Jason | TNCM/67 | 47 | 20.3.10.7 |  | technical | Is the doppler spread for Rayleigh fading? | specify it | [5 empty] | No change. Not defined. ????
Liu, Jason | TNCM/68 | 48 | 20.3.10.8 |  | technical | How the amplitude exactly varies? | specify it | [5 empty] | No change. Not defined. ????
Note on A3: Put your name here, last name first.
Note on B3: Please sequentially identify each of your comments using the following format: LASTNAME/#
Note on C3: Please put down whether you disapproved (neg) or approved (aff) this draft project. This column should be the SAME for every comment, regardless of the type of comment you make.
Note on D3: Insert the page number of the draft to which your comment applies.
Note on E3: Insert the subclause (paragraph) number in the draft to which your comment applies.
Note on F3: Insert the line number from the page of the draft to which your comment applies. (If your document does not have line numbers, leave this column blank.)
Note on G3: State whether your comment is technical or editorial. Regardless of the type of comment, all comments must be addressed by the Sponsor.
Note on H3: Enter your specific comment here. Include some perspective on what would be needed to satisfy your concern.
Note on I3: Enter your proposed change to the draft project here. Be as specific as possible, giving exact text if you can.
Note on J3: To be filled out by the Sponsor. (for ballot resolution use only)
Note on K3: To be filled out by the Sponsor. For ballot resolution use only
Note on L3: Enter your proposed change to the draft project here. Be as specific as possible, giving exact text if you can.
Note on M3: To be filled out by the Sponsor. (for ballot resolution use only)
Note on N3: To be filled out by the Sponsor. For ballot resolution use only

## References
References: