## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-08/1205r0
Venue Date: | September 2008
First Author: | Peter Ecclesine, Cisco Systems
Subject: | 802.11y Production
Full Date: | 2008-09-26
Author(s): | Peter Ecclesine
Cisco Systems
170 W. Tasman Dr, MS SJ-10-5, San Jose, CA 95134-1706
+1-408-527-0815
Fax:
petere@cisco.com
Abstract:
The weekly tally of participant hours, submissions, comments and resolutions and draft body pages. About 31 participant weeks over 2.5 years to draft and ballot 74 pages and resolve 1638 comments.

## 11y
TG Week number | Date | Draft | Body pages | Meeting Manweeks | Comments | Non-admin submissions | Cum Manweeks | Cum Comments | Cum Non-admin submissions
40
1 | 2006-03-19 | [5 empty] | 0 | 0 | 0
2 | 2006-03-26 |  |  | 0.025 |  |  | 0.025 | 0 | 0
3 | 2006-04-02 | [5 empty] | 0.025 | 0 | 0
4 | 2006-04-09 | [5 empty] | 0.025 | 0 | 0
5 | 2006-04-16 |  |  | 0.096667 |  |  | 0.12167 | 0 | 0
6 | 2006-04-23 | [5 empty] | 0.12167 | 0 | 0
7 | 2006-04-30 |  |  | 0.025 |  |  | 0.14667 | 0 | 0
8 | 2006-05-07 |  |  | 0.23125 |  | 1 | 0.37792 | 0 | 1
9 | 2006-05-14 |  |  | 1.9 |  |  | 2.2779 | 0 | 1
10 | 2006-05-21 | [5 empty] | 2.2779 | 0 | 1
11 | 2006-05-28 |  |  | 0.025 |  |  | 2.3029 | 0 | 1
12 | 2006-06-04 |  |  | 0.025 |  |  | 2.3279 | 0 | 1
13 | 2006-06-11 |  |  | 0.25 |  |  | 2.5779 | 0 | 1
14 | 2006-06-18 |  |  |  |  | 1 | 2.5779 | 0 | 2
15 | 2006-06-25 |  |  | 0.51667 |  | 2 | 3.0946 | 0 | 4
16 | 2006-07-02 |  |  | 0.025 |  |  | 3.1196 | 0 | 4
17 | 2006-07-09 |  |  | 0.27292 |  |  | 3.3925 | 0 | 4
18 | 2006-07-16 |  |  | 4.325 |  | 2 | 7.7175 | 0 | 6
19 | 2006-07-23 | [5 empty] | 7.7175 | 0 | 6
20 | 2006-07-30 |  |  | 0.025 |  |  | 7.7425 | 0 | 6
21 | 2006-08-06 |  |  | 0.025 |  |  | 7.7675 | 0 | 6
22 | 2006-08-13 |  |  | 0.2775 |  |  | 8.045 | 0 | 6
23 | 2006-08-20 | [5 empty] | 8.045 | 0 | 6
24 | 2006-08-27 |  |  | 0.26667 |  |  | 8.3117 | 0 | 6
25 | 2006-09-03 |  |  | 0.025 |  |  | 8.3367 | 0 | 6
26 | 2006-09-10 |  |  | 0.20583 |  |  | 8.5425 | 0 | 6
27 | 2006-09-17 | 0.1 | 38 | 2.0721 |  | 2 | 10.6146 | 0 | 8 | D0.01 posted 20-Sep
28 | 2006-09-24 |  | 38 | 0.028333 |  |  | 10.6429 | 0 | 8
29 | 2006-10-01 |  | 38 | 0.025 |  |  | 10.6679 | 0 | 8
30 | 2006-10-08 |  | 38 | 0.025 |  |  | 10.6929 | 0 | 8
31 | 2006-10-15 |  | 38 |  |  |  | 10.6929 | 0 | 8
32 | 2006-10-22 |  | 38 | 0.215 | 161 | 1 | 10.9079 | 161 | 9 | Informal review of D0.01 closed 22-Oct, 06/1609r3 comments
33 | 2006-10-29 |  | 38 |  |  |  | 10.9079 | 161 | 9
34 | 2006-11-05 |  | 38 | 0.25833 |  |  | 11.1663 | 161 | 9
35 | 2006-11-12 | 0.2 | 58 | 0.025 |  | 3 | 11.1913 | 161 | 12 | D1.0 posted 17-Nov
36 | 2006-11-19 | 1 | 62 | 3.4663 |  |  | 14.6575 | 161 | 12
37 | 2006-11-26 |  | 62 |  |  |  | 14.6575 | 161 | 12
38 | 2006-12-03 |  | 62 | 0.325 |  |  | 14.9825 | 161 | 12
39 | 2006-12-10 |  | 62 | 0.025 |  |  | 15.0075 | 161 | 12
40 | 2006-12-17 |  | 62 | 0.06 |  |  | 15.0675 | 161 | 12
41 | 2006-12-24 |  | 62 |  |  |  | 15.0675 | 161 | 12
42 | 2006-12-31 |  | 62 | 0.2325 |  |  | 15.3 | 161 | 12
43 | 2007-01-07 |  | 62 | 0.425 | 695 |  | 15.725 | 856 | 12 | LB94 closed 7-Jan, 07/0008r11 comments
44 | 2007-01-14 |  | 62 | 2.1979 |  |  | 17.9229 | 856 | 12
45 | 2007-01-21 |  | 62 |  |  |  | 17.9229 | 856 | 12
46 | 2007-01-28 |  | 62 | 0.3 |  |  | 18.2229 | 856 | 12
47 | 2007-02-04 |  | 62 | 0.025 |  |  | 18.2479 | 856 | 12
48 | 2007-02-11 |  | 62 | 0.3375 |  | 2 | 18.5854 | 856 | 14
49 | 2007-02-18 |  | 62 |  |  | 2 | 18.5854 | 856 | 16
50 | 2007-02-25 |  | 62 | 0.39833 |  | 2 | 18.9838 | 856 | 18
51 | 2007-03-04 |  | 62 | 0.27708 |  |  | 19.2608 | 856 | 18
52 | 2007-03-11 | 1.2 | 57 | 3.0967 |  | 2 | 22.3575 | 856 | 20
53 | 2007-03-18 |  | 57 |  |  |  | 22.3575 | 856 | 20
54 | 2007-03-25 | 2 | 57 |  |  |  | 22.3575 | 856 | 20
55 | 2007-04-01 |  | 57 | 0.025 |  | 1 | 22.3825 | 856 | 21
56 | 2007-04-08 |  | 57 | 0.025 |  | 2 | 22.4075 | 856 | 23
57 | 2007-04-15 |  | 57 |  |  | 1 | 22.4075 | 856 | 24
58 | 2007-04-22 |  | 57 |  |  |  | 22.4075 | 856 | 24
59 | 2007-04-29 |  | 57 | 0.1 | 265 |  | 22.5075 | 1121 | 24 | LB104 closed 5-May, 07/0602r7 comments
60 | 2007-05-06 |  | 57 | 0.2125 |  |  | 22.72 | 1121 | 24
61 | 2007-05-13 |  | 57 | 2.2363 |  |  | 24.9562 | 1121 | 24
62 | 2007-05-20 |  | 57 |  |  |  | 24.9562 | 1121 | 24
63 | 2007-05-27 |  | 57 | 0.025 |  |  | 24.9812 | 1121 | 24
64 | 2007-06-03 | 3 | 55 | 0.15 |  |  | 25.1312 | 1121 | 24
65 | 2007-06-10 |  | 55 |  |  |  | 25.1312 | 1121 | 24
66 | 2007-06-17 |  | 55 |  | 77 |  | 25.1312 | 1198 | 24 | LB106 closed 20-Jun, 07/2019r6 comments
67 | 2007-06-24 |  | 55 | 0.26667 |  |  | 25.3979 | 1198 | 24
68 | 2007-07-01 |  | 55 | 0.22625 |  | 2 | 25.6242 | 1198 | 26
69 | 2007-07-08 |  | 55 | 0.265 |  | 2 | 25.8892 | 1198 | 28
70 | 2007-07-15 | 4 | 70 | 0.31875 |  | 1 | 26.2079 | 1198 | 29
71 | 2007-07-22 |  | 70 |  |  |  | 26.2079 | 1198 | 29
72 | 2007-07-29 |  | 70 | 0.025 |  |  | 26.2329 | 1198 | 29
73 | 2007-08-05 |  | 70 | 0.025 |  |  | 26.2579 | 1198 | 29
74 | 2007-08-12 |  | 70 |  |  |  | 26.2579 | 1198 | 29
75 | 2007-08-19 |  | 70 |  | 189 |  | 26.2579 | 1387 | 29 | LB109 closed 21-Aug, 07/2333r7 comments
76 | 2007-08-26 |  | 70 | 0.10833 |  |  | 26.3662 | 1387 | 29
77 | 2007-09-02 |  | 70 | 0.285 |  | 2 | 26.6512 | 1387 | 31
78 | 2007-09-09 |  | 70 | 0.025 |  | 1 | 26.6762 | 1387 | 32
79 | 2007-09-16 | 5 | 73 | 0.8025 |  | 2 | 27.4787 | 1387 | 34
80 | 2007-09-23 |  | 73 |  |  |  | 27.4787 | 1387 | 34
81 | 2007-09-30 |  | 73 | 0.025 |  |  | 27.5037 | 1387 | 34
82 | 2007-10-07 |  | 73 | 0.025 | 42 |  | 27.5287 | 1429 | 34 | LB112 closed 13-Oct, 07/2623r5 comments
83 | 2007-10-14 |  | 73 | 0.16667 |  |  | 27.6954 | 1429 | 34
84 | 2007-10-21 |  | 73 | 0.15 |  | 1 | 27.8454 | 1429 | 35
85 | 2007-10-28 |  | 73 | 0.0975 |  | 1 | 27.9429 | 1429 | 36
86 | 2007-11-04 |  | 73 | 0.097917 |  |  | 28.0408 | 1429 | 36
87 | 2007-11-11 | 6 | 71 | 0.46083 |  | 1 | 28.5017 | 1429 | 37
88 | 2007-11-18 |  | 71 |  |  |  | 28.5017 | 1429 | 37
89 | 2007-11-25 |  | 71 |  |  |  | 28.5017 | 1429 | 37
90 | 2007-12-02 |  | 71 | 0.025 | 36 |  | 28.5267 | 1465 | 37 | LB116 closed 8-Dec, 07/2945r1 comments
91 | 2007-12-09 |  | 71 | 0.1275 |  | 1 | 28.6542 | 1465 | 38
92 | 2007-12-16 | 7 | 67 |  |  |  | 28.6542 | 1465 | 38
93 | 2007-12-23 |  | 67 |  |  |  | 28.6542 | 1465 | 38
94 | 2007-12-30 |  | 67 |  |  |  | 28.6542 | 1465 | 38
95 | 2008-01-06 |  | 67 | 0.025 |  |  | 28.6792 | 1465 | 38
96 | 2008-01-13 |  | 67 | 0.1475 |  |  | 28.8267 | 1465 | 38
97 | 2008-01-20 |  | 67 |  |  |  | 28.8267 | 1465 | 38
98 | 2008-01-27 |  | 67 | 0.025 | 146 |  | 28.8517 | 1611 | 38 | SB closed 30-Jan, 08/0226r8 comments
99 | 2008-02-03 |  | 67 | 0.2625 |  |  | 29.1142 | 1611 | 38
100 | 2008-02-10 |  | 67 | 0.020833 |  |  | 29.135 | 1611 | 38
101 | 2008-02-17 |  | 67 | 0.1175 |  | 1 | 29.2525 | 1611 | 39
102 | 2008-02-24 | 8 | 72 | 0.065 |  |  | 29.3175 | 1611 | 39
103 | 2008-03-02 |  | 72 | 0.025 | 22 |  | 29.3425 | 1633 | 39 | 802.11y-1 closed 8-Mar, 08/0277r4 comments
104 | 2008-03-09 | 9 | 72 | 0.11667 |  |  | 29.4592 | 1633 | 39
105 | 2008-03-16 |  | 72 | 0.34833 |  |  | 29.8075 | 1633 | 39 | 1.3696
106 | 2008-03-23 | [5 empty] | 29.8075 | 1633 | 39 | 802.11y-2 closed 27-Mar, 08/0443r3 comments
107 | 2008-03-30 |  |  |  | 2 |  | 29.8075 | 1635 | 39
108 | 2008-04-06 | 10 | 72 | 0.135 |  |  | 29.9425 | 1635 | 39 |  | 1197.7
109 | 2008-04-13 | [5 empty] | 29.9425 | 1635 | 39 | 802.11y-3 closed 18-Apr, 08/0467r3 comments
110 | 2008-04-20 |  |  | 0.083333 | 2 |  | 30.0258 | 1637 | 39
111 | 2008-04-27 |  |  | 0.07 |  |  | 30.0958 | 1637 | 39 |  | 1203.8333
112 | 2008-05-04 |  |  | 0.025 |  |  | 30.1208 | 1637 | 39
113 | 2008-05-11 |  |  | 0.075 |  |  | 30.1958 | 1637 | 39
114 | 2008-05-18 | [5 empty] | 30.1958 | 1637 | 39
115 | 2008-05-25 |  |  | 0.025 |  |  | 30.2208 | 1637 | 39
116 | 2008-06-01 | 11 | 72 | 0.0675 | 1 |  | 30.2883 | 1638 | 39
117 | 2008-06-08 | [5 empty] | 30.2883 | 1638 | 39
118 | 2008-06-15 | [5 empty] | 30.2883 | 1638 | 39 | 802.11y-4 closed 20-Jun, 08/0735r0 comment
119 | 2008-06-22 |  |  | 0.035 |  |  | 30.3233 | 1638 | 39
120 | 2008-06-29 |  |  | 0.025 |  |  | 30.3483 | 1638 | 39
121 | 2008-07-06 |  |  | 0.025 |  |  | 30.3733 | 1638 | 39
122 | 2008-07-13 |  |  | 0.1025 |  |  | 30.4758 | 1638 | 39
123 | 2008-07-20 | [5 empty] | 30.4758 | 1638 | 39
124 | 2008-07-27 |  |  | 0.025 |  |  | 30.5008
125 | 2008-08-03 | [5 empty] | 30.5008
126 | 2008-08-10 | [5 empty] | 30.5008
127 | 2008-08-17 | [5 empty] | 30.5008
128 | 2008-08-24 | [5 empty] | 30.5008
129 | 2008-08-31 |  |  | 0.025 |  |  | 30.5258
130 | 2008-09-07 |  |  | 0.1 |  |  | 30.6258
131 | 2008-09-14 |  | 74 |  |  |  | 30.6258
132 | 2008-09-21 | [5 empty] | 30.6258 |  |  | Approved Standard 25 September, 2008
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156

## Pagecount
|  | body pages | to Review | NesCom | RevCom | Per month | TG months | Actual months |  | fcast Months | fcast RevCom
802.11-2007 |  | 1184 |  | 2003-03-20 | 2007-03-08 | 24.7177 |  | 48 | 0.0145 | 67.0138 | 2008-10-06 04:02
11k-2008 | Radio Resource Measurement | 222 | 1406 | 2002-12-11 | 2008-05-09 | 3.3985 |  | 51 | 0.0145 | 59.6935 | 2007-11-20 17:27
11r-2008 | Fast Roaming | 108 | 1514 | 2004-05-13 | 2008-05-09 | 2.2423 |  | 48 | 0.0145 | 52.2749 | 2008-09-10 07:36
11y D11.0 | 3650-3700 MHz Operation in USA | 74 | 1588 | 2006-03-16 | 2008-09-25 | 2.4226 | 26 | 30 | 0.0145 | 47.0439 | 2010-02-06 01:51
11w D6.0 | Protected Management Frames | 65 | 1653 | 2005-03-20 | 2009-12-09 | 1.1399 | 54 |  | 0.0125 | 49.5238 | 2009-04-26 02:17
11n D7.0 | High Throughput | 529 | 2182 | 2003-09-11 | 2009-09-11 | 7.3003 | 72 |  | 0.0125 | 74.3761 | 2009-11-07 21:03
11z D2.0 | Extensions to Direct Link Setup | 45 | 2227 | 2007-08-22 | 2009-09-11 | 1.8126 | 25 |  | 0.0125 | 42.3529 | 2011-02-23 04:14
11p D4.02 | Wireless Access for the Vehicular Environment | 37 | 2264 | 2004-09-23 | 2009-12-09 | 0.58815 | 62.5 |  | 0.0125 | 38.4416 | 2007-11-29 20:34
11v D3.02 | Wireless Network Management | 295 | 2559 | 2004-12-08 | 2010-03-26 | 4.6141 | 63.5 |  | 0.0125 | 70.4478 | 2010-10-09 01:04
11u D3.01 | Interworking w/ External Networks | 164 | 2723 | 2004-12-08 | 2010-03-26 | 2.5651 | 63.5 |  | 0.0125 | 64.3137 | 2010-04-06 11:46
11s D2.02 | Mesh Networking | 254 | 2977 | 2004-05-13 | 2010-09-12 | 3.3219 | 64 |  | 0.0125 | 69.1156 | 2010-02-01 17:58
11mb | REV-mb
11aa | Video Transport Streams |  |  | 2008-12-03 | 2011-06-17 |  | 30.5
11ac | VHTL6 |  |  | 2008-09-26
Total |  | 2977
|  |  |  | Months | equals | pages | divided by | (0.5 + (0.0125 * pages))
Formulas:
fcast RevCom = [NesCom]+30.25*[fcast Months]

## Timelines
This spreadsheet has the 802.11 WG, 802 EC and Standards Board agenda and meeting dates and current timelines
802.11 WG |  | 2008-09-12 | 2008-11-14 | 2009-01-23 | 2009-03-13 | 2009-05-15 | 2009-07-17 | 2009-09-25 | 2009-11-20 |  | 2010-03-19 |  | 2010-07-16 |  | 2010-11-12 | 2011-03-18 | 2011-07-15
802 EC agenda |  | 2008-11-14: 2008-10-15; 2009-03-13: 2009-02-11; 2009-07-17: 2009-06-17; 2009-11-20: 2009-10-21 |  | 2010-02-17 |  | 2010-06-16 |  | 2010-10-13 | 2011-02-16 | 2011-06-15
802 EC vote |  | 2008-11-14: 2008-11-14; 2009-03-13: 2009-03-13; 2009-07-17: 2009-07-17; 2009-11-20: 2009-11-20 |  | 2010-03-19 |  | 2010-07-16 |  | 2010-11-12 | 2011-03-18 | 2011-07-15
RevCom agenda |  | 2008-08-15 | 2008-10-20 |  | 2009-02-06 | 2009-05-07 |  | 2009-07-31 |  | 2009-10-19 | 2010-02-14 | 2010-05-06 |  | 2010-08-01 | 2010-10-18 | 2011-02-11 | 2011-05-05
RevCom vote |  | 2008-09-25 | 2008-12-10 |  | 2009-03-18 | 2009-06-17 |  | 2009-09-11 |  | 2009-12-09 | 2010-03-26 | 2010-06-16 |  | 2010-09-12 | 2010-12-08 | 2011-03-23 | 2011-06-15
|  | pages | pages per month |  | pagecnt RevCom
11k-2008 | Radio Resource Measurement | 2008-09-12: 222; 2008-11-14: 4.3529; 2009-03-13: 2007-11-20 17:27
11r-2008 | Fast Roaming | 2008-09-12: 108; 2008-11-14: 2.25; 2009-03-13: 2008-09-10 07:36
11y D11.0 | 3650-3700 MHz Operation in USA | 2008-09-12: 74; 2008-11-14: 2.4667; 2009-03-13: 2010-02-06 01:51
11w D6.0 | Protected Management Frames | 2008-09-12: 65; 2008-11-14: 1.1399; 2009-03-13: 2009-04-26 02:17 | 2009-12-09
11n D6.03 | High Throughput | 2008-09-12: 529; 2008-11-14: 7.3003; 2009-03-13: 2009-11-07 21:03; 2009-09-25: 2009-09-11
11z D2.0 | Extensions to Direct Link Setup | 2008-09-12: 45; 2008-11-14: 1.8126; 2009-03-13: 2011-02-23 04:14; 2009-09-25: 2009-09-11
11p D4.02 | Wireless Access for the Vehicular Environment | 2008-09-12: 37; 2008-11-14: 0.58815; 2009-03-13: 2007-11-29 20:34 | 2009-12-09
11v D3.01 | Wireless Network Management | 2008-09-12: 295; 2008-11-14: 4.6141; 2009-03-13: 2010-10-09 01:04 |  | 2010-03-26
11u D3.01 | Interworking w/ External Networks | 2008-09-12: 164; 2008-11-14: 2.5651; 2009-03-13: 2010-04-06 11:46 |  | 2010-03-26
11s D2.02 | Mesh Networking | 2008-09-12: 254; 2008-11-14: 3.3219; 2009-03-13: 2010-02-01 17:58 |  |  |  |  | 2010-09-12

## References
References: