## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-09/0676r0
Venue Date: | 2009-06-15
Subject: | TGv Letter BallotComment Resolutions
Full Date: | 2009-06-15
Author(s): | Dorothy Stanley (TGv Chair, Aruba Networks), DStanley@arubanetworks.com
Emily Qi (TGv Editor, Intel Corporation), emily.h.qi@intel.com
Abstract:
LB#150 Master Resolution Spreedsheet. .

## LB150 Comments
ID | Commenter | Clause | Pg | Ln | E or T | Yes or No | Comment | Suggested Remedy | Resolution | Comment Resolution | Same As | Editor Status | Editor Notes | Assigned To | Category | Resolution Document | XLS Refer. | Addressed AT | LB #prev
2 | J. Thrasher | 15.2.6 | 235 | 42 | E | N | Figure 15-7 is unreadable when printed. | redraw the figure . | Accepted |  |  | Done | D6.01
3 | A. Malarky | 7.3.2.65 | 44 | 14 | T | N | Note the following is also being submitted against P802.11p D7.0. The text as written implies the standard deviation is a known value, which is not practical. The standard deviation is itself another estimate. | Change "…, and the standard deviation of the error in the offset estimate…" to "…, and an estimate of the standard deviation of the error in the offset estimate…" | Counter | TG agrees with proposed changes but the changes apply to TGp text that serves as a baseline and these changes will be incorporated provided TGp changes. |  |  |  |  | Time Advertisement+P96
4 | A. Malarky | 7.3.2.65 | 44 | 59 | E | N | The last sentence as written is not limited to just Timing Capabilities =2. Also there is a comma missing. | Change "…TSF Timer is 0. The format, including all subfields is shown in Table 7-37c." to " …TSF Timer is 0, using the format, including all subfields, shown in Table 7-37c." | Counter | same as CID #52. |  | Done | D6.01
5 | A. Malarky | 7.3.2.65 | 44 | 62 | T | N | Note the following is also being submitted against P802.11p D7.0. The text as written implies the standard deviation is a known value, which is not practical. The standard deviation is itself another estimate. | Change "The Time Error field specifies an unsigned integer in nanoseconds that defines the standard deviation of the error in the Time Value estimate." to "The Time Error field specifies an unsigned integer in nanoseconds that defines the estimate of the standard deviation of the error in the Time Value estimate." | Counter | TG agrees with proposed changes but the changes apply to TGp text that serves as a baseline and these changes will be incorporated provided TGp changes. |  |  |  |  | Time Advertisement
6 | A. Malarky | 7.3.2.68 | 66 | 63 | T | N | The resolution to comment 92 of LB146 indicated that OUI here did not refer to OUI as administered by the IEEE, but to a Vendor ID (as per the resolution : "However the 3 octet Vendor ID field referred to here (from RFC 3748) is a different value".) If this is not the OUI, as so defined by the IEEE, but some other field, then some clarification (e.g. reference to RFC 3748) or renaming is required to distinguish it from the IEEE controlled OUI. Also per abbreviations & acronyms of 802.11-2007, OUI stands for "organizationally unique identifier" and "indicate" should be "indicates". | change "The OUI field contains an Organizational Unique Identification, the first 24-bits of the network connected device, which indicate the specific vendor for that device." to "The OUI field contains a Vendor ID, per RFC 3748, the first 24-bits of the network connected device, which provides an organizationally unique identifier for the specific vendor for that device." | Counter | (1) P60L50, P66L61, P67L7, P71L6, P320L10, Change from "Manufacturer OUI" to "Manufacturer OI"; P60L50 change the length from "5" to "5 or 7" (2) P66L64, change from "The OUI field contains an Organizational Unique Identification, the first 24-bits of the network connected device, which indicate the specific vendor for that device." to "The OI field contains an Organizational Identifier,as defined in 7.1.3.21." (3)P67L3, Change the name of the field from "OUI" to "OI" and change the length from "3" to "3 or 5" |  |  |  |  | Diagnostics
7 | A. Malarky | 7.3.2.68 | 66 | 63 | E | N | Per abbreviations & acronyms of 802.11-2007, OUI stands for "organizationally unique identifier" | correct text as per comment | Accepted |  |  | Done | D6.01
8 | A. Malarky | 11.20.1 | 210 | 49 | T | N | Note the following is also being submitted against P802.11p D7.0. The text as written implies the standard deviation is a known value, which is not practical. The standard deviation is itself another estimate. | Change "…as well as the standard deviation of the error in that estimate…" to "…as well as an estimate of the standard deviation of the error in that estimate…" | Counter | TG agrees with proposed changes but the changes apply to TGp text that serves as a baseline and these changes will be incorporated provided TGp changes. |  |  |  |  | Time Advertisement
9 | J. Malinen | 7.3.2.22.13 | 34 | 32 | T | N | Reference to the URL of a IETF document that will expire before 802.11v is going to be published and is clearly stated to be work-in-progress does not look suitable for an IEEE standard. This URL is unlikely to be valid at the time IEEE 802.11v gets published. Consequently, having such a reference in normative text seems to make IEEE 802.11v depend on the publication of the Internet draft as an RFC. Is that the intention here? | Replace the temporary URL to an IETF working document with a more permanent reference to the URI format. If no such document exists yet, mark this dependency clearly and delay IEEE 802.11v publication until a suitable reference becomes available. | Counter | Change "is a URI format, provided to comply with http://www.ietf.org/internet-drafts/draft-ietf-geopriv-dhcp-lbyr-uri-option-04.txt." to "in URI format that points to a location object that can be used to return the location value for the requesting STA. The format of the location value returned when the URI is dereferenced is dependent on the location provider that the URI points to and is beyond the scope of this document." | 9 |  |  |  | Location
10 | J. Malinen | 7.3.2.21.8 | 21 | 56 | E | N | Missing verb | Replace “value” with “value exists”. Same applies to the similar D6.0 changes on page 22 line 62 and page 24 line 1. | Accepted |  | 10 | Done | D6.01
11 | J. Malinen | 7.3.2.6 | 18 | 18 | T | N | “n=log2 (maximum possible number of BSSIDs)” looks odd. Is this trying to indicate a base 2 logarithm of the maximum possible number of BSSIDs? Using subscript for “2” in that case would clarify the meaning a bit, but the use of a long text inside parenthesis may be somewhat confusing here. The unneeded use of parentheses for “k=(2n-1)” looks somewhat odd, too. | Replace “where the maximum possible number of BSSIDs is an integer power of 2, n=log2 (maximum possible number of BSSIDs) and k=(2n-1)” with “where m = the maximum possible number of BSSIDs is an integer power of 2, n = log2 m, and k = 2n - 1. | Counter | Incorprate the text changes indicated in submission 2009-0697r0. |  |  |  |  | Virtual AP
12 | J. Malinen | 7.3.2.68.5 | 60 | 8 | E | N | Undefined acronym: WFA | Add “WFA - Wi-Fi Alliance” into Clause 4. On page 69 line 59, replace “the WFA assigned identifier” with “the Wi-Fi Alliance (WFA) assigned identifier”. | Accepted |  |  | Done | D6.01
13 | J. Malinen | 7.4.12.9 | 108 | 37 | E | N | Inconsistent reference style used for an RFC. | Replace “RFC-3986” with “IETF RFC 3986-2005”. There are some additional references to RFC 3986 in the draft and those should also be made consistent with whatever reference style is going to be used (some existing RFC references in IEEE 802.11-2007 do not use this “IETF RFC <number>-<year>” style used in many places of IEEE 802.11v/D6.0). | Accepted |  |  | Done | D6.01
14 | J. Malinen | 10.3.6.1 | 126 | 55 | E | N | Why was the “TIM Broadcast” removed from the Type column of TIMBroadcastRequest? This leaves the text confusing since it is not clear which Request element this referring to. | Revert D6.0 change by replacing “As defined in Request element” with “As defined in TIM Broadcast Request element”. | Accepted |  |  | Done | D6.01
15 | J. Malinen | 11.21.2.1 | 212 | 20 | E | N | Typo | Replace “discard a received Event Request frames” with “discard received Event Request frames”. | Accepted |  |  | Done | D6.01
16 | J. Malinen | 11.21.2.2 | 213 | 7 | E | N | Plural vs. singular | Replace “5 of the most recent Transition event” with “5 of the most recent Transition events”. | Accepted |  |  | Done | D6.01
17 | J. Malinen | 11.21.2.4 | 214 | 20 | E | N | No need to repeat STA twice in the sentence. | Replace “A STA may log more than 5 of the most recent Peer-to-Peer events at a STA” with “A STA may log more than 5 of the most recent Peer-to-Peer events”. | Accepted |  |  | Done | D6.01
18 | J. Malinen | 11.21.4.1 | 219 | 32 | E | N | “wildcard BSS” is not a defined term. | Replace “wildcard BSS” with “wildcard BSSID”. | Accepted |  |  | Done | D6.01
19 | J. Malinen | 11.21.4.2 | 221 | 11 | E | N | The sentence here is next to impossible to parse due to complex set of components, length, and lack of commas. While it might be grammatically correct, it would benefit of splitting into shorter, clearer sentences. | Please reword the ESS Detection i) sentence to something easily understandable.. | Counter | Change "The STA should check for beacons transmitted by one or more APs belonging to the same ESS that configured the STA every ESS Detection Interval field in the Location Indication Parameters subelement configured by the Location Configuration Request frame" to "The ESS Detection Interval field is specified in the Location Indication Parameters subelement configured by the Location Configuration Request frame. The ESS Detection Interval defines how often the STA should check for beacons transmitted by one or more APs belonging to the same ESS that configured the STA. " |  |  |  |  | Location
20 | J. Malinen | 11.21.6.3 | 224 | 60 | E | N | “a MLME” | Replace “a MLME” with “an MLME” throughout the draft. | Accepted |  |  | Done | D6.01
21 | J. Malinen | 20.3.24 | 255 | 4 | E | N | Missing space | Replace “RXVECTORshall” with “RXVECTOR shall”. | Accepted
22 | L. Chu | 11.10.8.5 | 206 | 52 | T | Y | "The measuring STA shall not send further triggered STA Statistics reports for that trigger condition to the requesting STA until the Trigger Timeout period specified in the request frame has expired, or new trigger conditions have been requested." I assume that "that trigger condition" is the old condition compared with the new trigger condition. To me, the measuring STA will never send further triggered STA Statistics reports for that trigger condition if a new trigger condition is received. | Update the draft accordingly. | Counter | Line number reference for this comment is P206L62. Delete the phrase ", or new trigger conditions have been requested" (P206L64-65). |  |  |  |  | STA Statistics
23 | L. Chu | 11.21.2.1 | 211 | 52 | T | Y | "A STA sends an Event Request frame containing zero or more Event Request elements including one or more subelements." I am wondering how can a zero Event Request element including one or more subelements. | Clarify it. | Counter | Change from A STA sends an Event Request frame containing zero or more Event Request elements including one or more subelements to A STA sends an Event Request frame containing one or more Event Request elements, each of which contains zero or more subelements |  |  |  |  | Event
24 | L. Chu | Annex U | 340 | 1 | E |  | It should be 7.4.12 in this table. | Update the draft accordingly. | Accepted |  |  | Done | D6.01
25 | L. Chu | 11.21.2.1 | 212 | 57 | T | Y | I under standard why 11z needs to encapsulate the TDLS action frame in a data frame. But I do not understand why data encapsulation of an action frame is required here. | Clarify it. | Accepted | Event and Diagnostic frames are sent using data frames to enable the frames to be sent at lower priority than management or other data frames. This enables the frames to be exchanged without impacting high priority series, such as voice calls. (1) P212L35 Change from A STA shall transmit an Event Report with the same TID used for the Event Request which initiated this Event Report response. A STA shall only transmit Event Request and Event Report fram using Event Request and Event Report protocol payloads in Data frames using Ethertype 89-0d with Remote Frame Type field value set to Data Function, as defined in Annex U. to A STA shall only transmit Event Request and Event Report frames using Event Request and Event Report protocol payloads in Data frames using Ethertype 89-0d with the Remote Frame Type field value set to Data Function, as defined in Annex U. This enables Event Request and Report frames to be sent at lower priority than higher priority data and management frames. A STA shall transmit an Event Report with the same TID used for the Event Request which initiated the Event Report response. (2) P215L25 Change from A STA shall transmit a Diagnostic Report with the same TID that was received in the Diagnostic Request that initiated the Diagnostic Report to be transmitted by the STA. A STA shall only transmit Diagnostic Request and Diagnostic Report frames using Diagnostic Request and Diagnostic Report protocol payloads in Data frames using Ethertype 89-0d with Remote Frame Type field value set to Data Function, as defined in Annex U. to A STA shall only transmit Diagnostic Request and Diagnostic Report frames using Diagnostic Request and Diagnostic Report protocol payloads in Data frames using Ethertype 89-0d with the Remote Frame Type field value set to Data Function, as defined in Annex U. This enables the Diagnostic Request and Report frames to be sent at lower priority than higher priority data and management frames. A STA shall transmit a Diagnostic Report with the same TID used for the Diagnostic Request which initiated the Diagnostic Report response. | 25 |  |  |  | General
26 | L. Chu | 11.20.2 | 210 | 21 | T | Y | 802.11v and 802.11p use Timing Advertising frame. I think they should use different filtering rules: 802.11v should use the filtering rules defined in 802.11 baseline standard to filter Timing Advertising frale, 802.11p should use the following rule "If dot11OCBEnabled is set to TRUE, a STA shall accept the received Timing Advertising frame". | Change the text accordingly. | Counter | TG agrees with proposed changes but the changes apply to TGp text that serves as a baseline and these changes will be incorporated provided TGp changes. TGv chair will forward the comment to TGp for their consideration. |  |  |  |  | Time Advertisement
27 | A. Thomson | 3 | 5 | 6 | E | N | Poor /awkward description | Change "When the multiple BSSID advertisement capability is supported, the BSSID included in the MAC Header transmitter address field of a Beacon frame" to "The BSSID included in the MAC Header transmitter address field of a Beacon frame, when multiple BSSID advertisement capability is supported" | Accepted |  |  | Done | D6.01
28 | A. Thomson | 7.2.3.1 | 12 | 38 | T | Y | Time Zone does not change often. This information should be included in (re)association response rather than beacons | Move Time Zone (and possibly Time Advertisement) to (re)association responses | Counter | The Time Zone information element is already included in Probe Responses which should be sufficient to provide pre and post-association time zone information in a more efficient manner than including it in beacons. Time Advertisement information element should continue to be distributed via beacons periodically to aid with clock drift of the synchronization between UTC and TSF counters. Remove Time Zone information element from Table 7-8 and change clause 11.20.3 sentence from "When dot11MgmtOptionUTCTSFOffsetEnabled is true, the Time Advertisement and Time Zone elements shall be included in all Probe Response frames, and in the Beacon frame every dot11TimeAdvertisementDTIMInterval DTIMs. When the dot11MgmtOptionUTCTSFOffsetEnabled is false, the Time Advertisement and Time Zone elements shall not be included in Beacon and Probe Response frames." to "When dot11MgmtOptionUTCTSFOffsetEnabled is true, the Time Advertisement and Time Zone elements shall be included in all Probe Response frames, and the Time Advertisement element in the Beacon frame every dot11TimeAdvertisementDTIMInterval DTIMs. When the dot11MgmtOptionUTCTSFOffsetEnabled is false, the Time Advertisement and Time Zone elements shall not be included in Beacon and Probe Response frames." |  |  |  |  | Time Advertisement
29 | A. Thomson | 7.3.2.22.12 | 34 | 7 | T | Y | RFC5139 is an update to RFC4776. | Replace RFC4776 with RFC5139 | Declined | RFC4776 is the latest binary representation that is used by IEEE. RFC5139 is the latest version that is defined for the XML version (text). | 9 |  |  |  | Location
30 | A. Thomson | 7.3.2.66.1 | 45 | 64 | T | Y | 0 is presumably not a valid value for Event Response limit or is it? Does 0 mean "whatever the client can provide?" | Suggest we explicitly define 0 as whatever the client is capable of providing in the response. | Counter | Change from The Event Response Limit field contains the maximum number of requested Event Reports to be included in the Event Report Element. To The Event Response Limit field contains the maximum number of requested Event Reports to be included in the Event Report Element. A value of 0 indicates that no limit is set on the number of Event Reports to be included in the Event Report Element. |  |  |  |  | Event
31 | A. Thomson | 7.3.2.68.5 | 68 | 12 | E | N | Table v16 skips value 11 | Renumber rows 12 and higher to 11 and higher in Table v16 | Accepted |  |  | Done | D6.01
32 | A. Thomson | 7.3.2.70.1 | 73 | 30 | E | N | Table v22 skips value 8 thru 12 | Change "13-220" to "8-220" reserved row | Accepted |  |  | Done | D6.01
33 | A. Thomson | 7.3.2.78 | 88 | 56 | E | N | Missing "a" in "The max idle period is…" | Change to "The Max Idle Period field is a 16-bit unsigned integer"" | Accepted |  |  | Done | D6.01
34 | A. Thomson | 7.3.2.86 | 97 | 35 | T | Y | Time zone should not be a string. This is a very inefficient method to describe what is ultimately a number. | Define a numeric representation for time zone that is much more efficient than the string representation. | Declined | If resolution to CID28 is adopted then there is no need for a more efficient representation of time zone. |  |  |  |  | Time Advertisement
35 | A. Thomson | 11.20.3 | 210 | 40 | T | Y | There is no current definition that states the AP advertisement the offset needs to resync UTC to TSF=0 periodically so that it can account for drift. | Define such a requirement. | Counter | Adopt resolution in 09/0729r1 |  |  |  |  | Time Advertisement
36 | A. Ashley | 7.3.2.65 | 44 | 59 | T | N | The text currently states "... the Time Value field is set to the UTC UT0 time at which the TSF Timer is 0." Should this be "… time at which the TSF Timer was 0" because this time is in the past, or is it the next time that the TSF will be zero, which is in the future? | Change to "… the last time at which the TSF Timer was 0" | Accepted | As per comment |  |  |  |  | Time Advertisement
37 | A. Ashley | 7.3.2.68.5 | 69 | 56 | E | N | The WFA abbreviation is not defined in 11v nor in the baseline. | Either add "WFA WiFi Aliiance" to clause 4 or change occurances of WFA to "WiFi Alliance" | Accepted |  |  | Done | D6.01
38 | A. Ashley | 7.3.2.22.11 | 32 | 6 | T | N | In the current draft "First Sequence Number" is not used for a triggered report, however it could be used by the reporting STA to provide useful information in a triggered report. | Allow "First Sequence Number" to be reported in a triggered report by removing the sentence "This field is used only if the Measurement Result field is set to 1; otherwise, it is set to 0." and changing table v1 row "First Sequence Number" column "Triggered Report" to yes. | Accepted | [5 empty] | Multicast Diagnostics
39 | A. Ashley | 7.3.2.22.11 | 32 | 17 | T | N | In the current draft "Last Sequence Number" is not used for a triggered report, however it could be used by the reporting STA to provide useful information in a triggered report. | Allow "Last Sequence Number" to be reported in a triggered report by removing the sentence "This field is used only if the Measurement Result field is set to 1; otherwise, it is set to 0."and changing table v1 row "Last Sequence Number" column "Triggered Report" to yes | Accepted | [5 empty] | Multicast Diagnostics
40 | P. Ecclesine | 7.3.2.84 | 104 | 59 | E | N | "See 11.21.9" should reference 11.21.8 | per comment | Accepted |  |  | Done | D6.01
41 | P. Ecclesine | 7.3.2.84 | 105 | 30 | E | N | "See 11.21.9" should reference 11.21.8 | per comment | Accepted |  |  | Done | D6.01
42 | P. Ecclesine | 7.3.1.7 | 15 | 60 | E | N | Get all the <ANA> assignments filled in before another recirc, since TGv is requesting Conditional Approval to go to Sponsor Ballot. | per comment | Accepted |  |  | Done | D6.01
43 | J. Kneckt | General |  |  | T | N | When measured by only one sensor (based on rssi or flight time), the resulting location of a STA results in an area which is not closer than 'r', but closer than 'R' (an arch band). Such an area can be represented by either carrying PIDF-LO in a .11 frame, or define an efficient compact encoding for it. This latter one would be desirable, as a PIDF-LO may be very long. Such an arch band type of location is applicable both in geolocation and civic location determination cases. | define an arch band type of location representation. The arch band type may be used to describe the location (distance) of a STA from a well known point. he well known point may be represented in multiple formats, i.e. with geo coordinates (in Geo Location Report), or it may be a reference point within a civic location (Civic Location Report). | Declined | The IETF defines various formats to represent location information. The commenter suggests that there is a need for a new format. Given that the IEEE TGv group do not want to replicate work that may overlap with work in the IETF the commenter is encouraged to submit a proposal to IETF geopriv group to represent arch bands. The TG will prepare a liaison letter to the IETF to ask for modifications to their RFC that represents the required binary encodings. If the outreach to the IETF is not successfull then additional SDOs will be considered. | 43 |  |  |  | Location
44 | J. Kneckt | 7.3.2.22.12 | 33 | 41 | T | N | A civic location report only makes sense when the civic location has a reference point and the measurements are made from that reference point. RFC4776 does not define a reference point, only Civic Address Types. A location defined by these CATypes is an area without clear boundaries. A STA can not interpret (x,y,z) from an area without known boundaries. Even if the boundaries are known, what does (x,y,z) represent? The coordinate system needs to be defined. | The (x,y,z) estimates should only be taken into consideration when the civic address contains a reference point. Without reference point, the estimates should not be sent. | Counter | Delete x,y,z accuracy estimate fields and all related text. Accuracy fields will be represented by the civic location object itself. Remove Location Accuracy X-estimate, Location Accuracy Y-estimate & Location Accuracy Z-estimate from Figure 7-68q3 Remove text on P33 L55 to P33 L65 & P34 L1 P34 L5. | 44 |  |  |  | Location
45 | J. Kneckt | 11.21.5 | 223 | 30 | T | Y | The Timing Measurement Procedure could be used to measure the distance between the STAs based on the average flight time [(t2-t1)+(t4-t3)]/2. But this calculation should be done at the STA initiating the time measurement procedure, ie STA-A, but STA-A does not have the values t2 and t3. If M2-Ack carries back the values t2 and t3 back to STA-A, that would allow STA-A to perform these measurements. | add Follow on Dialog Token = n, ToA Timestamp = t2 and ToD Timestamp = t3 to M2-Ack. | Declined | The timing measurement procedure when initially proposed included the distance estimation feature in a form slightly different from the one that the commenter is proposing here. The timestamp accuracies however, are required to be in the order of a few nanoseconds (+/- 1 nanosecond error means +/- 1 feet error) for the timestamps in order for the estimated distance to be meaningful. With inherent uncertainties in the determination of timestamps, such timestamp accuracies are not possible without adding complexity to the implementation. Hence the distance estimation feature was dropped. Commenter mentioned that implementations in the future may be able to provide timestamps with greater accuracy that distance estimation may be viable. How do we address multipath issues? Proposed to the commenter during the 06/30/2009 teleconference to bring in a submission identifying changes/enhancements to the timing measurement frame and a description of the procedure to use timing measurement frame(s) for distance estimation. | 45 |  |  |  | Timing Measurement
46 | J. Kneckt | 7.3.2.1 | 12 | 38 | T | Y | The purpose of the Date Time and TimeZone element in TGU was to provide the non AP STA with the local time and time zone of the AP. Providing the STA only with the TimeZone means that the MAC layer will need to compute the local time using UTC and the offset, or using the date (which is not available any more) and the timezone information. It was discussed and decided in TGU, that the MAC layer should not be required to compute the local time. | Either: a) reverse the changes in TGu and remove this element from the beacon, or b) add the local time and date to this element | Declined | As per CID79 | 46 |  |  |  | Time Advertisement
47 | C. Chaplin | 7.3.2.85 | 96 | 59 | T | Y | My previous comment was only partially implemented. "n" is still not defined anywhere in the sub-clause. | I suggest the following (lovingly ripped off of a previous clause): "The Length field is set to 2xn+1, where n indicates the total number of Channel Entry subelements contained in the element." | Accepted | [5 empty] | Channel Usage
48 | C. Chaplin | 7.3.2.21.8 | 21 | 56 | T | Y | "For each bit in the STA Counter Trigger Condition field that is set to 1, a corresponding threshold value (defined in Figure 7-62i1) in the Triggered Reporting subelement for STA Counters." is an incomplete sentence. The part after the comma is missing something. | "For each bit in the STA Counter Trigger Condition field that is set to 1, a corresponding threshold value (defined in Figure 7-62i1) is in the Triggered Reporting subelement for STA Counters."? | Accepted | P21L56-57 Replace "For each bit in the STA Counter Trigger Condition field that is set to 1, a corresponding threshold value (defined in Figure 7-62i1) in the Triggered Reporting subelement for STA Counters." with "For each bit in the STA Counter Trigger Condition field that is set to 1, a corresponding threshold value (defined in Figure 7-62i1) is in the Triggered Reporting subelement for STA Counters." | 10 |  |  |  | STA Statistics
49 | C. Chaplin | 7.3.2.21.8 | 22 | 62 | T | Y | "For each bit in the QoS STA Counter Trigger Condition field that is set to 1, a corresponding threshold value (defined in Figure 7-62i3) in the Triggered Reporting subelement for QoS STA Counters." is an incomplete sentence. The part after the comma is missing something. | "For each bit in the QoS STA Counter Trigger Condition field that is set to 1, a corresponding threshold value (defined in Figure 7-62i3) is in the Triggered Reporting subelement for QoS STA Counters."? | Accepted | P22L62-63 Replace "For each bit in the QoS STA Counter Trigger Condition field that is set to 1, a corresponding threshold value (defined in Figure 7-62i3) in the Triggered Reporting subelement for QoS STA Counters." with "For each bit in the QoS STA Counter Trigger Condition field that is set to 1, a corresponding threshold value (defined in Figure 7-62i3) is in the Triggered Reporting subelement for QoS STA Counters." |  |  |  |  | STA Statistics
50 | C. Chaplin | 7.3.2.21.8 | 24 | 1 | T | Y | "For each bit in the RSNA Trigger Condition field that is set to 1, a corresponding threshold value (defined in Figure 7-62i5) in the Triggered Reporting subelement for RSNA Counters." is an incomplete sentence. The part after the comma is missing something. | "For each bit in the RSNA Trigger Condition field that is set to 1, a corresponding threshold value (defined in Figure 7-62i5) is in the Triggered Reporting subelement for RSNA Counters."? | Accepted | P24L1-2 Replace "For each bit in the RSNA Trigger Condition field that is set to 1, a corresponding threshold value (defined in Figure 7-62i5) in the Triggered Reporting subelement for RSNA Counters." with "For each bit in the RSNA Trigger Condition field that is set to 1, a corresponding threshold value (defined in Figure 7-62i5) is in the Triggered Reporting subelement for RSNA Counters.". |  |  |  |  | STA Statistics
51 | C. Chaplin | 7.3.2.22.13 | 34 | 32 | T | Y | This URL will be obsolete on September 9, 2009, when the I-D expires. Also, does this mean that this specification is now dependent on a standard that is not yet published? | Find a more permanent URL. | Counter | As per CID9 | 9 |  |  |  | Location
52 | C. Chaplin | 7.3.2.65 | 44 | 59 | E | Y | "The format, including all subfields is shown in Table 7-37c." | "The format, including all subfields, is shown in Table 7-37c." | Accepted |  |  | Done | D6.01
53 | C. Chaplin | 7.3.2.70.3 | 56 | 75 | T | Y | "The Length field is set to twice the number of channel entries." "n" is still undefined. | "The Length field is set to 2xn, where n indicates the total number of Channel Entry subelements contained in the element." | Accepted | Note - page and line numbers indicated by the commenter are swapped - comment refers to page 75, line 56 As per comment |  |  |  |  | Location
54 | C. Chaplin | 7.3.2.70.6 | 78 | 46 | T | Y | "If the Vertical Speed value is unknown or greater than 32766, the field is set to 32767. If the Vertical Speed value is less than -32766, the field is set to -32767." | "If the Vertical Speed value is unknown or greater than 32766, the field is set to 32767. If the Vertical Speed value is less than -32767, the field is set to -32768." | Accepted | As per comment. |  |  |  |  | Location
55 | C. Chaplin | 7.4.12.23 | 117 | 62 | E | Y | "The Supported Regulatory Classes is described in 7.3.2.54. EDITORIAL NOTE—7.3.2.56 is defined in TGy D5.0." Is it 7.3.2.54, or 7.3.2.56, or neither? | Resolve the conflict | Counter | change "7.3.2.56 is defined in TGy D5.0." to "7.3.2.54 is defined in IEEE 802.11y-2008.". |  | Done | D6.01
56 | C. Chaplin | 7.4.13.3 | 121 | 7 | E | Y | "In the Follow Up Timing Measurement frame, the Follow Up Dialog Token field is set to the value of the Dialog Token field used in the Initial Timing Measurement action frame. In the Follow Up Timing Measurement frame, the Follow Up Dialog Token is set to the value of the Dialog Token used in the Initial Timing Measurement frame." So important, you had to say it twice. | Delete one of the two. | Accepted |  |  | Done | D6.01
57 | C. Chaplin | 10.3.64.4.3 | 192 | 14 | T | Y | "This primitive is generated by the SME either in response to an MLME-DMS.indication requesting a DMS Response be sent to a non-AP STA." or ? The word "either" implys that two possibilities will be stated. There is only one possibility here. | Add the other possibility, or delete "either" | Accepted | remove "either". |  |  |  |  | Directed Multicast
58 | C. Chaplin | 11.1.2.3a | 196 | 13 | E | Y | "BSS(ID)" | "BSSID" | Accepted |  |  | Done | D6.01
59 | C. Chaplin | 11.1.2.3a | 196 | 16 | E | Y | "BSS(ID)" | "BSSID" | Accepted |  |  | Done | D6.01
60 | C. Chaplin | 11.4.4 | 205 | 61 | E | Y | "If the result code is REJECTED_WITH_SUGGESTED_BSS_TRANSITION, the non-AP STA may try to transition to other BSS." | "If the result code is REJECTED_WITH_SUGGESTED_BSS_TRANSITION, the non-AP STA may try to transition to other BSSs." | Accepted |  |  | Done | D6.01
61 | C. Chaplin | 11.21.4.2 | 221 | 59 | E | Y | "When a STA is capable of motion detection and is in motion, the In-Motion Report Interval and In-Motion number of frames per channel would apply" missing period | "When a STA is capable of motion detection and is in motion, the In-Motion Report Interval and In-Motion number of frames per channel would apply." | Accepted |  |  | Done | D6.01
62 | C. Chaplin | 15.4.4.2 | 236 | 38 | E | Y | "TIME_OF_Departure" | "TIME_OF_DEPARTURE" | Accepted |  |  | Done | D6.01
63 | C. Chaplin | 17.2.4 | 239 | 17 | E | Y | "TIME_OF_Departure" | "TIME_OF_DEPARTURE" | Accepted |  |  | Done | D6.01
64 | C. Chaplin | 18.3.5 | 245 | 28 | E | Y | "TIME_OF_Departure" | "TIME_OF_DEPARTURE" | Accepted |  |  | Done | D6.01
65 | C. Chaplin | 19.2 | 247 | 60 | E | Y | "TIME_OF_Departure" | "TIME_OF_DEPARTURE" | Accepted |  |  | Done | D6.01
66 | C. Chaplin | 20.2.5 | 250 | 31 | E | Y | "TIME_OF_Departure" | "TIME_OF_DEPARTURE" | Accepted |  |  | Done | D6.01
67 | G. Bajko | general |  |  | T | Y | The encoding of the LCI field from 802.11k is based on RFC3825, which is broken. IETF has decided to revise the encoding, but they do not have a final document yet. The open issues are editorial, the encoding is agreed. TGv should change the LCI encoding as well before going to SB, otherwise IEEE specs will end up being again published with a broken location representation. IEEE should also consider adopting the encoding from 3GPP, rather than waiting for IETF. IETF does not have expertise in location encoding, they did it once and did it wrongly. The 3GPP encoding is widely used and proven to work. | as suggested. | Declined | IETF is working on the revision. The commenter has two comments in one. Updates to the LCI fields can be done in either TGmb or TGv once the document is completed in IETF. The 2nd comment on use of 3GPP format should be submitted as a formal submission for the group to consider. Same resolution as CID43 for 2nd comment. |  |  |  |  | Location
68 | G. Bajko | general |  |  | T | Y | When measured by only one sensor (based on rssi or flight time), the resulting location of a STA results in an area which is not closer than 'r', but closer than 'R' (an arch band). Such an area can be represented by either carrying PIDF-LO in a .11 frame, or define an efficient compact encoding for it. This latter one would be desirable, as a PIDF-LO may be larger than an MPDU, thus there are fragmentation&reassembly and other issues with it. Such an arch band type of location is applicable both in geolocation and civic location determination cases. | define an arch band type of location representation, which can then be used to describe the location (distance) of a STA from a well known point. The well known point may be represented with geo coordinates (in Geo Location Report), or may be a reference point within a civic location (Civic Location Report). The binary encoding for the arch band can be referenced from the 3GPP document as well. | Declined | As per CID43 | 43 |  |  |  | Location
69 | G. Bajko | 7.3.2.22.12 | 33 | 41 | T | Y | Add compass data field (azimuth) to figure 7-68q3. Note, azimuth is not going to be defined in IETF, as that is not applicable for dhcp environment. That is why rfc3825 does not contain azimuth, but LCI does contain it. But azimuth in LCI does not replace the need to have the same capability for civic location as well. | as suggested. | Declined | The commenter is encouraged to submit a proposal that justifies the need and text changes for this addition. | 69 |  |  |  | Location
70 | G. Bajko | 7.3.2.22.12 | 33 | 41 | T | Y | A civic location report only makes sense when the civic location has a reference point and the measurements are made from that reference point. RFC4776 does not define a reference point, only Civic Address Types. A location defined by these CATypes is an area without clear boundaries. A STA can not interpret (x,y,z) from an area without known boundaries. Even if the boundaries are known, what does (x,y,z) represent? There is no coordinate system defined. | the text should either say that (x,y,z) estimates should only be taken into consideration when the civic address contains a reference point. If it doesn't, then the estimates should not be sent and ignored at the receiving side. | Counter | Fields are removed as per CID44 | 44 |  |  |  | Location
71 | G. Bajko | 7.3.2.22.12 | 33 | 43 | T | Y | What are the X,Y,Z estimates and how are those supposed to be interpreted? There is no coordinate system defined | define the coordinate system in which (x,y,z) can be interpreted. That can be a cartesian coordinate system, or polar coordinate system or euclidean space, etc., but it has to be stated what it is. In most coordinate systems there is an origin (a point) from where the distances are measured. If there is no origin (like in case of a civic address), then (x,y,z) makes no sense. | Counter | Fields are removed as per CID44 | 72 |  |  |  | Location
72 | G. Bajko | 7.3.2.22.12 | 33 | 49 | T | Y | The text says that x,y,z estimate fields are defined in RFC4776. That is not the case. The RFC does not describe any location value, nor does define any estimates. This is just a wrong reference. | add a correct reference if known, or define the x,y,z estimates and the coordinate system in which those can be interpreted. | Counter | Fields are removed as per CID44 |  |  |  |  | Location
73 | G. Bajko | 7.3.2.22.12 | 33 | 55 | T | Y | "The Location Accuracy X-estimate field is an estimated accuracy in the X-dimension ..." X-dimention belonging to maybe a cartesian coordinate system or an Euclidian one? | define it. | Counter | Fields are removed as per CID44 | 74 |  |  |  | Location
74 | G. Bajko | 7.3.2.22.12 | 33 | 43 | T | Y | The Civic Location is a variable length field. RFC4776 specifies CAType values, but the length field present in RFC4776 specifies the length of the DHCP option itself, including the DHCP type, DHCP code and the Civic Location itself. If the RFC4776 defined Civic Location is not transported using DHCP, then the type, code and legth fields are not present either. Since the length field is DHCP specific, 802.11v has to have its own field specifying the length. | define a Length field for the Location Civic Report field. | Counter | The information element has the length field already defined which covers the length of the report. See 7.3.2.22 in 11k for the length field of the measurement report element that contains the civic report sub-element. Change from The Civic Location field is a variable octet field and the format of the data is defined in IETF RFC 4776-2006. to The Civic Location field is a variable octet field and contains a list of civic address elements in TLV format as defined in IETF RFC 4776-2006. | 75 |  |  |  | Location
75 | G. Bajko | 11.21.5 | 223 | 30 | T | Y | The Timing Measurement Procedure could be used to measure the distance between the STAs based on the average flight time [(t2-t1)+(t4-t3)]/2. But this calculation should be done at the STA initiating the time measurement procedure, ie STA-A, but STA-A does not have the values t2 and t3. If M2-Ack carries back the values t2 and t3 back to STA-A, that would allow STA-A to perform these measurements. | add Follow on Dialog Token = n, ToA Timestamp = t2 and ToD Timestamp = t3 to M2-Ack. | Declined |  | 45 |  |  |  | Timing Measurement
76 | G. Bajko | Q | 311 | 34 | T | Y | The text says: ""This attribute indicates a variable octet field in URI (aka URL) format, provided to comply with RFC 3693" while it should say ""This attribute indicates a variable octet field in URI (aka URL) format, provided to comply with http://www.ietf.org/internet-drafts/draft-ietf-geopriv-lbyr-requirements-05.txt" | change as suggested | Counter | Change "This attribute indicates a variable octet field in URI (aka URL) format that contains the location by reference for the requesting STA" |  |  |  |  | Location
77 | G. Bajko | 7.3.2.22.13 | 34 | 32 | T | Y | http://www.ietf.org/internet-drafts/ draft-ietf-geopriv-dhcp-lbyr-uri-option-04.txt is the wrong reference!!!!!!!!!!!!!!!!!!!!! This shouldn't be so difficult to understand. The draft describes how to carry the URI in DHCP, but you need a reference to a document which describes what the URI has to be compliant with in order to be usable by the application layer!!!!!!!! | Change it for gods sake. | Counter | As per CID9 | 9 |  |  |  | Location
78 | G. Bajko | 7.3.2.1 | 12 | 38 | T | Y | The Time Zone field can be 40 octets long, it is not practical to put it into the beacon. Besides, it is an information which is rarely needed, thus it should be available upon request instead (as it was in TGu) | reverse the changes in TGu and remove this element from the beacon | Counter | Same resolution as CID28 |  |  |  |  | Time Advertisement
79 | G. Bajko | 7.3.2.1 | 12 | 38 | T | Y | The purpose of the Date Time and TimeZone element in TGU was to provide the non AP STA with the local time and time zone of the AP. Providing the STA only with the TimeZone means that the MAC layer will need to compute the local time using UTC and the offset, or using the date (which is not available any more) and the timezone information. It was discussed and decided in TGU, that the MAC layer should not be required to compute the local time. | Either: a) reverse the changes in TGu and remove this element from the beacon, or b) add the local time and date to this element | Declined | The AP advertises the real-time when TSF is 0. The receiving STA can determine the current time of the AP by knowing the current value of TSF, UTC0 and Timezone which is receives in multiple ways. Therefore the STA can calculate the current time of the AP when it receives a Time Advertisement information element in beacons or probe responses. | 46 |  |  |  | Time Advertisement
80 | K. Padam | 7.3.2.22.12 | 33 | 41 | T | N | Consider adding compass data field (azimuth) to figure 7-68q3. The reason is that it can provide the civic location same capability as currently provided for LCI. Azimuth information in LCI does not replace the need to have the same capability for civic location as well. | as suggested. | Declined | As per CID69 | 69 |  |  |  | Location
81 | K. Padam | 7.3.2.22.12 | 33 | 41 | T | N | A civic location report can be only useful when the civic location has a reference point and the measurements are made from that reference point. A STA can not interpret (x,y,z) from an area of a civic location without any known boundaries or a reference point. The coordinate sytem or specific method to specify (x,y, z) accuracy estimates is not clear. | the text need to clear enough to either state that (x,y,z) estimates should only be taken into consideration when the civic address contains a reference point (with a clear format of this definition). If it doesn't, then the estimates should not be sent and ignored at the receiving side. | Counter | Fields are removed as per CID44 |  |  |  |  | Location
82 | K. Padam | 7.3.2.22.12 | 33 | 43 | T | N | What are the X,Y,Z estimates and how are those supposed to be interpreted? There is no coordinate system or specific method defined to specify this. | define how the coordinate system in which (x,y,z) can be interpreted. That can be a cartesian coordinate system, or polar coordinate system or euclidean space, etc., but it has to be stated what it is, and how it has to be specified (in terms of what absolute reference point) | Counter | Fields are removed as per CID44 | 72 |  |  |  | Location
83 | K. Padam | 7.3.2.22.12 | 33 | 55 | T | N | "The Location Accuracy X-estimate field is an estimated accuracy in the X-dimension ..." X-dimention belonging to maybe a cartesian coordinate system or an Euclidian one? | define it. | Counter | Fields are removed as per CID44 | 74 |  |  |  | Location
84 | K. Padam | 7.3.2.22.12 | 33 | 43 | T | N | The Civic Location is a variable length field. RFC4776 specifies CAType values, but the length field present in RFC4776 specifies the length of the DHCP option itself, including the DHCP type, DHCP code and the Civic Location itself. If the RFC4776 defined Civic Location is not transported using DHCP, then the type, code and legth fields are not present either. Since the length field is DHCP specific, 802.11v has to have its own field specifying the length. | define a Length field for the Location Civic Report field. | Counter | Same resolution as per CID74 | 75 |  |  |  | Location
85 | K. Padam | 11.21.5 | 223 | 30 | T | N | The Timing Measurement Procedure could be used to measure the distance between the STAs based on the average flight time [(t2-t1)+(t4-t3)]/2. But this calculation should be done at the STA initiating the time measurement procedure, ie STA-A, but STA-A does not have the values t2 and t3. If M2-Ack carries back the values t2 and t3 back to STA-A, that would allow STA-A to perform these measurements. | add Follow on Dialog Token = n, ToA Timestamp = t2 and ToD Timestamp = t3 to M2-Ack. | Declined |  | 45 |  |  |  | Timing Measurement
86 | K. Padam | 7.3.2.1 | 12 | 38 | T | N | The purpose of the Date Time and TimeZone element in TGU was to provide the non AP STA with the local time and time zone of the AP. Providing the STA only with the TimeZone means that the MAC layer will need to compute the local time using UTC and the offset, or using the date (which is not available any more) and the timezone information. It was discussed and decided in TGU, that the MAC layer should not be required to compute the local time. | Either: a) reverse the changes in TGu and remove this element from the beacon, or b) add the local time and date to this element | Declined | As per CID79 | 46 |  |  |  | Time Advertisement
87 | M. Hamilton | 7.3.2.6 | 18 | 37 | T | Y | Response to CID 207 on LB146 really wasn't sufficient. If we (as the Standard writers) "know the conditions under which method B or method A is used" we should state those conditions explicitly in the Standard. Otherwise, we are expecting every implementer to (re)derive the same understanding of these conditions, which is risky and a waste of effort. | We seem to know the conditions ("For example, when all the associated STAs support the multiple BSSID capability, the AP knows it and encodes the TIM element using method B. There are other example conditions as well."), so list them, and there will no room for misinterpretation. | Declined | The existing text is clear. The commenter is encouraged to develop additional text to be added to Annex L. |  |  |  |  | Virtual AP
88 | M. Hamilton | 7.4.13 | 119 | 38 | E | N | Wouldn't unprotected Action frames be useful outside of just WNM? Why not name this facility just "Unprotected Action"? | Change "Unprotected WNM Action" to "Unprotected Action" throughout the Amendment. | Declined | The group prefers to use "Unprotected WNM Action". All HT action frames are unprotected action frames. Obviously, these HT action frames don’t belong to Unprotected Action.
89 | M. Hamilton | 7.4.13.2 | 120 | 27 | T | Y | The term "AID 0 field" isn't a defined term. | Change "the AID 0 field" to "the bit corresponding to buffered group addressed frames". | Accepted | Change from The TIM Element field contains a TIM element as specified in 7.3.2.6. The AID 0 field is set to zero for all BSSIDs and ignored upon reception. to The TIM Element field contains a TIM element as specified in 7.3.2.6. The bit corresponding to buffered group addressed frames is set to zero for all BSSIDs and ignored upon reception. |  |  |  |  | TIM Broadcast
90 | G. Venkatesan | 7.4.13.3 | 120 | 34 | T | N | [Robert Stacey] The Timing Measurement frame also triggers the capture of timestamps so the statement about its use is incomplete. Since this is the frame format section, descriptive text on its use is redundent (already present in 11.21.5). | Change the first paragraph to simply state "The format of the Timing Measurement frame is shwon in Figure v115." | Counter | Replace the first paragraph in Cl. 7.4.13.3 with "The Timing Measurement frame is to support the timing measurement procedure described in 11.21.5. The format of the Timing Measurement frame is shown in Figure v115.". Editor to incorporate changes as shown in document 09/711r1. |  |  |  |  | Timing Measurement
91 | G. Venkatesan | 7.4.13.3 | 120 | 38 | T | N | [Rober Stacey] For simplicity, all fields should always be present in the frame. The lack of meaningful values in the fields can be signaled with Follow UP Dialog Token = 0. | Remove (optional) from the figure on all fields. Modify | Counter | Change as recommended. Also change descriptions for ToD, ToA, Max ToD Error and Max ToA Error in 10.3.54.1.2 to reflect this. Editor to incorporate changes as shown in document 09/711r1. |  |  |  |  | Timing Measurement
92 | G. Venkatesan | 7.4.13.3 & 11.21.5 |  |  | T | N | [Robert Stacey] The timing measurement frames are sent in pairs. The first frame triggers the timestamp captures and the second transfers the values captured. Each frame, however, can both trigger the capture of timestamps and transfer previously captured timestamps. It is not clear from the text that this is possible. | Clarify the text to show that this is possible. | Accepted | Change the frame description in Cl. 7.4.13.3 and the Timing Measurement procedure in Cl. 11.21.5 as shown in document 09/711r1. Editor to incorporate changes as shown in document 09/711r1. |  |  |  |  | Timing Measurement
93 | G. Venkatesan | 11.21.5 | 222 | 12 | E | N | [Robert Stacey] "Timing Measurement procedure" should not be capitalized. | Uncapitalize | Accepted |  |  | Done | D6.01
94 | G. Venkatesan | 11.21.5 | 222 | 17 | T | N | [Robert Stacey] The normative behavior is that a STA that supports the timing measurement procedure may send Timing Measurement frames to a STA that also supports the timing measurement procedure. No normative statements can be made about what the receiving STA does with the frames. Also, (obviously) a STA that supports the timing measurement procedure is not required to send Timing Measurement frames to another STA. | Change the first sentence to read "A STA that supports the timing measurement procedure may transmit Timing Measurement frames addressed to a peer STA that also supports the timing measurement procedure. The procedure by which a STA determines that it will transmit Timing Measurement frames addressed to a peer STA is beyond the scope of this standard." | Accepted | Change the description of Timing Measurement procedure in Cl. 11.21.5 as shown in document 09/711r1, to only include normative behavior. Editor to incorporate changes as shown in document 09/711r1. |  |  |  |  | Timing Measurement
95 | G. Venkatesan | 7.3.2.21.8 | 21,23, 24 | 61-62, 3-4, 6-7 | T | N | "One or more trigger conditions are set with specified thresholds." The requirement that at least one of the bits in the {STA¦QoS STA¦RSNA] Counter Trigger Condition field is not adequately conveyed by this sentence. | Reword to state the requirement clearly. If Clause-7 is not the appropriate place for stating this requirement, state it in Cl. 11.10.8.5. | Counter | P206L53 Replace "One or more trigger conditions may be set with specified thresholds" with "One or more trigger conditions shall be set with specified thresholds." |  |  |  |  | STA Statistics
96 | G. Venkatesan | 7.4.13.3 | 130 | 64-65 | T | N | "The Dialog Token set to zero indicates that the Timing Measurement frame is not part of a time synchronization transaction." 1. Malformed sentence 2. What is the purpose of this statement? Are there special uses for the Timing Measurement frame when used with the Dialog Token set to zero? When would one use a Timing Measurement frame outside of the Timing Synchronization transaction? 3. Time synchronization is sometimes (one instance in Annex-U) referred to as Timing Synchronization. Are they the same? | Fix inconsistencies. Is Time Synchronization Procedure and better term instead of Time Synchronization transaction? | Accepted | Replace "The Dialog Token set to zero indicate that the Timing Measurement frame is not part of a time synchronization transaction, see 11.21.5." with "The Dialog Token is set to zero to indicate that the Timing Measurement frame will not be followed by a subsequent follow up Timing Measurement frame." Editor to incorporate changes as shown in document 09/711r1. Replace P141L52-54 "This accuracy test does not apply when the Time of Departure timestamps are exclusively used for Timing Synchronization (See 11.20.5)." with "This accuracy test does not apply when the Time of Departure timestamps are exclusively used for timing measurement (See 11.21.5)." |  |  |  |  | Timing Measurement
97 | G. Venkatesan | 10.3.54 | 150 | 33-38 | T | N | Use of different terms to refer to the same/similar data -- tiiming measurement information, time synchronization information, time synchronization information exchange. | Reword this paragraph to accurately describe what Figure V120 represents -- the four time instants t1, t2, t3 and t4. | Accepted | P150L35-37 Replace "The informative diagram in Figure v120 depicts the time synchronization information exchange. Multiple exchange of time synchronization information may be required in order for a STA to synchronize itself and remain synchronized with respect to another STA. " with "The informative diagram in Figure v120 depicts various points in time that are of interest to the timing measurement procedure. " P152L4-5 Replace "On receipt if this primitive, the MLME constructs a Timing Measurement frame containing the time measurement parameters specified." with "On receipt if this primitive, the MLME constructs a Timing Measurement frame with the specified parameters." Editor to incorporate changes as shown in document 09/711r1. |  |  |  |  | Timing Measurement
98 | G. Venkatesan | 10.3.54.3.2 | 154 | 12-13 | E | N | "Max ACK TOD" parameter should be "Max ACK TOD Error" in the table in order to match the parameter list in the primitive. |  | Accepted |  |  | Done | D6.01
99 | G. Venkatesan | 11.21.5 | 222 | 1 | T | N | "Timing Measurement Procedure"? Are we measuring time? Should this be called "Time Synchronization Procedure?" |  | Declined | The receiving STA never synchronizes the local clock. The timing measurement procedure only computes offset of the local clock relative to that of a peer clock. In addition time is measured (estimated) at point t1, t2, t3 and t4. Hence timing measurement is more appropriate than timing/time synchronization. |  |  |  |  | Timing Measurement
100 | G. Venkatesan | 11.21.5 | 222 | 18-20 | T | N | "… timing values in the Timing Measurement action frame along with timing information derived locally ..."? | Replace with "values in the received Timing Measurement action frame along with time information that is locally estimated/determined corresponding to events related to the receipt of the Timing Measurement action frame and the transmission of the corresponding ACK..." | Counter | The referred text is removed as a result of rewriting the Timing Measurement procedure for clarity. Editor to incorporate changes as shown in document 09/711r1. |  |  |  |  | Timing Measurement
101 | G. Vlantis | 11.21.2.1 | 212 | 57 | T | Y | The Event Request and Event Report protocol smack of action frames. It's not clear why they are being encapsulated in data frames. Such encapsulation might be desirable in a tunneling standard (.11z, .11s), or if the results were being sent over a higher layer (IP) but not clear here. | Please change these two frames to action frames or clarify the motivation for using data frames. | Counter | Same as resolution to CID 25 | 25 |  |  |  | General
102 | G. Vlantis | 11.21.3.1 | 215 | 28 | T | Y | The Diagnostic Request and Diagnostic Report protocol smack of action frames. It's not clear why they are being encapsulated in data frames. Such encapsulation might be desirable in a tunneling standard (.11z, .11s), or if the results were being sent over a higher layer (IP) but not clear here. | Please change these two frames to action frames or clarify the motivation for using data frames. | Counter | Same as resolution to CID 25 | 25 |  |  |  | General
103 | Y. Seok | 11.21.15 | 231 | 20-23 | T | Y | Even though DMS is terminated by AP policy (because of the lack of wireless resource), station still wants to receive the multicast stream. In this case, station can not filter some duplicated multicast frames after DMS is terminated. For example, AP transmits A1, A2, A3, A4, M1, M2, A5, A6, A7, A8, M3, M4 frames, where A1 means a unicast frame for STA A with sequence number set to 1 and M1 means a multicast frame with sequence number set to 1. A1 is a DMS-converted frame for M1. A2 is a DMS-converted frame for M2. A5 is a DMS-converted frame for M3. A6 is a DMS-converted frame for M4. When DMS for STA is terminated by AP policy after receiving A6, STA does not discard M3 and M4 because DMS is not used. But, M3 and M4 are already received by DMS and they are duplicated frames to STA A. | When DMS is terminated, AP shall provide the Sequence Number of the last DMS-converted frame for discarding the duplicated multicast frames. | Declined | The scenarios described is a corner case. The additional complexity in the protocol is not warranted. The AP can prevent the scenario described by terminating DMS for a STA after the multicast frames have been transmitted. |  |  |  |  | Directed Multicast
104 | Y. Seok | 11.21.15 | 231 | 35-39 | T | Y | "The AP may decide to reject a new DMS or cancel a granted DMS at any time based on network condition, i.e. the number of associated STAs and channel load and so on." For the call admission control, AP may need TSPEC information element. To this end, non-AP STA should provide TSPEC information element in DMS Request information element. | non-AP STA should provide TSPEC information element in DMS Request information element. | Declined | Rejecting or Canceling a granted DMS will typically be based on network load. It is not necessary to use TSPEC information for a QoS related purpose. The STA can include the TCLAS element that is included in the DMS request frame in the ADDTS request frame to identify the converted unicast frame. |  |  |  |  | Directed Multicast
105 | Y. Seok | 7.3.2.46 | 43 | 59 | E | Y | HT Information element was changed to HT Operation element. | HT Information element was changed to HT Operation element. | Accepted |  |  | Done | D6.01
106 | Y. Seok | 7.3.2.68.5 | 68 | 12 | E | Y | In Table v16, bit 11 is not defined. | In Table v16, bit 11 is not defined. | Accepted | same as CID #31 |  | Done | D6.01
107 | Y. Seok | 7.3.2.68.5 | 68 | 17 | T | Y | TGz also provides two power save modes for tunneled direct link setup (TDLS), Peer-UAPSD and Peer PSM. Add TDLS power save modes into Table v16. | Add TDLS power save modes into Table v16. | Accepted | (1) P63L33 change the length of the Power Save Mode field from 2 to 4 octets (2) Insert the following entries in Table V16, using bits 14 anf 15, indicating bits 16-31 as reserved. TDLS Peer U-APSD (see 11.2.1.14) TDLS Peer PSM (see 11.2.1.13) |  |  |  |  | Diagnostics
108 | Y. Seok | 7.3.2.27 |  |  | T | Y | In Table 7-35a, non-AP STA shall set DMS field to 0 because supporting DMS is AP function. | In Table 7-35a, non-AP STA shall set DMS field to 0. | Declined | this field indicates where fthe capability of STA. | 109 |  |  |  | Directed Multicast
109 | Y. Seok | 7.3.2.27 |  |  | T | Y | In Table 7-35a, non-AP STA shall set FMS field to 0 because supporting FMS is AP function. | In Table 7-35a, non-AP STA shall set FMS field to 0. | Declined | this field indicates where fthe capability of STA. | 109 |  |  |  | Directed Multicast
110 | Y. Seok | 7.3.2.27 |  |  | T | Y | In Table 7-35a, non-AP STA shall set TFS field to 0 because supporting TFS is AP function. | In Table 7-35a, non-AP STA shall set TFS field to 0. | Declined | this field indicates where fthe capability of STA. | 109 |  |  |  | Directed Multicast
111 | Q. Wang | 7.3.1.18 | 15 | 65 | T | Y | "Rate identification field" is only included in the FMS subelement, so it's more appropriate to place the text within 7.3.2.75 where FMS subelement is specified. Also, please rename "rate" to "FMS rate" or the similar to clearly indicate its scope of applicability. | As in comment. | Declined | The rate identification field is a generic representation of rate introduced by the need to represent rates in 11n. It is intended to communicate a rate information as part of control or the management plane rather than replacing the rate information defined in the preamble of the packet. It is not specific to FMS. This will be usefull for other groups and features when they come to represent rates including 11n rates. |  |  |  |  | FMS
112 | Q. Wang | 7.3.2.21.8 | 20 | 4 | T | Y | "The peer MAC Address field is the RA or TA MAC address for the frame statistics of this measurement. If the peer MAC Address field is the wildcard address, then the value of the STA counters reported in the STA Statistics Report is the sum of the respective values for every peer of the reporting STA." How does a reporting STA know the statistics counter information of its every peer so that it can report the "sum"? Clarify and modify the text accordingly. | As in comment. | Counter | P20L4-9 delete "If the Peer MAC Address field is the wildcard address, then the value of the STA counters reported in the STA Statistics Report is the sum of the espective values for every peer of the reporting STA. For other MAC addresses in the Peer MAC Address field, the value of STA counters reported in the STA Statistics Report corresponds to frames where the RA or the TA matches the MAC address in the Peer MAC Address field" |  |  |  |  | STA Statistics
113 | Q. Wang | 7.3.2.27 | 35 | 23 | T | Y | "ES CIVIC Location". Civic location information may be useful for applications other than emergency service, so why name it "ES CIVIC location" to limit its scope of applicability? Make the name general. | As in comment. | Accepted | Change field name to "CIVIC Location" in all instances |  |  |  |  | Location
114 | Q. Wang | 7.3.2.27 | 35 | 27 | T | Y | "ES Geo Location". Geo location information may be useful for applications other than emergency service, so why name it "Geo CIVIC location" to limit its scope of applicability? Make the name general. | As in comment. | Accepted | Change field name to "Geo Location" in all instances |  |  |  |  | Location
115 | Q. Wang | 7.3.2.65 | 44 | 34 | T | Y | The meanings of "value=1" and "value=2" are the same and the only differences are how the format of representing the time offset at TSF=0. Why are the two (as opposed to one) formats needed? Merge the two into one. | As in comment. | Declined | Value 2 is the value of UTC at TSF=0. Value 1 is the value of UTC at a different point as defined in TGp draft. Although they represent UTC time they are based on different points in time when the value was determined. Some implementations may find it easier to implement Value 2 (TGu, TGv) whereas Value 1 (TGp) may be easier for those products. |  |  |  |  | Time Advertisement
116 | Q. Wang | 7.3.2.66.2 | 46 | 54 | T | Y | "Transition time" in Event Request subelement should be be renamed to "transition time threshold" here and everywhere else in the spec. | As in comment. | Accepted | (1) P46L53 In Table V3, entry order 3, change from "Transition Time" to "Transition Time Threshold" (2) P47L49, change from The Transition Time subelement is used to request that a Transition Event Report includes the transition event entry when the Transition Time is greater than or equal to the Transition Time Threshold. to The Transition Time Threshold subelement is used to request that a Transition Event Report includes the transition event entry when the Transition Time is greater than or equal to the Transition Time Threshold value." (3) P47L61, change the figure title from Figure v6—Transition Time subelement format to Figure v6—Transition Time Threshold subelement format (4)P47L65, change from The Subelement ID field is equal to the Transition Time value in Table v3. to The Subelement ID field is equal to the Transition Time Threshold value in Table v3. |  |  |  |  | Event
117 | Q. Wang | 7.3.2.66.2 | 47 | 49 | T | Y | "The Transition Time subelement is used to request that a Transition Event Report includes the transition event entry when the transition Time is greater than or equal to the Transition Time Threshold." What does a reporting STA include if the transition is not successful? Clarify and modify the text accordingly. | As in comment. | Counter | No change to the text is needed. See 11.21.2.2 page 213, L32-50 For transition logging and reporting purposes, the transition time is defined as the time difference between the starting time and the ending time of a transition between APs, even if the transition results in remaining on the same AP. |  |  |  |  | Event
118 | Q. Wang | 7.3.2.67.1 | 53 | 53 | T | Y | "The Event Time Value field is set the UTC value that corresponds to the UTC UT0 time when the TSF timer is equal to 0." The sentence is incorrectly. The Event Time Value field is set to the UTC value when the event took place, not the UTC value when the TSF=0. Modify the sentence. | As in comment. | Counter | Rename the "Event Time Value" field to be "UTC UT0 Offset" Changes required in table and description, P53L9, P53L47, P53L53, P53L54, and P211L20. |  |  |  |  | Event
119 | Q. Wang | 7.3.2.67.2 | 54 | 29 | T | Y | "The Transition Time field contains the transition time in Tus." How to set the Transition Time field when the transition is unsuccessful? Clarify and modify the text accordingly. | As in comment. | Accepted | Same as resolution to CID 117. |  |  |  |  | Event
120 | Q. Wang | 7.3.2.68.5 | 63 | 30 | T | Y | Rename "collocated radio" field to "collocated radio type" field and modify the related text accordingly. | As in comment. | Accepted | (1) P63, Figure V30, change from "Collocated Radio" to "Collocated Radio Type" (2) P63L38 Change from The Collocated Radio field contains a one octet field indicating the type of collocated radio, and is set to one of the values in Table v14. The method that a STA uses to obtain the information on the Collocated Radio is out of the scope of this standard. to The Collocated Radio Type subelement contains a one octet field indicating the type of collocated radio, and is set to one of the values in Table v14. The method that a STA uses to obtain the information on the Collocated Radio is out of the scope of this standard. (3)P64L1, change the title of the table from "Table v14—Collocated Radios" to "Table v14—Collocated Radio Type" (4) P64L4, change the table heading from "Collocated Radio" to "Collocated Radio Type" |  |  |  |  | Diagnostics
121 | Q. Wang | 7.3.2.68.5 | 64 | 36 | T | Y | Rename "device code" field to "device type" field and modify related text accordingly. | As in comment. | Accepted | (1) P64L36, change the field name from "Device Code" to "Device Type" (2) P64L44 and P64L46, change the table title and heading from "Device Code" to "Device Type" |  |  |  |  | Diagnostics
122 | Q. Wang | 11.1.2.3a | 195 | 35 | T | Y | "multiple BSSID " is now renamed to "multiple BSSID advertisement" in other parts of the spec, so "multiple BSSID procedures" need to be renamed to "multiple BSSID advertisement procedure" to be consistent. | As in comment. | Accepted | Rename "multiple BSSID procedures" to "multiple BSSID advertisement procedure" |  |  |  |  | Virtual AP
123 | Q. Wang | 11.1.2.3 | 195 | 25 | T | Y | Replace "When dot11MgmtOptionMultiBSSIDEnabled is set to true and the non-AP STA associated to the SSID corresponding to the non-transmitted BSSID,…" with "When dot11MgmtOptionMultiBSSIDEnabled is set to true and the non-AP STA associated to the non-transmitted BSSID,…". | As in comment. | Counter | Replace "When dot11MgmtOptionMultiBSSIDEnabled is set to true and the non-AP STA associated to the SSID corresponding to the non-transmitted BSSID,…" with "When dot11MgmtOptionMultiBSSIDEnabled is set to true and the non-AP STA associated to the BSS corresponding to the non-transmitted BSSID,…". |  |  |  |  | Virtual AP
124 | Q. Wang | 11.21.4.1 | 218 | 26 | T | Y | "The minimum Normal and In-Motion Report Interval in a Location Configuration Request frame is 500ms." My understanding is that the interval is not negotiated during the configuration process, so that the reporting always transmit using the interval specified in the Configuration Request frame. But, I couldn't find any explicit text on this. Add explicit text to make the requirement clear. | As in comment. | Counter | Insert after the following sentence "If all Location Parameter subelements included in the Location Configuration Request are successfully configured on the receiving STA, then the STA shall include in the Location Configuration Response frame a single Location Status subelement indicating success." "Upon successfull configuration, the receiving STA shall start transmitting the Location Track Notification frames based on the Location Configuration Request Frame parameters, as described in 11.21.4.2." |  |  |  |  | Location
125 | D. Engwer | 10.3.64.5 | 192 | 24 | E | Y | In X.210 nomenclature there is no ".termrequest" primitive type. | change MLME-DMS.termrequest to MLME-DMS-TERM.request | Accepted |  |  | Done | D6.01
126 | D. Engwer | 10.3.64.6 | 193 | 1 | E | Y | In X.210 nomenclature there is no ".termindication" primitive type. | change MLME-DMS.termindication to MLME-DMS-TERM.indication | Accepted |  |  | Done | D6.01
127 | D. Engwer | L.3 | 284 | 34 | E | Y | With the modifications to the sample code to support multiple BSSID encoding of the TIM, the formatting of the sample code is now inconsistent both with itself and the 802.11 style guideline for code. As a representative comparison point the 802.11v D6.0 Annex L sample code formatting is inconsistent with 802.11-2007. | As the author and formatter of the original Annex L sample code, the commenter offers to provide sample code that has been reformatted to conform to the guidelines and that is consistent throughout. This will be an editorial reformatting only. The reformatted sample code should also be verified by the originator of the 802.11v amendments to Annex L to ensure consistency with the normative text in clause 7.3.2.6 and clause 11. A revised version of the sample code will be made available at www.tinyurl.com/annex-l-tim6 | Counter | On TGv D6.0 P288, L11, change from "==" to "=" |  |  |  |  | Virtual AP
128 | D. Stephenson | 5.2.11.6 | 8 | 32 | T | N | The text states that "Diagnostic requests enable a STA to request a non-AP STA …". This is confusing. If an AP is only permitted to send a diagnostic request, then the first "STA" should be "AP". However, if any STA (i.e., either AP or non-AP STA) is permitted to request a diagnostic report, then "a non-AP STA" should be changed to "another STA" (or similar wording). | Clarify the text. | Declined | A Non-AP STA cannot request a diagnostic report from an AP STA. AN AP STA can request a report from a Non-AP STA. A STA in an IBSS can request a report from a peer STA. The current text, shown below is accurate: "Diagnostic requests enable a STA to request a non-AP STA to report on information that may be helpful in diagnosing and resolving problems with the WLAN network. Diagnostic reports include information on hardware, configuration, and STA capabilities" |  |  |  |  | Diagnostics
129 | D. Stephenson | 7.3.2.21 | 22 | 31 | E | N | Figure 7-29j appears to be an incorrect cross-reference. I can't find it in IEEE 802.11-2007, 802-11k-2008 or 802.11v-d6?? | Correct it. | Counter | change "Figure 7-29j" to "Table 7-29j". |  | Done | D6.01
130 | D. Stephenson | 7.3.2.31 | 37 | 42 | T | N | The phrase "when the protocol is TCP or UDP" is too restrictive and should be removed. I see no reason the TCLAS element should have such restrictions. Note that TCP and UDP are not the only protocols that use source and destination ports. See RFC-4960 and RFC-3828 as two examples that also use source and destination prots and are not TCP or UDP. | Remove the text. | Declined | Classifier type 1 is from the base spec, which supported only TCP and UDP, TGv makes no changes in this regard. The commenter is encouraged to submit this comment to the upcoming TGmb letter ballot. See also the resolution to CID 133; The TG believes that no additional text changes are needed. |  |  |  |  | TCLAS
131 | D. Stephenson | 7.3.2.31 | 37 | 64 | E | N | The text of the citation is "IETF RFC 791-1981". Note that this is inconsistent with the way RFCs are cited in the IEEE 802.11-2007 (e.g., see 802.11-2007 page 206 citation for IETF RFC 1321). The year of publication should be removed. There are many places in the TGv draft using this style which need to be corrected to match the baseline standard. | Fix the text. | Declined | The Year of publication appears in the IEEE 802.11-2007, see page 137IETF RFC 2474-1998. It is required to have year.
132 | D. Stephenson | 7.3.2.31 | 38 | 48 | T | N | The phrase "is either set to TCP or UDP" is too restrictive and should be removed. I see no reason the TCLAS element should have such restrictions. Note that TCP and UDP are not the only protocols that use source and destination ports. See RFC-4960 and RFC-3828 as two examples that also use source and destination prots and are not TCP or UDP. | Remove the text. | Declined | Same as resolution to CID 130 |  |  |  |  | TCLAS
133 | D. Stephenson | 7.3.2.31 | 39 | 2 | T | N | Classifier type 4 seems to be the same as classifer type 1. If so, it is redundant and should be deleted. If not, there should be some text explaining how they are different. | Fix the text. | Declined | Classifier type 1 is from the base spec, which supported only TCP and UDP; Classifier Type 4 is added to remove the restriction without risk of backward compatability issues. |  |  |  |  | TCLAS
134 | D. Stephenson | 7.3.2.31 | 39 | 9 | T | N | The equation for the length of the filter value and filter mask fields is incorrect. | Replace the 3 with 5. | Accepted | As in comment |  |  |  |  | TCLAS
135 | D. Stephenson | 7.3.2.66.2 | 47 | 25-29 | T | N | The text states "Excluding this subelement from the event request element indicates a request for transition events for all source BSSIDs. The format of the Transition Source BSSID subelement is shown in Figure v5." | A better method, which is in the style of the 802.11 standard, would be to include the source BSSID, but set its value to the wildcard BSSID when it's desired to request a transition event for all source BSSIDs. Note this same comment applies to the rest of this sub-clause. | Declined | The current encoding method is more efficient than that proposed by the commenter, saving 8 octets. |  |  |  |  | Event
136 | D. Stephenson | 7.3.2.66.3 | 50 | 64 | E | N | The foot note to IANA EAP types should be moved to clause 2--it is a normative reference. Note that EAP types URL is shown as a footnote in several places and all instances should be fixed. | Fix the text. | Accepted |  |  | Done | D6.01
137 | D. Stephenson | 7.3.2.66.5 | 51 | 26 | E | N | The word "link" is missing. | Change "… a TDLS or …" to "… a TDLS link or …" | Accepted |  |  | Done | D6.01
138 | D. Stephenson | 7.3.2.67.2 | 56 | 18 | T | N | It would be helpful to add 2 additional transition reasons as roaming from heterogenous systems will be common place in the future and it could be helpful for an 802.11 management system to have knowledge of this: 17 - Roam from cellular 18 - Roam from WiMax | Add the new transition reasons. | Counter | Note - page indicated by the commenter is incorrect; comment refers to page 55, not 56. Insert a new transition reason code in Table V7: Roam from a non-802.11 system, updating the reserved values accordingly. |  |  |  |  | Event
139 | D. Stephenson | 7.3.2.68.5 | 66 | 64 | T | N | The OUI field has been superseded by Organizational Identifier (see 802.11p-d6, clause 7.3.1.21). | Align with the 11p draft. | Counter | Same as resolution to CID 6 |  |  |  |  | Diagnostics
140 | D. Stephenson | 11.2.1.14.3 | 205 | 1 | T | N | The text should describe the interaction of this feature with the Listen Interval (cf IEEE 802.11-2007, clause 11.2.1.5 bullet k)). | Add the text. | Counter | Change bullet k in 11.2.1.5 as follows: An AP can delete buffered frames for implementation-dependent reasons, including the use of an aging function and availability of buffers. The AP may base the aging function on the listen interval specified by the non-AP STA in the (Re)Association Request frame or the WNM-Sleep Interval specified by the non-AP STA in the WNM-Sleep Mode Request frame. add a paragraph at the end of 11.2.1.14.1 WNM-Sleep mode capability: “WNM-Sleep Mode enables an extended power save mode for non-AP STAs in which a non-AP STA need not listen for every DTIM Beacon frame, and need not perform GTK/IGTK updates. The non-AP STA can sleep for extended periods as indicated by the WNM-Sleep Interval.” |  |  |  |  | Sleep Mode
141 | D. Stephenson | 11.20.15 | 231 | 65 | T | N | I'm not satisfied with the response to this comment from LB-146 (CID 294). The original comment was: "The text states that the classifier type must be 0 (ethernet parameters). This is a problem since up to 32 IP multicast addresses may be mapped to the same ethernet group address; thus this format does not uniquely define a multicast stream. Moreover, I can see no reason for this limitation. Why restrict the TCLAS parameters at all?" TGv declined the comment with the following response: "The intention of the DMS request is to specify which multicast traffic is requested for AP to transmit as unicast traffic. This multicast traffic is identified by DMSID, and the Destination Address of the multicast traffic is equal to the multicast address as specified in TCLAS element. The original proposal is to use a MAC Address field to describe the destination address of desired multicast traffic group. Since TGv uses TCLAS element in multiple places, we decided to use TCLAS to describe the destination address of desired multicast traffic group. This is why we have this restriction to make sure the Destination Address of the desired multicast traffic group is specified in the TCLAS element. Specifying the multicast address of the desired multicast traffic can allow the non-AP STA to filter out duplicated multicast traffic without deep packet inspection. " This is not responsive to my comment. For further explanation of mapping IP multicast addresses to MAC addresses, see: http://www.tcpipguide.com/free/t_TCPIPAddressResolutionForIPMulticastAddresses.htm. Having the restriction to only be able to classify by MAC address means that a single DMS request may map anywhere between 1 and 32 multicast streams to unicast and create much more traffic than intended by the requesting STA. DMS should not be designed to operate in this manner. | Modify the text so as not to restrict TCLAS parameters. | Counter | change "In the TCLAS element, the Classifier Type subfield shall be set to the value 0 (Ethernet parameters), the Classifier Mask subfield shall be set to the value 2, and the Destination Address subfield shall be set to the multicast address that the STA requests to receive as individually addressed frames." to "In the TCLAS element, the Classifier Type subfield shall be set to the value 0, 1, or 4, and the Destination Address or Destination IP Address subfield shall be set to the multicast address that the STA requests to receive as individually addressed frames.". |  |  |  |  | Directed Multicast
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070
1071
1072
1073
1074
1075
1076
1077
1078
1079
1080
1081
1082
1083
1084
1085
1086
1087
1088
1089
1090
1091
1092
1093
1094
1095
1096
1097
1098
1099
1100
1101
1102
1103
1104
1105
1106
1107
1108
1109
1110
1111
1112
1113
1114
1115
1116
1117
1118
1119
1120
1121
1122
1123
1124
1125
1126
1127
1128
1129
1130
1131
1132
1133
1134
1135
1136
1137
1138
1139
1140
1141
1142
1143
1144
1145
1146
1147
1148
1149
1150
1151
1152
1153
1154
1155
1156
1157
1158
1159
1160
1161
1162
1163
1164
1165
1166
1167
1168
1169
1170
1171
1172
1173
1174
1175
1176
1177
1178
1179
1180
1181
1182
1183
1184
1185
1186
1187
1188
1189
1190
1191
1192
1193
1194
1195
1196
1197
1198
1199
1200
1201
1202
1203
1204
1205
1206
1207
1208
1209
1210
1211
1212
1213
1214
1215
1216
1217
1218
1219
1220
1221
1222
1223
1224
1225
1226
1227
1228
1229
1230
1231
1232
1233
1234
1235
1236
1237
1238
1239
1240
1241
1242
1243
1244
1245
1246
1247
1248
1249
1250
1251
1252
1253
1254
1255
1256
1257
1258
1259
1260
1261
1262
1263
1264
1265
1266
1267
1268
1269
1270
1271
1272
1273
1274
1275
1276
1277
1278
1279
1280
1281
1282
1283
1284
1285
1286
1287
1288
1289
1290
1291
1292
1293
1294
1295
1296
1297
1298
1299
1300
1301
1302
1303
1304
1305
1306
1307
1308
1309
1310
1311
1312
1313
1314
1315
1316
1317
1318
1319
1320
1321
1322
1323
1324
1325
1326
1327
1328
1329
1330
1331
1332
1333
1334
1335
1336
1337
1338
1339
1340
1341
1342
1343
1344
1345
1346
1347
1348
1349
1350
1351
1352
1353
1354
1355
1356
1357
1358
1359
1360
1361
1362
1363
1364
1365
1366
1367
1368
1369
1370
1371
1372
1373
1374
1375
1376
1377
1378
1379
1380
1381
1382
1383
1384
1385
1386
1387
1388
1389
1390
1391
1392
1393
1394
1395
1396
1397
1398
1399
1400
1401
1402
1403
1404
1405
1406
1407
1408
1409
1410
1411
1412
1413
1414
1415
1416
1417
1418
1419
1420
1421
1422
1423
1424
1425
1426
1427
1428
1429
1430
1431
1432
1433
1434
1435
1436
1437
1438
1439
1440
1441
1442
1443
1444
1445
1446
1447
1448
1449
1450
1451
1452
1453
1454
1455
1456
1457
1458
1459
1460
1461
1462
1463
1464
1465
1466
1467
1468
1469
1470
1471
1472
1473
1474
1475
1476
1477
1478
1479
1480
1481
1482
1483
1484
1485
1486
1487
1488
1489
1490
1491
1492
1493
1494
1495
1496
1497
1498
1499
1500
1501
1502
1503
1504
1505
1506
1507
1508
1509
1510
1511
1512
1513
1514
1515
1516
1517
1518
1519
1520
1521
1522
1523
1524
1525
1526
1527
1528
1529
1530
1531
1532
1533
1534
1535
1536
1537
1538
1539
1540
1541
1542
1543
1544
1545
1546
1547
1548
1549
1550
1551
1552
1553
1554
1555
1556
1557
1558
1559
1560
1561
1562
1563
1564
1565
1566
1567
1568
1569
1570
1571
1572
1573
1574
1575
1576
1577
1578
1579
1580
1581
1582
1583
1584
1585
1586
1587
1588
1589
1590
1591
1592
1593
1594
1595
1596
1597
1598
1599
1600
1601
1602
1603
1604
1605
1606
1607
1608
1609
1610
1611
1612
1613
1614
1615
1616
1617
1618
1619
1620
1621
1622
1623
1624
1625
1626
1627
1628
1629
1630
1631
1632
1633
1634
1635
1636
1637
1638
1639
1640
1641
1642
1643
1644
1645
1646
1647
1648
1649
1650
Note on L1: This must be a comment number - without text
Note on K1: Describe how the group or individual came to the resolution status.
Note on J1: Resolution to Comment Accepted - Tech Comm - means voted on by the group - Ed. Comm - means the comment was approved Declined - Tech Comm - means voted on by the group - Ed. Comm - means the comment was declined by the group Counter - Tech Comm - means voted on by the group - Ed. Comm - means the comment was countered by the group Deferred - deferred needs group approval
Note on I1: Do not edit this column. It is copied exactly from the submission worksheet.
Note on H1: Do not edit this column. It is copied exactly from the submission worksheet.
Note on G1: Do not edit this column. It copied exactly from the submission worksheet. Part of No Vote Yes - means it was part of "no" vote No - means it was not part of "no" vote
Note on F1: Do not edit this column. It copied exactly from the submission worksheet.
Note on E1: Do not edit this column. It is copied exactly from the submission worksheet.
Note on D1: Do not edit this column. It is copied exactly from the submission worksheet.
Note on C1: This column can be modified to strip out conflicting clauses
Note on P1: Should be broken down by clause or clauses
Note on Q1: Enter document # or Will of the Group
Note on T1: Record LB 78 Comment # if required
Note on S1: Pull down to identify at which meeting the comment was addressed
Note on R1: Record (xls) when it is the comments were resolved in (xls) w/o (doc)

## OverView
Category (Include all technical and select editorial comments) | Total | Accepted | Declined | Counter | Deferred | Blank | Work Remaining | Editor To Do | Editor Done | Category Owner | Notes
General | 3 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | Dorothy Stanley
Event | 8 | 2 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | Joe Kwak
Diagnostics | 6 | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | Dorothy Stanley
Multicast Diagnostics | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Alex Ashley
STA Statistics | 6 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | Ganesh Venkatesan
FMS | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Allan Thomson
Location | 26 | 4 | 6 | 16 | 0 | 0 | 0 | 0 | 0 | Allan Thomson
Timing Measurement | 11 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | Ganesh Venkatesan
Roaming Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Emily Qi
Extended Channel Switch | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TG
Virtual AP | 5 | 1 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | Qi Wang
TFS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Emily Qi
Sleep Mode | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Emily Qi
TIM Broadcast | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Menzo Wentink
Collocated Interference | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Jing Zhu
Annex | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Stephen McCann
QOS Traffic Capability | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fujio Watanabe
Directed Multicast | 7 | 1 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | Emily Qi
Proxy ARP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Dorothy Stanley
Channel Usage | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Emily Qi
Time Advertisement | 12 | 1 | 5 | 6 | 0 | 0 | 0 | 0 | 0 | Allan Thomson
TCLAS | 4 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | TG
Total | 94 | 25 | 27 | 42 | 0 | 0 | 0 | 0 | 0
Comment Break Down | Count |  |  |  | Assignee | Total | Open |  | Color | Comments Remaining
Total | 140 |  |  |  |  | 0 | 0
Technical | 93 |  |  |  |  | 0 | 0
Editorial | 47 |  |  |  |  | 0 | 0
Accepted | 65 |  |  |  |  | 0 | 0
Counter | 46 |  |  |  |  | 0 | 0
Declined | 29 |  |  |  |  | 0 | 0
Deferred | 0 |  |  |  |  | 0 | 0
Duplicates | 30 |  |  |  |  | 0 | 0
Editor To Do | 0 |  |  |  |  | 0 | 0
Can't do | 0 |  |  |  |  | 0 | 0
Editor Done | 42 |  |  |  |  | 0 | 0
Blank | 0 |  |  |  | Total: | 0 | 0
Precentage
Editor Done
30%
Process to following when merging xxx comments
Copy columns A-G starting at Row number 9 through all populated rows
Do not copy rows, but just cells desired
Paste into master spreadsheet
Place pointer in Column C on the proper row (row 2 for first paste)
Navigate to Edit->Paste Special "text"
This will preserve the formatting, conditional coloring, etc.
Update the "Revisions" worksheet
Record the submitter and total comments
Update the "Author" column
Update the "Date" column
Save file as next revision
Process to follow when updating master spreadsheet
Filter/Sort on "New Column" and change everything to "No"
As modifications are made to each row
Update the "Resolution Document" column if necessary
Update the "New" column
Update the "Addressed At" if the comment was resolved
Update the "Title" worksheet updating the revision number of the document
Update the "Revisions" worksheet
Record the exact meeting
Register each comment addressed
Update the "Author" column
Update the "Date" column
Save file as next revision

## Revisions
Rev Number | Meeting | Comments Addressed and/or Notes | Author | Date | To Do: | Draft Version
0 |  | This is a new & mostly un-edited first version of a compilation of all comments received by the Task Group v Chair during the WG LB150 review period. | Dorothy Stanley | 2009-06-15
1 |  | Implemented editorial comments and ANA. Fixed clause number, Figure number and Table number. | Emily Qi | 2009-07-07

## References
References:

## LB Voters
Voter | LB140 | LB146 | LB150 | Remaining "no" comments
Aboulmagd, Osama S | Y | Y | Y | None
Adachi, Tomoko | A | A | A | n/a
Aggarwal, Alok | Y | Y | Y | None
Aldana, Carlos H | N | N | N | LB140 comments
Alexander, Thomas | Y | Y | Y | None
Armstrong, Lee R | Y | Y | Y | None
Ashley, Alex | Y | Y | Y | None
Audeh, Malik | Y | Y | Y | None
Awater, Geert A | Y | Y | Y | None
Bagby, David | A | N | N | LB146 comment(1), CID 2
Bahr, Michael | Y | Y | Y | None
Bai, Fan | Y | A | A | n/a
Bajko, Gabor | N | N | N | LB150 comments
Baker, Dennis J | M | M | M | n/a
Bansal, Amit | A | A | A | n/a
Barr, John R. | Y | Y | Y | None
Basson, Gal | Y | Y | Y | None
Bavafa, Moussa | N | N | Y | None
Baykas, Tuncer | Y | Y | Y | None
Benko, John L | Y | Y | Y | None
Benveniste, Mathilde | E | Y | Y | None
Bjerke, Bjorn A | Y | Y | Y | None
Borges, Daniel | Y | Y | Y | None
Braskich, Anthony | Y | Y | Y | None
Brennan, Joseph | A | A | A | n/a
Britz, David | M | M | M | n/a
Bumiller, George | N | N | Y | None
Cam-Winget, Nancy | Y | Y | Y | None
Canpolat, Necati | N | N | Y | None
Cardona, Javier | Y | Y | Y | None
Chan, Douglas S | Y | Y | Y | None
Chaplin, Clint F | N | N | N | LB150 comments
Chen, Lidong | A | A | A | n/a
Cheong, Minho | Y | Y | Y | None
Cho, Woong | Y | Y | Y | None
Choi, Nakjung | Y | Y | Y | None
Chu, Liwen | N | N | N | LB150 comments
Cole, Terry L | M | M | M | n/a
Coleman, Ryon K | M | M | M | n/a
Cook, Charles I | Y | Y | Y | None
Cooklev, Todor | Y | Y | Y | None
Costa, Xavier Perez | Y | Y | Y | None
Cypher, David E | A | A | A | n/a
De Courville, Marc | Y | Y | Y | None
de Vegt, Rolf J | Y | Y | Y | None
Denteneer, Theodorus | Y | Y | Y | None
deVries, Jeremy | A | A | A | n/a
Dickey, Susan | A | A | A | n/a
DING, ZHIMING | M | M | M | n/a
Doi, Yoshiharu | Y | Y | Y | None
Dorsey, John | N | N | N | LB146 comments
Durand, Roger P | N | N | Y | None
duvvuri, srinivasa | Y | Y | Y | None
Eastlake, 3rd, Donald E. | Y | Y | Y | None
Ecclesine, Peter | Y | Y | Y | None
Ellis, Michael | Y | Y | Y | None
Emeott, Stephen P | Y | Y | Y | None
Emmelmann, Marc | Y | Y | Y | None
Engwer, Darwin | N | N | N | LB150 comments
Epstein, Joseph | N | N | N | LB140 comments
Erceg, Vinko | N | N | N | LB146 comments
Falk, Lars P | Y | Y | Y | None
Fanfelle, Robert | A | Y | Y | None
Fechtel, Stefan | Y | Y | Y | None
Feinberg, Paul H. | M | M | M | n/a
Fischer, Matthew J | N | N | N | LB140 comments
Fisher, Wayne K | Y | Y | Y | None
Fracchia, Roberta | M | M | M | n/a
Funada, Ryuhei | M | M | M | n/a
Gast, Matthew | N | N | Y | None
Gilb, James P K | Y | Y | Y | None
Gilbert, Jeffrey | Y | Y | Y | None
Gloger, Reinhard | Y | Y | Y | None
Goodall, David | Y | Y | Y | None
Guener, Tugrul | M | M | M | n/a
Guo, Jianlin | A | A | A | n/a
Hamilton, Mark | Y | N | N | LB150 comments
Hansen, C J | N | Y | Y | None
Hart, Brian D | Y | Y | Y | None
Hassan, Amer A | Y | Y | Y | None
Hassel, Vegard | Y | Y | Y | None
Heile, Robert F | M | M | M | n/a
Hiertz, Guido R. | Y | Y | Y | None
Hu, Junling | M | M | M | n/a
hu, wendong | A | A | A | n/a
Huang, Robert Y | Y | Y | Y | None
Hunter, David | M | Y | Y | None
Inoue, Yasuhiko | M | M | M | n/a
Iso, Akio | Y | Y | Y | None
Jee, Junghoon | Y | Y | Y | None
Jeon, Hongseok | Y | Y | Y | None
Jeong, Yeonkwon | A | A | A | n/a
Jetcheva, Jorjeta G | Y | Y | Y | None
Ji, Lusheng | N | N | N | LB140 Comment(1), CID 142
Jiang, Daniel | Y | Y | Y | None
Kafle, Padam | Y | Y | Y | None
Kain, Carl W | A | A | A | n/a
Kakani, Naveen K | Y | Y | Y | None
Kato, Masato | Y | Y | Y | None
Kavner, Douglas | Y | Y | Y | None
Kennedy, Richard H | M | Y | Y | None
Kenney, John | A | A | A | n/a
Kerry, Stuart J | Y | Y | Y | None
Kim, Joonsuk | A | A | A | n/a
Kim, Kyeongpyo | Y | Y | Y | None
kim, Seong Soo | M | M | M | n/a
Kim, Yongsun | Y | Y | Y | None
KNECKT, JARKKO | M | M | M | n/a
KOBAYASHI, MARK M | N | A | A | n/a
Kojima, Fumihide | Y | Y | Y | None
Kolze, Tom | M | M | M | n/a
Kraemer, Bruce P | Y | Y | Y | None
Kruys, Johannes P | Y | Y | Y | None
Kuehnel, Thomas | Y | Y | Y | None
Kurihara, Thomas M | Y | Y | Y | None
Kwak, Joseph | N | N | Y | None
KWON, EDWIN | A | A | A | n/a
Lan, Zhou | Y | A | A | n/a
Landt, Jeremy A | Y | Y | Y | None
Lauer, Joseph P | N | N | Y | None
Lee, Tae Hoon | A | A | A | n/a
Lee, Wooyong | Y | Y | Y | None
Levy, Joseph | Y | Y | Y | None
Li, Sheung | Y | Y | Y | None
Lin, Paul | M | M | M | n/a
Liu, Hang | Y | Y | Y | None
Livshitz, Michael | A | A | A | n/a
Loc, Peter | Y | Y | Y | None
Lubar, Daniel | Y | Y | Y | None
Maida, Anthony F | M | M | M | n/a
Majkowski, Jakub | Y | Y | Y | None
Malarky, Alastair | N | N | Y | None
Malinen, Jouni K | N | Y | Y | None
Maltsev, Alexander | Y | Y | Y | None
Marshall, Bill | N | N | N | LB140 comments(8) CIDs 107 through 114
Maslennikov, Roman M | Y | Y | Y | None
MATTA, SUDHEER | Y | Y | Y | None
Mccann, Stephen | N | N | Y | None
Mcnew, Justin P | Y | Y | Y | None
Mesecke, Sven | Y | Y | Y | None
Miller, Robert R | N | N | N | LB140 comment(1), CID 99
Montemurro, Michael | N | N | Y | None
Moorti, Rajendra T | A | A | A | n/a
Morioka, Hitoshi | Y | Y | Y | None
Murray, Peter | Y | Y | Y | None
Myles, Andrew | Y | Y | Y | None
Nabar, Rohit | Y | Y | Y | None
Nagai, Yukimasa | Y | Y | Y | None
nagata, kengo | Y | Y | Y | None
Ngo, Chiu | Y | Y | Y | None
Nikula, Eero | Y | Y | Y | None
Noens, Richard H | Y | Y | Y | None
Odagiri, Hideaki | A | A | A | n/a
Oh, Jisung | A | A | A | n/a
Olson, Chandra S | Y | Y | Y | None
Omori, Youko | A | A | A | n/a
Oyama, Satoshi | Y | Y | Y | None
Paine, Richard H | Y | Y | Y | None
PALANIVELU, Arul Durai Murugan | Y | Y | Y | None
Park, Changmin | Y | Y | Y | None
Park, Jungsoo | M | M | M | n/a
Park, Minyoung | Y | Y | Y | None
Patel, Vijaykumar | Y | Y | Y | None
Peiris, Bemini Hennadige | Y | Y | Y | None
Perahia, Eldad | Y | Y | Y | None
Petranovich, James E | Y | Y | Y | None
petrick, Albert | Y | Y | Y | None
Pirzada, Fahd | Y | Y | Y | None
Portaro, James D | Y | Y | Y | None
Ptasinski, Henry S | N | N | N | LB146 comments
Purnadi, Rene | N | A | A | n/a
Qi, Emily H | Y | Y | Y | None
Qian, Luke | Y | Y | Y | None
Qu, Huyu | Y | Y | Y | None
Raab, Jim E | Y | Y | Y | None
Rai, Vinuth | A | A | A | n/a
Raissinia, Ali | N | N | Y | None
Ramamurthy, Harish | Y | Y | Y | None
Rayment, Stephen G | A | A | A | n/a
Razoumov, Leonid | M | M | M | n/a
Reede, Ivan | Y | Y | Y | None
Reuss, Edward | Y | Y | Y | None
Reznik, Alex | Y | Y | Y | None
Roebuck, Randal | Y | Y | Y | None
Rosdahl, Jon W | M | M | M | n/a
Roy, Richard | N | N | N | LB146 comments
Safonov, Alexander | A | Y | Y | None
Sakoda, Kazuyuki | A | Y | Y | None
Sampath, Hemanth | Y | A | A | n/a
SATO, KATSUYOSHI | Y | Y | Y | None
Sawada, Hirokazu | Y | Y | Y | None
Schultz, Donald | Y | Y | Y | None
Seok, Yongho | N | N | Y | None
Shao, Huairong | Y | Y | Y | None
Sharma, Neeraj | A | A | A | n/a
Shellhammer, Stephen J | M | M | M | n/a
Sherlock, Ian | Y | Y | Y | None
Shi, Kai | A | A | A | n/a
Shimada, Shusaku | Y | Y | Y | None
Simon, Francois | Y | Y | Y | None
Singh, Harkirat | Y | Y | Y | None
Smith, Graham Kenneth | N | N | N | LB146 comments
Smith, Matt | Y | Y | Y | None
Song, Yoo-Seung | Y | Y | Y | None
Sood, Kapil | N | Y | Y | None
Sridhara, Vinay | Y | Y | Y | None
Stanley, Dorothy | Y | Y | Y | None
Stephens, Adrian P | Y | Y | Y | None
Stephenson, David S | Y | Y | Y | None
Stevenson, Carl R. | M | M | M | n/a
Stine, John | A | A | A | n/a
STRUTT, GUENAEL T | Y | Y | Y | None
Sum, Chin-Sean | A | A | A | n/a
Takagi, Eiji | Y | Y | Y | None
Takai, Mineo | Y | Y | Y | None
Tan, Teik-Kheong | Y | Y | Y | None
THOMSON, ALLAN | Y | Y | Y | None
Thrasher, Jerry | A | A | A | n/a
Tokubo, Eric | Y | Y | Y | None
Tolpin, Alexander | M | M | M | n/a
Trachewsky, Jason | N | A | A | n/a
Trainin, Solomon B. | Y | Y | Y | None
Van Nee, Richard D.J. | Y | Y | Y | None
Van Zelst, Allert | Y | Y | Y | None
Varlet-Andre, Mathieu | Y | Y | Y | None
Varshney, Prabodh | Y | Y | Y | None
Venkatesan, Ganesh | Y | Y | Y | None
Victor, Dalton T | A | A | A | n/a
Vlantis, George A | A | N | N | LB150 comments
Walker, Jesse R | Y | Y | Y | None
Wang, Junyi | A | A | A | n/a
Wang, Qi | N | N | N | LB150 comments
Warren, Craig D | A | A | A | n/a
Watanabe, Fujio | Y | Y | Y | None
waye, patrick | Y | Y | Y | None
Wentink, Menzo M | Y | Y | Y | None
Whetten, Frank | A | A | A | n/a
Williams, Kyle | A | A | A | n/a
Woo, Pyo Chang | M | M | M | n/a
Worsham, James | N | Y | Y | None
Worstell, Harry R | N | N | N | LB140 comment (1), CID 9
Xia, Pengfei | M | M | M | n/a
Yamada, Akira | Y | Y | Y | None
Yamamoto, Takeshi | Y | Y | Y | None
Yamaura, Tomoya | A | A | A | n/a
Yee, Peter | A | A | A | n/a
Yong, Su Khiong | Y | Y | Y | None
Yoshida, Seiji | Y | Y | Y | None
Young, Christopher | A | A | A | n/a
Zaks, Artur | Y | Y | Y | None
Zhang, Hongyuan | M | M | M | n/a
zhang, huimin | Y | Y | Y | None
Zhu, Jing | Y | Y | Y | None
Zuniga, Juan | Y | Y | Y | None