## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-09/0927r2
Venue Date: | September 2009
First Author: | Wayne Fisher, ARINC, Inc.
Subject: | LB154-TGp-Comment Resolution Master
Full Date: | 2009-09-22
Author(s): | Wayne Fisher, Lee Armstrong
ARINC, Inc
2551 Riva Road, Annapolis, MD 21401
Phone: 410-266-4958
Fax: 410-573-3170
email: wfisher@arinc.com
Abstract:
The spreadsheet contains the combined comment submissions from LB154. Rev 0: 8/10/09. Initial Spreadsheet Rev 1: 8/20/09. Spreadsheet updated with comments withdrawn. Rev 2: 9/22/09. Spreadsheet updated with comments withdrawn and 15 comments addressed.
Notice: This document has been prepared to assist IEEE 802.11. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein. Release: The contributor grants a free, irrevocable license to the IEEE to incorporate material contained in this contribution, and any modifications thereof, in the creation of an IEEE Standards publication; to copyright in the IEEE’s name any IEEE Standards publication even though it may include portions of this contribution; and at the IEEE’s sole discretion to permit others to reproduce in whole or in part the resulting IEEE Standards publication. The contributor also acknowledges and accepts that this contribution may be made public by IEEE 802.11. Patent Policy and Procedures: The contributor is familiar with the IEEE 802 Patent Policy and Procedures <http:// ieee802.org/guides/bylaws/sb-bylaws.pdf>, including the statement "IEEE standards may include the known use of patent(s), including patent applications, provided the IEEE receives assurance from the patent holder or applicant with respect to patents essential for compliance with both mandatory and optional portions of the standard." Early disclosure to the Working Group of patent information that might be relevant to the standard is essential to reduce the possibility for delays in the development process and increase the likelihood that the draft publication will be approved for publication. Please notify the Chair <stuart@ok-brit.com> as early as possible, in written or electronic form, if patented technology (or technology under patent application) might be incorporated into a draft standard being developed within the IEEE 802.11 Working Group. If you have questions, contact the IEEE Patent Committee Administrator at <patcom@ieee.org>.

## Master
ID | Commenter | Clause | Pg | Ln | Type | Comment | Suggested Remedy | Resolution | Comment Resolution | Same As | Editor Status | Editor Notes | Assigned To | Category | Resolution Document | Addressed AT | XLS Refer. | New Change (this Ver)
6 | Wang, Qi | 7.2.3.14 | 5 | 39 | TR | What is the format for reporting "Timestamp" in the Timing Advertisement frame in terms of the length of the field and the units used? If the intention is to use the same format as the timestamp field used in the beacons, please state so, and/or provide a clause reference. | As in comment. | Declined | Declined. This comment is out of scope for this ballot as it does not relate to changed material or material effects by changed material or a previous unsatisfied comment. The comment will be submitted by the TGp chair during the sponsor ballot. |  |  |  | McNew | Clause 7. | 09-0988r3 | Hawaii |  | Yes
15 | Chaplin, Clint | 9.9.1.2 | 10 | 25 | E | "Insert the following text at the end the second paragraph of 9.9.1.2 after NOTE 3:" missing "of" | "Insert the following text at the end of the second paragraph of 9.9.1.2 after NOTE 3:" | Declined | Declined. TGp declines to consider this comment at this time. The comment will be submitted by the TGp chair during the sponsor ballot. |  |  |  | McNew | Clause 9. | 09-0988r3 | Hawaii |  | Yes
18 | Wang, Qi | 11.1 | 17 | 47 | TR | "A STA for which dot11OCBEnabled is true is not a member of a BSS, and is not required to synchronize to a common clock or use these mechanisms." This sentence disallows the use of a TSF timer at a TGp STA, since TSF timer is one of the mechanisms defined in 11.1. However, this contradicts to the statement in 11.21.1 (pg18, Line34) that "According to 11.1.2. each STA maintains a TSF Timer for synchronization purpose.". Modify the text to be consistent. | As in comment. | Declined | Declined. The use of a TSF timer is not precluded by this statement. |  |  |  | McNew | Clause 11. | 09-0988r3 | Hawaii |  | Yes
20 | Chaplin, Clint | 11.3 | 17 | 53 | TR | The added footnote is changing normative behavior, and thus cannot be a footnote. | Change the footnote into an in-line statement | Declined | Declined. TGp declines to consider this comment at this time. The comment will be submitted by the TGp chair during the sponsor ballot. |  |  |  | McNew | Clause 11. | 09-0988r3 | Hawaii |  | Yes
21 | Stephens, Adrian | 11.3 | 18 | 7 | T | The inserted footnote contains information that should be presented in body text. Also, authentication and assocition variables define a state that is used in filtering frames. What classes are frames when OCBEnabled is true? How are they filtered? | Remove footnote. Replace "A STA" at P18L1 with "A STA in which dot11OCBEnabled is true". Add note after it: "NOTE--For operation of a STA in which dot11OCBEnabled is true, see 11.20". | Declined | Declined. TGp declines to consider this comment at this time. The comment will be submitted by the TGp chair during the sponsor ballot. |  |  |  | McNew | Clause 11. | 09-0988r3 | Hawaii |  | Yes
22 | Chaplin, Clint | 11.20 | 18 | 18 | E | "subtype Action and Timing Advertisement" | "subtypes Action and Timing Advertisement" | Declined | Declined. TGp declines to consider this comment at this time. The comment will be submitted by the TGp chair during the sponsor ballot. The comment will be submitted by the TGp chair during the sponsor ballot. |  |  |  | McNew | Clause 11. | 09-0988r3 | Hawaii |  | Yes
23 | Stephens, Adrian | 11.20 | 18 | 18 | T | 11.3 also deals with frame classification. This is not used with OCBEnabled. | Add "classification" to the list after "association". | Declined | Declined. TGp declines to consider this comment at this time. The comment will be submitted by the TGp chair during the sponsor ballot. |  |  |  | McNew | Clause 11. | 09-0988r3 | Hawaii |  | Yes
24 | Wang, Qi | 11.21.1 | 18 | 34 | TR | "According to 11.1.2. each STA maintains a TSF Timer for synchronization purpose." Since TGp devices don't operate in a BSS, the TSF timer here represents a local time and is different from the TSF value advertised by the beacon in an infrastructure BSS. Please provide an accurate description for what the TSF timer represents. | As in comment. | Declined | Declined. The TSF timer in this case does not represent a local time, but, when corrected by values in the Time Advertisement IE, the result is a local time. See the third paragraph of 7.3.2.65. The comment will be submitted by the TGp chair during the sponsor ballot. |  |  |  | McNew | Clause 11. | 09-0988r3 | Hawaii |  | Yes
25 | Wang, Qi | 11.21.1 | 19 | 1 | TR | "…. The receiving STA's SME can use the Timestamp, Local Time, and Time Advertisement information element to align its estimate of the time standard to the transmitting STA's estimate of the corresponding time standard." Is the flight time ignored? Please clarify. | As in comment. | Declined | Declined. Whether or not the flight time is included in the corrections is an implementation issue. |  |  |  | McNew | Clause 11. | 09-0988r3 | Hawaii |  | Yes
26 | Cypher, David | A.4.3 | 21 | 18 | E | CF2.1 and PC37 are the same. Why? I know that you are not following any authoritative standard on the construction of PICS proformas, so it is hard to guess why you are duplicating items. | Change in A.4.4.1, PC37 status column from "O" to "CF18:O" | Declined | Declined. TGp declines to consider this comment at this time. The comment will be submitted by the TGp chair during the sponsor ballot. |  |  |  | Roebuck | Annex A | 09-1023 | Hawaii |  | Yes
27 | Cypher, David | A.4.3 | 21 | 18 | E | CF2.1 and PC37 are the same. Why? I know that you are not following any authoritative standard on the construction of PICS proformas, so it is hard to guess why you are duplicating items. | Change in A.4.4.1, PC37 status column from "O" to "CF18:O" | Declined | Declined. TGp declines to consider this comment at this time. The comment will be submitted by the TGp chair during the sponsor ballot. |  |  |  | Roebuck | Annex A | 09-1023 | Hawaii |  | Yes
36 | Cypher, David | Annex D | 26 | 42 | TR | Instruction on line 40 states "Insert dot11TempType2", while on line 42 the name is "dot11TempType" not dot11TempType2. Besides dot11TempType was deprecated in the previous instruction on line 20. This was correct in Draft 7, but now changed in Draft 8. There was no associated comment in the last comment resolution to indicate this change. | Change "dot11TempType" to "dot11TempType2" by inserting a number, 2. | Declined | Declined. TGp declines to consider this comment at this time. The comment will be submitted by the TGp chair during the sponsor ballot. The technical editor made a typographical error: it was correct in the previous draft; there was no comment associated with this text; and no intention to change it. |  |  |  | McNew | Annex D | 09-0988r3 | Hawaii |  | Yes
37 | Cypher, David | Annex D | 26 | 42 | T | Instruction on line 40 states "Insert dot11TempType2", while on line 42 the name is "dot11TempType" not dot11TempType2. Besides dot11TempType was deprecated in the previous instruction on line 20. | Change "dot11TempType" to "dot11TempType2" by inserting a number, 2. | Declined | Declined. TGp declines to consider this comment at this time. The comment will be submitted by the TGp chair during the sponsor ballot. The technical editor made a typographical error: it was correct in the previous draft; there was no comment associated with this text; and no intention to change it. |  |  |  | McNew | Annex D | 09-0988r3 | Hawaii |  | Yes
38 | Stephens, Adrian | Annex I.1 | 28 | 34 | T | ITS is not in the abbreviations | Add ITS to abbreviations. | Declined | Declined. Following the style of Table I.1 in the IEEE 802.11-2007 baseline, acronyms for the various regulatory agencies and standards bodies (FCC, CFR, ETSI, MIC, etc.) are defined when first used and then reused in the subsequent Tables I.2 and I.3. They are not defined in Clause 4. Also see http://wireless.fcc.gov/services/index.htm ?job=service_home&id=intelligent_ts. In addition, this section has previous passed WG letter ballot without comment. |  |  |  | Landt | Annex I | 11-09-0939r2 | Hawaii |  | Yes
39 | Stephens, Adrian | Annex J | 32 | 27 | TR | "Within the same Regulatory Class, the channels in use in any location shall be non-overlapping." While I believe this is necessary, this is a normative requirement that is "distributed" across multiple entities. The "in any location" is ill-defined. This single sentence does not relieve TGp of defining processes and requirements on an individual STA that enables it to meet the goals of this statement. Otherwise, this statement will remain a statement of good intent, not actuality. Same comment in Table J.2. | Define rules and processes that demonstrably enable a TGp device to meet the intend of this statement. For example, it could be required to perform some kind of period scan to build a map of used channels and widths and required select a channel that partly overlaps a used channel. | Declined | Declined. The rules and procedures for a STA to satisfy the requirements of the footnote are outside the scope of 802.11. Channel selection when dot11OCBEnabled is true is not performed using MAC services. As stated in subclause 5.2 : "A STA for which dot11OCBEnabled is true initially transmits and receives on a channel known in advance, either through regulatory designation or some other out-of-band communication. A STA's SME determines PHY layer parameters, as well as any changes in operating channel, e.g., using information obtained via out-of-band communication or over-the-air frame exchange". The STA performs no scanning, and by regulation, the only means for a STA to change channel is via such information. Therefore, like authentication, such rules and procedures apply to the station management entity (SME) or to applications outside of the MAC sublayers. |  |  |  | Malarky | Annex J | 11-09-0939r2 | Hawaii |  | Yes
Note on K1: This must be a comment number - without text
Note on J1: Describe how the group or individual came to the resolution status.
Note on I1: Resolution to Comment Accepted - Tech Comm - means voted on by the group - Ed. Comm - means the comment was approved Declined - Tech Comm - means voted on by the group - Ed. Comm - means the comment was declined by the group Counter - Tech Comm - means voted on by the group - Ed. Comm - means the comment was countered by the group Deferred - deferred needs group approval
Note on H1: Do not edit this column. It is copied exactly from the submission worksheet.
Note on G1: Do not edit this column. It is copied exactly from the submission worksheet.
Note on F1: Do not edit this column. It copied exactly from the submission worksheet. Part of No Vote Yes - means it was part of "no" vote No - means it was not part of "no" vote
Note on E1: Do not edit this column. It is copied exactly from the submission worksheet.
Note on D1: Do not edit this column. It is copied exactly from the submission worksheet.
Note on C1: This column can be modified to strip out conflicting clauses
Note on O1: Should be broken down by clause or clauses
Note on P1: Enter document # or Will of the Group
Note on Q1: This column represents the meetinng which the comment was resolved, but not voted on.
Note on R1: Record (xls) when it is the comments were resolved in (xls) w/o (doc)

## OverView
Category | Total | Accepted | Declined | Counter | Deferred | Blank | Work Remaining | Editor To Do | Editor Done | Category Owner | Notes | Status
Clause 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Armstrong | General / Admin | Open
Reference | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fisher | References, Errors | Open
General | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Armstrong | General / Document | Open
Clause 1. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Armstrong | Overview | Open
Clause 3. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Armstrong | Definitions | Open
Clause 4. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Armstrong | Abbrs & Acronyms | Open
Clause 5. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Kenney | General Description | Open
Clause 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Kavner | MAC service definition | Open
Clause 7. | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | McNew | Frame formats | In-Proc
Clause 9. | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | McNew | MAC sublayer functional | Open
Clause 10. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | McNew | Layer management | Open
Clause 11. | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | McNew | MLME | In-Proc
Clause 17. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Kain | OFDM PHY specification | Open
Annex A | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Roebuck | PICS proforma | In-Proc
Annex D | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Roebuck | ASN.1 encoding of the MAC and PHY MIB | In-Proc
Annex I | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Landt | Regulatory classes | In-Proc
Annex J | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Malarky | Country information element and regulatory classes | In-Proc
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Open
Editorial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fisher | General Editorial | Open
Total: | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0
Comment Break Down | Count |  |  |  | Assignee | Total | Open |  | Color | Comments Remaining
Total | 15 |  |  |  | Armstrong | 0 | 0 |  | 0 | 0 - comments remaining - done
Editorial | 4 |  |  |  | Fisher | 0 | 0 |  | 0 | 5 or fewer comments remaining
Editorial-Required | 0 |  | Precentage |  | Kenney | 0 | 0 |  | 0 | 6 - 10 comment remaining
Technical | 4 |  | Complete |  | Kavner | 0 | 0 |  | 0 | 11-25 comments remaining
Technical-Required | 7 |  | 100% |  | McNew | 9 | 0 |  | 0 | 25 or more comments remaining
Accepted | 0 |  |  |  |  | 0 | 0 |  | 0 | Not started
Counter | 0 |  | Remaining |  |  | 0 | 0 |  | 0 | Total
Declined | 15 |  | same as |  | Kain | 0 | 0
Deferred | 0 |  | 0 |  | Roebuck | 4 | 0
Duplicates | 0 |  | #DIV/0! |  | Landt | 1 | 0
Editor To Do | 0 |  |  |  | Malarky | 1 | 0
Editor Done | 0 |  |  |  |  | 0 | 0
Blank | 1 |  |  |  |  | 0 | 0
[5 empty] | Total: | 15 | 0
Process to following when merging LB comments
Copy columns A-G from LB (.xls) starting at Row number 9 through all populated rows
Do not copy rows, but just cells desired
Paste into master spreadsheet
Place pointer in Column C on the proper row (row 2 for first paste)
Navigate to Edit->Paste Special "text"
This will preserve the formatting, conditional coloring, etc.
Update the "Revisions" worksheet
Record the submitter and total comments
Update the "Author" column
Update the "Date" column
Save file as next revision
Process to follow when updating master spreadsheet
Filter/Sort on "New Column" and change everything to "No"
As modifications are made to each row
Update the "Resolution Document" column if necessary
Update the "New" column
Update the "Addressed At" if the comment was resolved
Update the "Title" worksheet updating the revision number of the document
Update the "Revisions" worksheet
Record the exact meeting
Register each comment addressed
Update the "Author" column
Update the "Date" column
Save file as next revision
Note on D30: # of work remaining comments (blank or deferred) that have somethinng in the "same as" column
Note on L1: Notes about the categories, this field is only for documentation.
Note on A1: These categories shall match the category column on the master spreadsheet
Note on A36: You will need to plug in the total row number, I did not take the time to figure out the proper calc.

## Revisions
Rev Number | Meeting | Comments Addressed and/or Notes | Author | Date | To do: | Draft Version
0 | San Francisco | Initial Comment Resolution Spreadsheet | Wayne Fisher | 8/10/09 | - | D8.0
1 | Telcon1 | The following comments have been withdrawn: 2, 3, 4, 5, 7, 8, 9, 16, 17, 19, 28, 29, 30, 31, 32, 34, 35 | Wayne Fisher | 8/20/09 | Update Master Worksheet | D8.0
2 | Telcon1 | The following comments have been withdrawn: 12 and 33. The following comments have been addressed: 6, 10, 11, 13, 14, 15, 18, 21, 22, 23, 24, 25, 38, and 39 | Wayne Fisher | 9/15/09 | Update Master Worksheet | D8.0
3 | Hawaii | The following comments have been withdrawn: 10, 11, 13, 14. The following comments have been addressed: 6, 15, 18, 20 -27, and 36 - 39. | Wayne Fisher | 9/22/09 | Update Master Worksheet | D8.0
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## References
References: