## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-10/0223r0
Venue Date: | February 2010
First Author: | Kazuyuki Sakoda (Sony Corporation)
Subject: | MAC beaconing sync comment resolution xls
Full Date: | 2010-02-17
Author(s): | Kazuyuki Sakoda
Sony Corporation
5-1-12 Kitashinagawa, Shinagawa-ku, Tokyo, Japan
81-3-5448-4018
KazuyukiA.Sakoda(at)jp.sony.com
Abstract:
Proposed resolutions to M-BS category open comments. .

## Comments
CID | Submitter | Original Clause | Orig Page No. | Orig Line No. | Orig Comment Type | Part of No Vote? | Topic Category | Page | Line | Type | Clause | Major Clause | Issue Ident. | Duplicate of CID | Resolution Status | Asignee | Submission | TGs Approval Date | Comment / Explanation | Recommended Change | Resolution Code | Resolution Notes | Updated (to assist editor) | Edit Status | Edit Notes | Edited in Draft | Closed by:
2718 | Sakoda, Kazuyuki | 11C.12.4.2 | 215 | 8 | E | N | MAC | 215 | 8 | E | 11C.12.4.2 | 11C.12 Synchronization and beaconing in MBSSs | M-BS |  | Open | Kaz |  |  | The sentence starting with "The Beacon Timing element may be contained ..." is vague. | Provide more accurate information when it is present. Especially when present in Probe Response frame is not provided. | Counter | BT element condition: The text has been modified to be clear on this. See the latest version of the submission 11-10/222. | 11-10/222
2009 | Bahr, Michael | 10.3.77.1.4 | 124 | 37-39 | T | N | MAC | 124 | 37-39 | T | 10.3.77.1.4 | 10.3 MLME SAP interface | M-BS |  | Open | Kaz |  |  | The Beacon Timing element can only hold beacon information of dot11MeshBeaconTimingReportMaxNum neighbors, and a maximum of 51 due to the length restriction of IEs. How is the case of (dot11MeshBeaconTimingReportMaxNum+n) and 52 or more neighbors handled? | Extend description of construction of TBTT Adjustment Request frame accordingly. | Counter | BT element limit: The text has been modified to be clear on this issue. Partial report method is introduced, and multiple BT elements will be contained in the Probe Response and TBTT Adjustment Request frame. See the latest version of the submission 11-10/222. | 11-10/222
2032 | Bahr, Michael | 11C.12.4.2 | 215 | 2010-08-11 | T | N | MAC | 215 | 8-11 | T | 11C.12.4.2 | 11C.12 Synchronization and beaconing in MBSSs | M-BS |  | Open | Kaz |  |  | The Beacon Timing Report Enabled subfield in the Mesh Capability field of the Mesh Configuration element is superfluous here. If a mesh STA is capable of including the Beacon Timing element in its Beacon or Probe Response, the recipient will see this. It does not need a redundant information in the Mesh Capability field in order to include the Beacon Timing IE. | Delete sentence "The mesh STA that is capable of this beacon timing report procedures shall set Beacon Timing Report Enabled subfield in the Mesh Capability field of the Mesh Configuration element to 1." Remove Beacon Timing Report Enabled subfield from Mesh Capability field. | Counter | Control bits in Mesh Config IE: The control bits in the Mesh Capability field has been consolidated. See the latest version of the submission 11-10/222. | 11-10/222
2049 | Bahr, Michael | 11C.12.4.3 | 215-216 | 37-33 | T | N | MAC | 215-216 | 37-33 | T | 11C.12.4.3 | 11C.12 Synchronization and beaconing in MBSSs | M-BS |  | Open | Kaz |  |  | There is confusion with TBTT selection and TSF adjustments and corresponding bits in Mesh Capability field. The text describes the conditions for the selection of the TBTT and the procedure for adjusting the TSF. | Review the procedures for TBTT selection and TSF adjustment thoroughly and remove any unnecessary control bits from the mesh capability field. | Counter | Control bits in Mesh Config IE: The control bits in the Mesh Capability field has been consolidated. See the latest version of the submission 11-10/222. | 11-10/222
2519 | Ramamurthy, Harish | 10.3.2.2.2 | 115 | 62 | T | N | MAC | 115 | 62 | T | 10.3.2.2.2 | 10.3 MLME SAP interface | M-BS |  | Open | Kaz |  |  | Add Beacon Timing report element in BSS description if dot11MeshTbttSelectionActivated is true. This will be useful while starting/joining MBSS. | A proposal can be submitted if required |  | Missing element. Will be resolved by 11-10/136. (Beacon Timing element is included in the BSS description as suggested.) | 136r0
2521 | Ramamurthy, Harish | 10.3.78.1.2 | 126 | 11 | T | N | MAC | 126 | 11 | T | 10.3.78.1.2 | 10.3 MLME SAP interface | M-BS |  | Open | Kaz |  |  | MLME-STARTBEACONING can be merged with MLME-START with small changes. This will save lots of redundant text and will make it more consistent for BSS, IBSS and MBSS | A proposal can be submitted if required |  | MLME-STARTBEACONING: will be resolved by 11-10135 | 135r0
2522 | Ramamurthy, Harish | 10.3.78.2 | 127 | 47 | T | N | MAC | 127 | 47 | T | 10.3.78.2 | 10.3 MLME SAP interface | M-BS |  | Open | Kaz |  |  | MLME-MeshNieghborOffsetMeasure Should be MLME-STARTBEACONNING | As suggested in the comment. |  | MLME-STARTBEACONING: will be resolved by 11-10135 | 135r0
2638 | Sakoda, Kazuyuki | 10.3.78 | 126 | 1 | E | N | MAC | 126 | 1 | E | 10.3.78 | 10.3 MLME SAP interface | M-BS |  | Open | Kaz |  |  | The primitive title "Start Beaconing" is vague and could be confusing. | Replace "Start Beaconing" with "Start Mesh Beaconing". And replace "STARTBEACONING" with "STARTMESHBEACONING". |  | MLME-STARTBEACONING: will be resolved by 11-10135 | 135r0
2050 | Bahr, Michael | 11C.12 | 212-216 | 55-33 | T | N | MAC | 212-216 | 55-33 | T | 11C.12 | 11C.12 Synchronization and beaconing in MBSSs | M-BS |  | Open | Kaz |  |  | The neighbor offset protocol and the beaconing procedures for mesh BSS contain interesting ideas, but the written text shows clearly, that these procedures are not really thought through into all the necessary details, and more importantly, the relationship between these procedures are not considered. Right now, they are described independently from each other. The relationship between Neighbor Offset Synchronization Protocol, Mesh Beacon Collision Avoidance mechanism and the MCCA mechanism have to be considered and according rules have to be specified. Some things are not fully specified, for instance, what happens, if a Beacon Timing Report IE does not contain all neighbors? Certain mechanisms will not work then (e.g. Detection of reception of own Beacon). | Review clause 11C.12 and all other clauses related to this clause with respect to the following aspects: - relation between neighbor offset protocol, mesh beacon avoidance mechanism, MCCA mechanism - full and consitent specification of all mechanisms, especially neighbor offset protocol and mesh beacon avoidance mechanism - editorial improvements - remove unnecessary or redundant elements (e.g. bit in Mesh Capability field) Related clauses are, for instance, 7.4.18.8 TBTT Adjustment Request frame format, 10.3.77 MLME-Mesh TBTT Adjustment, 7.3.2.95.8 Mesh Capability, A.4 PICS proforma - IEEE Std 802.11, 2007, Annex D (normative) ASN.1 encoding of the MAC and PHY MIB, X.3 Design rationale of MBCA, 7.3.2.102 Beacon Timing element | Counter | The synchronization protocol, related frames, layer management, etc, has been carefully reviewed again to satisfy the commenter's concern. See revised text in the latest version of the submission 11-10/222. | 11-10/222
2258 | Bahr, Michael | 11C.12 | 212-216 | 55-33 | T | N | MAC | 212-216 | 55-33 | T | 11C.12 | 11C.12 Synchronization and beaconing in MBSSs | M-BS |  | Open | Kaz |  |  | The Synchronization and Beaconing in an MBSS are a rather basic and important mechanisms (the former only for certain functionalities), and very much care has to be taken for their specification. Although the specification of Synchronization and Beaconing improved considerably compared to D3.0, there are still little errors in it. Moreover, it might be the case that some new problems have been introduced by some comment resolutions. Furthermore, it is known that in certain dynamic situations and interactions with other mechanisms in the mesh, especially between Neighbor Offset Protocol, Beaconing, Mesh Beacon Collision Avoidance, MCF Coordinated Channel Access, and Power Save, something might not function correctly. Furthermore, the interoperation between the related mechanisms has to be checked. | Check the synchronization and beaconing description and specification for the MBSS case thoroughly for correctness, completeness, right numbers and terminology, and consistency. Especially, check all possible state that can occur during operation. Pay special attention to the interaction between Neighbor Offset Protocol, Beaconing, Mesh Beacon Collision Avoidance, MCF Coordinated Channel Access, and Power Save. Furthermore, check the references. | Counter | The synchronization protocol, related frames, layer management, etc, has been carefully reviewed again to satisfy the commenter's concern. See revised text in the latest version of the submission 11-10/222. | 11-10/222
2715 | Sakoda, Kazuyuki | 11C.12.2.2.2 | 214 | 23 | E | N | MAC | 214 | 23 | E | 11C.12.2.2.2 | 11C.12 Synchronization and beaconing in MBSSs | M-BS |  | Open | Kaz |  |  | The lettered bullet c) is somewhat vague. | Refine the text. | Counter | Wordsmith. The text has been modified to be clear on this. See the latest version of the submission 11-10/222. | 11-10/222
2741 | Stephens, Adrian | 11C.12.2.2.2 | 214 | 23 | T | N | MAC | 214 | 23 | T | 11C.12.2.2.2 | 11C.12 Synchronization and beaconing in MBSSs | M-BS |  | Open | Kaz |  |  | "When the mesh STA sees one of its neighbor’s TSF is delaying due to the clock drift" Presumably the STA has an eye-glass trained on clock-tower of the the STA and declares "ahoy, me hearties, you're running slow today". Or perhaps I've misunderstood. | Relate to observed on-the-air signalling. | Counter | Wordsmith. The text has been modified to be clear on this. See the latest version of the submission 11-10/222. | 11-10/222
2014 | Bahr, Michael | 11C.12.2.2.1 | 213 | 59 | E | N | MAC | 213 | 59 | E | 11C.12.2.2.1 | 11C.12 Synchronization and beaconing in MBSSs | M-BS |  | Open | Kaz |  |  | The neighbor mesh STA's TSF timer value is not translated, it is actually the neighbor mesh STA's TSF timer value. The own TSF timer value will be translated. | remove "Translated". You might want to add text that this is the neighbor mesh STA's TSF timer the corresponding mesh STA thinks it is. | Counter | The text has been modified to be clear on this. See the latest version of the submission 11-10/222. | 11-10/222
2721 | Sakoda, Kazuyuki | 11C.12.4.3 | 216 | 8 | E | N | MAC | 216 | 8 | E | 11C.12.4.3 | 11C.12 Synchronization and beaconing in MBSSs | M-BS |  | Open | Kaz |  |  | The lettered bullet b) is somewhat vague. Collision occurs for Beacon frames not TBTT (same logic apply to bullet c)). And what if the MAC address is unknown for neighbor's neighbor. | As in comment. | Counter | The text has been modified to be clear on this. See the latest version of the submission 11-10/222. | 11-10/222

## Issue Ids
Issue IDs are used to identify groups of CIDs that are related to the same issue
MAC |  |  | total | closed | open | assignee | resolved | remaining
| M-BS | Beaconing and Synchronization | 14 | 0 | 14 | Kaz | 10 | 4

## Rev. History
Revisision | Date | Notes / Summary of Changes
r0 | 2010-02-17 | initial revision
r1
r2
r3
r4