## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-10/0478r1
Venue Date: | April 2010
First Author: | Kazuyuki Sakoda (Sony Corporation)
Subject: | LB 161 Comment Resolutions
Full Date: | 2010-04-22
Author(s): | Kazuyuki Sakoda
Sony Corporation
5-1-12 Kitashinagawa, Shinagawa-ku, Tokyo, Japan
81-3-5448-4018
KazuyukiA.Sakoda@jp.sony.com
Abstract:
This is a cummulation of the comments submitted by voters for IEEE 802.11 LB 161 on P802.11s Draft D5.0 with resolutions so far.

## Comments
CID | Submitter | Submitter Affiliation | Original Clause | Orig Page No. | Orig Line No. | Orig Comment Type | Part of No Vote? | Page | Line | Type | Clause | Topic Category | Issue Ident. | Duplicate of CID | Asignee | Submission | TGs Approval Date | Resolution Status | Comment / Explanation | Recommended Change | Resolution Code | Resolution Notes | Updated (to assist editor) | Edit Status | Edit Notes | Edited in Draft | Closed by:
3194 | Sakoda, Kazuyuki | Sony Corporation | 7.3.2.96.7 | 44 | 21 | E | N | 44 | 21 | E | 7.3.2.96.7 | Security | S-Editorial |  |  |  |  | Open | "... the type of authentication protocol..." should read "... the type of mesh peering protocol...". | As in comment. | Accept | resolved with 11-10/0632 | x
3221 | Sakoda, Kazuyuki | Sony Corporation | 8.4.1.1.1 | 101 | 8 | E | N | 101 | 8 | E | 8.4.1.1.1 | Security | S-Editorial |  |  |  |  | Open | "Authenticator, or peer, MAC address" should read "Authenticator's or peer's MAC address | As in comment. | Accept | resolved with 11-10/0632 | x
3236 | Sakoda, Kazuyuki | Sony Corporation | 11C.5 | 192 | 1 | E | N | 192 | 1 | E | 11C.5 | Security | S-Editorial |  |  |  |  | Open | The title of subclause under 11C.5 contains unnecessary capitalization. For instence, 11C.5.2 "Security Capabilities Selection" should read "Security capabilities selection". It is necessary to apply these lower/upper case corrections. | As commented. Apply the same change in 11C.6. | Accept | resolved with 11-10/0632 | x
3019 | Bahr, Michael | Siemens AG | 7.4.14 | 67-72 | 7-42 | T | N | 67-72 | 7-42 | T | 7.4.14 | Security | S-Frame |  |  |  |  | Open | There is some mismatch between the "security level" of Action frames and the category of action frames. Self Protected is defined as a category in 7.4.14, but it is in fact a "security level" that would be between Public Action frames and Robust Action frames. So, the new functionality related to self protection should be defined where Public Action frames and Robust Action frames are defined, so that there is that new level of Self Protected Action frames. The category of the action frames in clause 7.4.14 should reflect the application space, that is, Mesh Peering. | make the specification of self-protection similar to Public and Robust action frames. Rename category to Mesh Peering. I will try to make a strong enough case that a self-protected action frame is a new security level. | Reject | discussed this and a submission is needed to possibly rename the category of "self-protected" to something else. However this is not essential at this stage of the draft. | x
3059 | Chaplin, Clint | Samsung Electronics | 8.2 | 84 | 15 | T | Y | 84 | 15 | T | 8.2 | Security | S-General |  |  |  |  | Open | "Open System Authentication and Deauthentication shall not be used between mesh STAs." Ambiguous | "Open System Authentication and Open System Deauthentication shall not be used between mesh STAs." | Accept | resolved with 11-10/0632 | x
3121 | Harkins, Dan | Aruba Networks | 11C.5.5.2 | 195 | 15-27 | T | Y | 195 | 15-27 | T | 11C.5.5.2 | Security | S-General |  |  |  |  | Open | The only thing the RSN IE is being used for is ciphersuite selection and that can be handled by the AMPE IE. Just turn the "selected pairwise cipher suite field" into a list, add a count, and add a "group cipher suite field". The RSN IE has a whole bunch of other cruft that is not being used or defined or referenced here. What happens, for instance, if the PMKID in the RSN IE does not match the "Chosen PMK field"? Or should the PMKID in the RSNIE be zero'd out? What about the AKM? Should it be SAE? What if it isn't but the "Chosen PMK field" indicates a PMK created by SAE? Or should the AKM be zero'd out? | get rid of the RSN IE from AMPE. | Reject | this was discussed and a submission is required to retain the functionality the RSNIE provides without using the RSNIE. Since this is not critical at this stage of the draft the comment is rejected in anticipation of it being remade during the next balloting. | x
3154 | Purnadi, Rene | Research In Motion | 5.4.3.1 | 12 | 35 | T | Y | 12 | 35 | T | 5.4.3.1 | Security | S-General |  |  |  |  | Open | Pre-shared password is between two mesh STA or among mesh STAs with the same mesh-ID? How the pre-shared password distributed? | Please clarify or just say 'beyond the scope of this specification' | Counter | mention of distribution being out-of-scope will be made in the definiton of a password in clause 3 (similar to that done for PSK). Resolved with 11-10/0632. | x
3161 | Purnadi, Rene | Research In Motion | 8.5.1.5.1 | 106 | 16 | T | Y | 106 | 16 | T | 8.5.1.5.1 | Security | S-General |  |  |  |  | Open | Should the PMK shows as MPMK in figure 8.22a | Please clarify | Accept
3162 | Purnadi, Rene | Research In Motion | 8.5.1.5.3 | 107 | 9 | T | Y | 107 | 9 | T | 8.5.1.5.3 | Security | S-General |  |  |  |  | Open | Should the PMK be called MPMK? | Please clarify | Accept | resolved with 11-10/0632 | x
3185 | Sakoda, Kazuyuki | Sony Corporation | 5.2.13.5.3 | 9 | 38 | T | N | 9 | 38 | T | 5.2.13.5.3 | Security | S-General |  |  |  |  | Open | TGs draft D5.0 does not define any means to use AS (Authentication Server) that provides the authorization upon successful authentication. | Discuss if it is a reasonable way to go. | Reject | using an AS can be secure but it is difficult and complicated. This clause specifies that a PMK between mesh STAs is needed but does not specify how that PMK is obtained. It could be from an AS which is beyond the scope of this standard. | x
3214 | Sakoda, Kazuyuki | Sony Corporation | 8.2a | 84 | 23 | T | N | 84 | 23 | T | 8.2a | Security | S-General |  |  |  |  | Open | While SAE is an exciting new mutual authentication method offering many technical advantage, it is not a proven technology yet. Hence, it should be safe for TGs to define a backup option for the safety measure. Consider to reuse an exisiting mechnanism such as one defined in IEEE1363-2 (also ratified as ISO/IEC11770-4) for the backup (define as an option for the mutual authentication). ISO/IEC11770-4 Key Agreement Mechanism 1 assumes the peer-to-peer model which can fit with mesh authentication scenario using a shared password. | Discuss to define a backup method. | Reject | It is a good idea to have a backup but there is no clear candidate to become the backup. | x

## Issue Ids
Issue IDs are used to identify groups of CIDs that are related to the same issue
General |  |  | total | closed | open | assignee | resolved | remaining
| G-Base | Unification with base standard. | 0 | 0 | 0 |  | 0 | 0
| G-Def | Terminology | 0 | 0 | 0 |  | 0 | 0
| G-Discovery |  | 0 | 0 | 0 |  | 0 | 0
| G-Editor | Editorial fixes (wording, typo fixing, etc) | 0 | 0 | 0 |  | 0 | 0
| G-Frame | General Frame Format | 0 | 0 | 0 |  | 0 | 0
| G-General |  | 0 | 0 | 0 |  | 0 | 0
| G-Architecture | Mesh architecture and MBSS concept | 0 | 0 | 0 |  | 0 | 0
| G-Emergency | Emergency services | 0 | 0 | 0 |  | 0 | 0
| G-MIB |  | 0 | 0 | 0 |  | 0 | 0
| G-PICS |  | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0
MAC
| M-BS | Beaconing and Synchronization | 0 | 0 | 0 |  | 0 | 0
| M-CC | Congestion Control | 0 | 0 | 0 |  | 0 | 0
| M-CS | Channel Selection | 0 | 0 | 0 |  | 0 | 0
| M-General |  | 0 | 0 | 0 |  | 0 | 0
| M-MCCA | MCCA | 0 | 0 | 0 |  | 0 | 0
| M-PM | Power Management | 0 | 0 | 0 |  | 0 | 0
| M-QoS | QoS related issues | 0 | 0 | 0 |  | 0 | 0
| M-11n | 11n compatibility | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0
RFI
| R-LM | Link Metric | 0 | 0 | 0 |  | 0 | 0
| R-Frame | Frame Format | 0 | 0 | 0 |  | 0 | 0
| R-FWD | Forwarding | 0 | 0 | 0 |  | 0 | 0
| R-General |  | 0 | 0 | 0 |  | 0 | 0
| R-HWMP |  | 0 | 0 | 0 |  | 0 | 0
| R-MeshGate |  | 0 | 0 | 0 |  | 0 | 0
| R-Proxy |  | 0 | 0 | 0 |  | 0 | 0
| R-PU | Proxy Update | 0 | 0 | 0 |  | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0
Security
| S-General |  | 7 | 0 | 7 |  | 7 | 0
| S-Editorial |  | 3 | 0 | 3 |  | 3 | 0
| S-Frame | Frame Format | 1 | 0 | 1 |  | 1 | 0
| S-E2E | Need end-to-end security? | 0 | 0 | 0 |  | 0 | 0
| S-PLM | Peer Link Management | 0 | 0 | 0 |  | 0 | 0
| S-SAE | SAE | 0 | 0 | 0 |  | 0 | 0
|  |  | 11 | 0 | 11 |  | 11 | 0

## Statistics
Statistics
| Overall Summary | Total | Open | Closed | % Closed
| Total Comments: | 11 | 11 | 0 | 0%
| Editorial Comments: | 3 | 3 | 0 | 0%
| Technical Comments: | 8 | 8 | 0 | 0%
| Total Comments: | 11 | 11 | 0 | 0%
| General | 0 | 0 | 0 | #DIV/0!
| MAC | 0 | 0 | 0 | #DIV/0!
| RFI | 0 | 0 | 0 | #DIV/0!
| Security | 11 | 11 | 0 | 0%

## Saved Statistics
Saved Statistics

## Instr. for Subteams
Instructions for editing of this spreadsheet by comment resolution subteams
1 | Do not change any of columns A-G, R-T, or Y-AA.
2 | Insert a unique value identifier (i.e. "RFI-Waikoloa-1") in column X (Updated Resolution) for any row edited
3 | Only use the following values in column V (Resolution):
Accept
Reject
Counter
Defer
Blank
4 | When identifying comments related to the same issue, list unique issue identifiers in the "Issue Identifiers" worksheet..
Use these lables in column M. Issue Identifierss should start with G, M, R, or S.
5 | Do not use AutoSort when pasting multiple fields from one spreadsheet to another!!!!
6 | If an issue identifier is changed, then insert "XFER" in column X (Updated Resolution) for any row edited in this fashion.

## Schema
Description of Fields used on the Comments Tab
Field | Description
CID | Comment identifier. This is a unique integer that identifies a comment whereever the need to cross-reference occurs. There is no significance to the actual values or ordering of values in this field.
Submitter | The name of the commenter
Orig Clause | The clause number indicated by the commenter
Orig Page No. | The page number indicated by the commenter
Orig Line No. | The line number indicated by the commenter
Orig Type | The type of comment indicated by the commenter
Part of No Vote | Whether the comment forms part of the commenter's "No" vote
Topic Category | Topic category of the comment MAC -- MAC-related comments, e.g. MCCA, congestion control, power save, beaconing, etc. Security -- Security-related comments, e.g. SAE, peer link establishment, etc. RFI -- Routing/Interworking/Forwarding-related comments, e.g. HWMP, Forwarding, Airtime metric, etc. General -- All comments not covered by the other categories
Issue Identifier | Identifier for comments that are related to a particular issue. Issue Identifiers should start with M, S, R, or G depending on the issues Topic Category.
Duplicate of CID | A non-blank value indicates that the comment is an exact match in the clause, comment and recommended change fields with the referenced comment.
Resolution Status | Status of the comment (Open or Closed)
Assignee | If non-blank, the person identified by this column has agreed to bring a submission to TGs in resolution of the comment.
Submission | If non-blank, identifies a document submission brought in resolution of the comment.
TGs Approval Date | Date of TGs motion approving resolution.
Comment | The comment made by the commenter. Minor fixups may be made to remove embedded objects.
Proposed Change by Commenter | The proposed change made by the commenter. Minor fixups may be made to remove embedded objects.
Resolution | The resolution for the comment (Accept, Reject, Counter, Defer, Transfer) If the Comment Status is Closed, this is the resolution that was officially adopted by TGs. If the Comment Status is Open, this is a suggest resolution (e.g. proposed at an ad-hoc) that needs to be voted on by TGs.
Resolution Notes | Notes providing more detail on the resolution.
Edit Status | Done -- resolution has been implemented in the draft To Be Done -- to be implemented in a future draft revision -- no additional action required by TG Needs Rework -- insufficient detail provided for editor to implement in the draft. TG needs to rework this CID.
Color Codes | Yellow - Closed but not implemented in draft revision Green - Closed and implemented Orange - Comment was updated but not voted on in last session.

## Rev. History
Revisision | Date | Notes / Summary of Changes
r0 | 2010-04-21 | Compilation of comments gathered through LB161. Preliminary Topic Category and Issue Identifier are put in column M and column N of "Comments" sheet.
r1 | 2010-04-22 | Suggested resolutions marked with "20100422G-Editor" in column X of "Comments" sheet are incorporated. Some of the Topic Category and Issue Identifier are changed.