## Slide 1: IEEE 802.11ah Timeline Projection
Date: 2013-3-20
Authors:

## Slide 2: History
May 2012 – Move out 2 months
November 2012 – Suggest move out internal task group letter ballot and enlarging time between letter ballot to sponsor ballot.
March 2013 – Internal LB not starting in March 2013 since draft text not finished. Timeline needs to be reviewed.

## Slide 3: Abstract
IEEE 802.11ah timeline. This document gets updated as milestones are met.

## Slide 4: Current projected IEEE 802.11ah timeline
Internal Task Group Ballot : March 2013
Initial Letter Ballot : July 2013
Initial Sponsor Ballot : Jan. 2015
EC Approval : November 2015
Revcom Approval : Jan. 2016

## Slide 5: Discussion for March 2013
Draft text not available yet. Internal LB not happening in March.
Do we want to,
  Try to avoid slipping end date
  Make slight slip of date
  Move dates out significantly

## Slide 6: Try to avoid end date slip discussion Start WG LB in July
Draft text arrives before May face to face meeting
Review draft text in conference call(s) prior to May face to face
Internal TG LB starts in May
  Comments and resolution happen in parallel in May
Finish addressing Internal TG LB comments in July
Start WG LB in July

## Slide 7: Make slight date slip discussion Start WG LB in September
Draft text arrives in May face to face meeting
Internal TG LB starts in May
Start WG LB in September

## Slide 8: Move dates out significantly discussion Start WG LB in ?
Draft text arrives in May
Several rounds of review needed before WG LB

## Slide 9: Suggested update to IEEE 802.11ah timeline
Try to avoid end date slip