## Slide 1: March 802.19 Liaison Report
Date: 2012-03-14
Authors:

## Slide 2: Abstract
March 802.19 liaison report

## Slide 3: 802.19 March Meeting Plan
WG officer elections
802.19.1

## Slide 4: 802.19.1 Agenda
Identify missing parts in the draft
Review of the new draft by the editor
Vote to accept new draft as official draft of the TG1.
Recruit volunteers to bring the text for missing parts
Discuss and vote on text contributions
Incorporation of new text to the draft
Discuss to forward the draft to WG for letter ballot

## Slide 5: 802.19.1 Timeline
 | 2010 |  |  |  |  |  | 2011 |  |  |  |  |  | 2012 |  |  |  |  |  | 2013 |  |  |  |  | 
 | 1 | 3 | 5 | 7 | 9 | 11 | 1 | 3 | 5 | 7 | 9 | 11 | 1 | 3 | 5 | 7 | 9 | 11 | 1 | 3 | 5 | 7 | 9 | 11
Task Group formed | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
System Design Document completed |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Call for Proposals issued |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Contribution presentations with straw polls |  |  | x | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Proposal presentations |  |  |  |  | x | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Round of votes on proposals in clause order |  |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Create candidate draft document |  |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Comment ballot on the candidate draft |  |  |  |  |  |  |  |  |  | x | x | x | x |  |  |  |  |  |  |  |  |  |  | 
Comment resolutions on the candidate draft |  |  |  |  |  |  |  |  |  |  | x | x | x | x |  |  |  |  |  |  |  |  |  | 
Adoption of draft normative text |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Letter ballot Comment Resolution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Recirculation Ballot |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Comment Resolution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 6: References
https://mentor.ieee.org/802.19/dcn/12/19-12-0038-01-0001-802-19-tg-1-march-session-opening-report.ppt
https://mentor.ieee.org/802.19/dcn/12/19-12-0035-00-0000-march-2012-opening-report.ppt