## Slide 1: 802.11REVmc Editor’s Report – July 2016
Date: 2016-07-08
Authors:

## Slide 2: Acknowledgement
The following people have kindly aided the technical editor in one way or another during the development of REVmc:
  Dorothy Stanley, Jon Rosdahl, Mark Hamilton, Mark Rison, Peter Ecclesine, Mike Montemurro, Liwen Chu, Eldad Perahia, Brian Hart, Sai Shankar, James {Yee|Wang|P.K. Gilb}, Assaf Kasher, Carlos Cordeiro, Edward Au, Kaberi Banerjee, Rich Kennedy, Yongho Seok, Carlos Aldana, Gabor Bajko, Scott Marin, Graham Smith, Sigurd Schelstraete, Emily Qi
And a big thank you to Edward Au and Emily Qi, who are the sub-editors

## Slide 3: Status of Draft

## Slide 4: Reference Documents
Draft: P802.11REVmc D6.0 (members’ area)
WG & Sponsor Ballot composite comments
  11-15/0532 – currently R47
    SB0 is shown as “LB1000”, comments start at CID 5001
    SB1 is shown as “LB1001”, comments start at CID 7001
    SB2 is shown as “LB1002”, comments start at CID 8001
    Includes pre-ballot comments
MAC comment resolutions
  11-15/0565
GEN comment resolutions
  11-15/0665
MAC/GEN sheets usually used for motioning tech resolutions.
  Composite SS may lag contents of these sheets during a session, but is the eventual resting place of approved resolutions.

## Slide 5: Comments by commenter

## Slide 6: Status (2016-07-08)

## Slide 7: GEN & MAC detail

## Slide 8: Status of speculative editing

## Slide 9: A prediction
We took 249 days to resolve 1899 comments from SB0.
We have 334 comments unresolved from SB2.
Assuming linear progress, this implies 43 days left (from date of writing) to resolve these comments at the same rate
  This is Aug 13th.

## Slide 10: End timing
Constraints:
  At most one new recirculation may be performed after conditional approval in the July 2016 EC meeting (this is not a hard and fast rule)
  Aug 5th is the submission deadline for September RevCom. A last recirculation may still be in progress at the time of submittal. Comments must be resolve by 7th Sept.
We are resolving SB2 comments. Assuming we make changes, there will be at least SB3 (D7) and SB4 (D7 unchanged).
To make the Aug 5th deadline, we have to resolve SB2 comments, 15-day recirc (SB3), resolve those comments and start SB4. There are 26 days available for this, which includes the July 802.11 session.