## Slide 1: TGaf Vancouver Closing Report
Date: 2013-01-18
Authors:

## Slide 2: Abstract
This presentation is the closing report for the 19th face-to-face meeting of IEEE 802.11 TGaf, taking place the week of January 14th, 2013 at the IEEE 802 Wireless Interim in Vancouver.

## Slide 3: Plan for the Week
Regulatory update
Review the results of LB189 and Comment Collection
Review of the progress since November
Editorial review; spreadsheet 11-12/1017r27
Review and Approve all comment resolution submissions
Update the draft and comment resolution spreadsheet with approved changes, and request a recirculation letter ballot
Plan for March meeting and teleconferences

## Slide 4: TGaf Accomplishments
Reviewed the comment spreadsheet and resolved all of the remaining comments from LB189 and the Comment Collection
Requested the Editor to prepare D3.0 and the asked WG to start a recirculation letter ballot
Planned for March meeting, and weekly teleconferences
  Tuesdays at 21:00 ET for 2 hours

## Slide 5: Plan for March
Approve Vancouver and Teleconference minutes
Review and resolve comments from the recirculation letter ballot on Draft 3.0
Plan for May and Teleconferences

## Slide 6: TGaf Timeline – Affirmed January 2013
Initial Working Group Letter Ballot: January 2011
Second Working Group Letter Ballot: July 2012
Recirculation Letter Ballot: January 2013
Form Sponsor Ballot Pool: June 2013
Initial Sponsor Ballot: July 2013
Recirculate Sponsor Ballot: November 2013
Final WG/EC Approval: March 2014
RevCom/Standards Board Approval: June 2014

## Slide 7: Teleconferences
Weekly on Tuesdays through March 30th
  Until recirc is complete, calls will be used for regulatory updates
Time: 21:00 ET for up to 2 hours

## Slide 8: Motion
Having approved comment resolutions for all of the comments received from LB189 and the Comment Collection on TGaf D2.0 and D2.2 respectively, as contained in document 11-12/1017r29
Instruct the editor to prepare Draft 3.0 incorporating these resolutions and,
Approve a 15 day Working Group Recirculation Ballot, asking the question “Should P802.11af D3.0 be forwarded to Sponsor Ballot?”
Moved by Rich Kennedy on behalf of TGaf
TGaf vote:
Moved: Yongho Seconded: Zhou Lan Result: 11-0-0