## Slide 1: IEEE 802.11 TGmc Mar 2013 Agenda
March 2013
Dorothy Stanley, Aruba Networks
Slide <number>
Date: 2013-03-19
Authors:
Notes: doc.: IEEE 802.11-11/0291r0
July 2010
        Dorothy Stanley, Aruba Networks
Page <number>

## Slide 2: Abstract
March 2013
Dorothy Stanley, Aruba Networks
Slide <number>
This presentation contains the IEEE 802.11 TGmc agenda for the March 2013 session.
Notes: doc.: IEEE 802.11-11/0291r0
July 2010
        Dorothy Stanley, Aruba Networks
Page <number>

## Slide 3: TGmc Agenda
March 2013
Dorothy Stanley, Aruba Networks
Slide <number>
Attendance reminder: https://murphy.events.ieee.org/imat/
Documents: https://mentor.ieee.org/802.11/documents
Monday PM1
  Chair’s Welcome, Status, Review of Objectives, Approve agenda, minutes
  Editor’s Report
  Timeline and Schedule
  Comment resolution – Editor discuss
Wednesday PM1
  Motions
  Comment resolution –CID 1394, MAC comments
Thursday PM1, PM2
  Comment, LB Motions
  Plans for May
  AOB
Thursday PM1
  Motion, Comment Resolution –
  Editorial Discuss and Review, 13/330
Tuesday PM1
  13/293– Yaron Alpert
  Comment resolution –Editor Review, “Trivial technical”
Tuesday PM2
  Comment Resolution - Ashley,
  Scope of editorial comments
Wednesday PM2
  Comment Resolution - Security, Mesh, 13/0012, 13/0013
Notes: doc.: IEEE 802.11-11/0291r0
July 2010
        Dorothy Stanley, Aruba Networks
Page <number>

## Slide 4: TGmc – Monday PM1
March 2013
Dorothy Stanley, Aruba Networks
Slide <number>
Call Meeting to Order
Policies and Procedures, Attendance reminder
  **IEEE Patent Policy http://standards.ieee.org/board/pat/pat-slideset.ppt
    Are there any patent claim(s)/patent application claim(s) and/or the holder of patent claim(s)/patent application claim(s) that the participant believes may be essential for the use of that standard? Minute any responses that were given, specifically the patent claim(s)/patent application claim(s) and/or the holder of the patent claim(s)/patent application claim(s) that were identified (if any) and by whom.
** Read slide deck
*** Note especially items #7 & #11
Notes: doc.: IEEE 802.11-11/0291r0
July 2010
        Dorothy Stanley, Aruba Networks
Page <number>

## Slide 5
March 2013
Dorothy Stanley, Aruba Networks
Slide <number>
Please review the documents at the following links: - IEEE Patent Policy - http://standards.ieee.org/board/pat/pat-slideset.ppt - Patent FAQ - http://standards.ieee.org/board/pat/faq.pdf - LoA Form - http://standards.ieee.org/board/pat/loa.pdf - Affiliation FAQ -http://standards.ieee.org/faqs/affiliationFAQ.html
- Anti-Trust FAQ - http://standards.ieee.org/resources/antitrust-guidelines.pdf - Ethics - http://www.ieee.org/portal/cms_docs/about/CoE_poster.pdf - IEEE 802.11 Working Group P&P - https://mentor.ieee.org/802.11/public-file/07/11-07-0360-04-0000-802-11-policies-and-procedures.doc
802 WG P&P: https://mentor.ieee.org/802-ec/dcn/09/ec-09-0007-02-00EC-draft-lmsc-wg-p-p.pdf
New 802 LMSC P&P:https://mentor.ieee.org/802-ec/dcn/09/ec-09-0005-02-00EC-draft-revised-lmsc-p-p-for-wg-p-p-ballot.pdf
New 802 LMSC OM: https://mentor.ieee.org/802-ec/dcn/09/ec-09-0006-02-00EC-draft-revision-of-the-lmsc-om-for-wg-p-p.pdf
Notes: doc.: IEEE 802.11-11/0291r0
July 2010
        Dorothy Stanley, Aruba Networks
Page <number>

## Slide 6: Logistics
March 2013
Dorothy Stanley, Aruba Networks
Slide <number>
Slide <number>
Attendance recording procedures
  See 11-09/0246r0
  https://murphy.events.ieee.org/imat
  Must register before logging attendance
  Must log attendance during each 2 hour session
Documentation
  http://mentor.ieee.org
  Use “TGm” for documents relating to the Revision PAR
Notes: doc.: IEEE 802.11-11/0291r0
July 2010
        Dorothy Stanley, Aruba Networks
Page <number>
doc.: IEEE 802.11-10/0503r4
May 2010
        Michael Montemurro, Research in Motion
Page <number>

## Slide 7: Monday PM1 (continued)
March 2013
Dorothy Stanley, Aruba Networks
Slide <number>
Slide <number>
Objectives
  Comment resolution
Approve prior meeting minutes
  https://mentor.ieee.org/802.11/dcn/13/11-13-0022-00-000m-minutes-for-jan-2013-interim-vancouver.docx
  https://mentor.ieee.org/802.11/dcn/13/11-13-0236-01-000m-minutes-for-tg-revmc-teleconferences-feb-and-march-2013.docx
    Motion to approve: Moved: Jon Rosdahl, Second: Mike Montemurro, Result: Approved by unanimous consent
Editor’s Report (Adrian Stephens)
  Draft Status
  Comment Status
Notes: doc.: IEEE 802.11-11/0291r0
July 2010
        Dorothy Stanley, Aruba Networks
Page <number>
doc.: IEEE 802.11-10/0503r4
May 2010
        Michael Montemurro, Research in Motion
Page <number>

## Slide 8: TGmc Plan of Record
March 2013
Dorothy Stanley, Aruba Networks
Slide <number>
Slide <number>
20 July 2012 – 12 Sept 2012 – Call for Comment/Input
29-30 Aug 2012 – NesCom, SASB PAR Approval
Sept 2012 – Begin to process input
Sept 2012 – 11aa, 11ae integration
Jan – First WG Letter ballot - without 11ad
Dec 2012 – March/May 2013 – 11ad integration – May/July ballot on D2.0
Dec 2013 – March 2014 – 11ac integration
Feb 2014 – Mandatory Draft Review
Feb-March 2014 – Form Sponsor Pool (45 days)
April/May – Initial Sponsor Ballot
TBD – integration of additional completed amendments (e.g. 11af)
Nov 2014 – WG/EC Final Approval
March 2015 – RevCom/SASB Approval
Notes: doc.: IEEE 802.11-11/0291r0
July 2010
        Dorothy Stanley, Aruba Networks
Page <number>
doc.: IEEE 802.11-10/0503r4
May 2010
        Michael Montemurro, Research in Motion
Page <number>

## Slide 9: Advancing the “Needs Submission” Category Comments
March 2013
Dorothy Stanley, Aruba Networks
Slide <number>
Please review the comments with “Needs Submission” in Ad-Hoc status category (Column W) in
  in https://mentor.ieee.org/802.11/dcn/13/11-13-0233-03-000m-revmc-wg-ballot-comments.xls
Are there any CIDs that should not be so categorized?
  If so, please notify the chair
Proposal is to
  Assign submission to commenter
  If no submission received, reject comment with “insufficient detail provided” reason
Additionally mark CIDs 1010, 1078, 1640, 1417(same as 1640) as “Needs Submission”
  Any disagreement, please notify the chair
Notes: doc.: IEEE 802.11-11/0291r0
July 2010
        Dorothy Stanley, Aruba Networks
Page <number>

## Slide 10: Motion
March 2013
Dorothy Stanley, Aruba Networks
Slide <number>
Approve comment resolutions to comments in Document
  Editor Tab, Column “W – Ad-hoc Status” blank, and Column “N-Resolution Status” non-blank, except CID 1595
  And Editor Tab, Column “W – Ad-hoc Status” Ready for Motion, and Column “N-Resolution Status” non-blank, except CID 1595 in https://mentor.ieee.org/802.11/dcn/13/11-13-0233-05-000m-revmc-wg-ballot-comments.xls
Moved:
Seconded:
Result:
Notes: doc.: IEEE 802.11-11/0291r0
July 2010
        Dorothy Stanley, Aruba Networks
Page <number>

## Slide 11: March – May Meeting Planning
March 2013
Dorothy Stanley, Aruba Networks
Slide <number>
Objectives
  Comment resolution
Conference Calls 10am Eastern 2 hours
  April 5, 12, 19, 26,
  May 3
Ad-Hoc meeting – none
Schedule review
Notes: doc.: IEEE 802.11-11/0291r0
July 2010
        Dorothy Stanley, Aruba Networks
Page <number>

## Slide 12: References
March 2013
Dorothy Stanley, Aruba Networks
Slide <number>
https://mentor.ieee.org/802.11/dcn/12/11-12-0594-02-0000-revision-par-proposal-for-802-11-2012.doc
https://mentor.ieee.org/802.11/dcn/09/11-09-0002-12-0000-802-11-operations-manual.doc
https://mentor.ieee.org/802.11/dcn/12/11-12-1082-08-0000-revmc-pre-ballot-comments.xls
https://mentor.ieee.org/802.11/dcn/13/11-13-0233-04-000m-revmc-wg-ballot-comments.xls
Notes: doc.: IEEE 802.11-11/0291r0
July 2010
        Dorothy Stanley, Aruba Networks
Page <number>