## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-13/0361r47
Venue Date: | January 2015
First Author: | Mark Hamilton, Spectralink
Subject: | REVmc Working Group Ballot Comments for MAC ad-hoc
Full Date: | 2015-01-14
Author(s): | Name(s) | Mark Hamilton
| Company | Spectralink
Address
Phone:
Fax:
| email: | mark.hamilton@spectralink.com
Abstract:
This document contains comments in the "MAC ad hoc" group, submitted on REVmc letter ballots and by interested parties on the published IEEE Std 802.11-2012

## Revision History
Revision | Date | Description
0 | 2013-03-20 | Initial revision after first letter ballot. CIDs with resolutions ready for Motion MAC-F: 1074, 224, 1477, 1042, 1044, 1052, 1053, 118, 1065, 1628, 1194, 1429, 1456, 1555, 1556, 1585, 1622, 1060.
1 | 2013-03-21 | CIDs with resolution ready for Motion MAC-G (per TG discussion on 3-20): 1098, 1073, 1092, 1093, 1094, 1095, 1071, 1097, 1337, 1108, 1168, 1328, 1331, 1332, 1333, 1096.
2 | 2013-03-21 | Updates done during Orlando Thursday meetings. CIDs with resolution ready for Motion MAC-H: 1707, 1039, 1038, 1031, 284, 128.
3 | 2013-04-04 | Proposed resolutions to CIDs (ready for review): 89, 1008, 1134, 1135, 1424.
4 | 2013-04-23 | From teleconferences, CIDs with resolution ready for Motion MAC-H: 1006, 1008, 1026, 1027, 1049, 1051, 1055, 1056, 1057, 1058, 1062, 1102, 1134, 1136, 1151, 1172, 1222, 1229, 1263, 1269, 1392, 1410, 1430, 1469, 1480, 1549, 1638, 1694, 1703, 1704, 1705, 1706.
5 | 2013-05-06 | From Apr 26 teleconference, CIDs with resolution ready for Motion MAC-H: 1109, 1091, 1075, 1054, 1035, 1034, 1032, 1030, 1029, 1455, 1578, 1552, 1550, 1499, 1712, 1454, 1422, 1419, 1340, 1339, 1338.
6 | 2013-05-13 | Updates done during Kona Monday meetings. CIDs with resolution ready for Motion MAC-H: 1059, 1080, 1061, 1063, 1064, 1069, 1070, 30, 1005, 1043, 1037, 1104.
7 | 2013-05-14 | Updates done during Kona Tuesday meetings. CIDs with resolution ready for Motion MAC-H: 277, 1003, 287, 1251, 1257.
8 | 2013-07-02 | Updates from teleconferences, CIDs with resolution ready for Motion MAC-I: 1067, 1160, 1159, 1158, 1152, 1118, 1111, 50, 1106, 1163, 1066, 1007, 312, 309, 1460, 1448, 1107, 1398, 1534, 1474, 1473, 1472, 1406, 1402, 1161, 1399, 1162, 1397, 1315, 1169, 1166, 1165, 1164, 1661, 1401.
9 | 2013-07-15 | Updates from Geneva meeting, CID 1009 with resolution ready for Motion MAC-K (to be motioned independently). CIDs with resolution ready for Motion MAC-J: 1515, 1068, 1100, 1274, 1275, 1281, 1290, 1396, 1047, 1503, 1711, 1617, 1652, 1664, 1666, 1667, 1709, 1710, 1407. CID 309 removed from Motion MAC-I, and returned to unresolved (Comments tab).
10 | 2013-07-17 | Updates from Geneva meeting, CIDs with resolution ready for Motion MAC-L: 1511, 1155, 1167, 1170, 1292, 1295, 1400, 1439, 1150, 1482, 1679, 1516, 1566, 1615, 1616, 1656, 1658, 1678, 1481.
11 | 2013-07-23 | Updates from Geneva meeting, Motion MAC-L CIDs resolutions moved (except CID 1155). CIDs 78, 309, 310 resolutions moved. All remaining comments assigned to someone.
12 | 2013-09-17 | Updates from teleconferences, CIDs with resolution ready for Motion MAC-M: 1141, 263, 314, 317, 324, 1021, 1028, 1088, 1132, 1135, 1137, 1138, 77, 1140, 1654, 1148, 1153, 1154, 1258, 1259, 1260, 1296, 1305, 1311, 1335, 1367, 1373, 1139. Updates from Nanjing meeting, CIDs with resolution ready for Motion MAC-N: 1510, 1418, 278, 280, 285, 1216, 1411, 1458, 1671, 1525, 1548, 1602, 1635, 1660, 1668, 1424.
13 | 2013-09-18 | Updates from Nanjing meeting, CIDs with resolution ready for Motion MAC-O: 1291, 1050, 58.
14 | 2013-09-19 | Updates from Nanjing meeting, CIDs with resolution ready for Motion MAC-P: 1632, 1433, 1261, 1146, 1087, 1046, 1025, 1483, 1468, 1425, 1157, 1156, 1084, 91, 132, 131, 124, 121, 120, 11, 117, 148, 89, 88, 86, 59, 36, 31, 119, 201, 1442, 1155, 1086, 363, 361, 283, 145, 211, 147, 200, 198, 177, 157, 153, 1526, 222.
15 | 2013-10-30 | Comments from LB 199 added. (All previous comments resolved and moved to EDITOR ad hoc.)
16 | 2013-11-12 | CIDs with resolution ready for Motion MAC-Q: 2461, 2347, 2047, 2007. Many assignments made on other comments.
17 | 2013-11-14 | More CIDs with resolution ready for Motion MAC-Q: 2190, 2161, 2142, 2141, 2124, 2114, 2081, 2073, 2068, 2067, 2064, 2324, 2052, 2325, 2029, 2027, 2026, 2024, 2022, 2019, 2018, 2016, 2014, 2013, 2495, 2056, 2352, 2453, 2452, 2451, 2444, 2437, 2422, 2421, 2420, 2419, 2418, 2417, 2320, 2354, 2480, 2351, 2350, 2349, 2348, 2336, 2333, 2332, 2331, 2328, 2327, 2326, 2408.
18 | 2013-12-18 | Updates from teleconferences, CIDs with resolution ready for Motion MAC-R: 2035, 2046, 2045, 2044, 2042, 2041, 2356, 2036, 2095, 2034, 2033, 2032, 2030, 2028, 2359, 2037, 2329, 2448, 2447, 2446, 2339, 2338, 2335, 2050, 2330, 2066, 2197, 2132, 2130, 2117, 2116, 2469, 2334.
19 | 2013-12-27 | From teleconferences, more CIDs with resolution ready for Motion MAC-R: 2172, 2427, 2406, 2405, 2392.
20 | 2013-12-27 | One more CID from teleconference, with resolution ready for Motion MAC-R: 2134.
21 | 2014-01-19 | From teleconferences, more CIDs with resolution ready for Motion MAC-R: 2098, 2470, 2467, 2472.
22 | 2014-01-23 | Updates from Los Angeles meeting, CIDs with resolution ready for Motion MAC-S: 2370, 2169, 2171, 2187, 2358, 2362, 2363, 2364, 2365, 2366, 2367, 2165, 2369, 2494, 2371, 2372, 2374, 2376, 2391, 2416, 2426, 2445, 2466, 2486, 2368
23 | 2014-01-23 | Additional resolutions from Los Angeles meeting, CIDs with resolution ready for Motion MAC-T: 2496, 2140, 2048, 2023.
24 | 2014-01-24 | Additional resolution from Los Angeles meeting, CIDs with resolution ready for Motion MAC-T: 2031.
25 | 2014-03-01 | From teleconference, CIDs with resolution ready for Motion MAC-U: 2092, 2055, 2070, 2071, 2074, 2075, 2077, 2078, 2080, 2082, 8083, 2084, 2087, 2053, 2091, 2159, 2096, 2097, 2103, 2104, 3205, 2108, 2113, 2126, 2133, 2144, 2148, 2149, 2156, 2090.
26 | 2014-03-17 | From teleconference, CIDs with resolution ready for Motion MAC-U: 2125, 2143.
27 | 2014-03-20 | From face-to-face meeting: CIDs with resolution ready for Motion MAC-V: 2436, 2199, 2170, 2110, 2065, 2049, 2043, 2404, 2403, 2129, 2490, 2468, 2436, 2407, 2164.
28 | 2014-04-04 | From teleconference. CIDs with resolution ready for Motion MAC-X: 2102, 2063, 2079, 2086, 2089, 2093, 2058, 2101, 2167, 2109, 2138, 2153, 2158, 2160, 2162, 2100.
29 | 2014-05-12 | From teleconference, CID 2157 ready for Motion MAC-X
30 | 2014-05-13 | From face-to-face meeting: CIDs with resolution ready for Motion MAC-Y: 2464, 2460, 2458, 2455, 2454, 2410, 2168, 2155, 2154, 2119, 2094, 2054, 2051, 2009, 2005.
31 | 2014-05-15 | From face-to-face meeting: CIDs with resolution ready for Motion MAC-Z: 2481, 2479, 2473, 2471, 2360, 2462, 2459.
32 | 2014-07-17 | Updated for D3.0 ballot cycle (LB 202 comments added). From teleconference and F2F meeting: CIDs with resolution ready for Motion MAC-AA: 3069, 3024, 3013, 3011, 3005, 3001.
33 | 2014-07-17 | From face-to-face meeting: CIDs with resolution ready for Motion MAC-AB: 3093, 3085, 3072.
34 | 2014-09-12 | From teleconferences, CIDs with resolution ready for Motion MAC-AC: 3133, 3002, 3278, 3277, 3225, 3224, 3222, 3280, 3147, 3283, 3081, 3080, 3040, 3039, 3037, 3014, 3148, 3432, 3739, 3514, 3510, 3505, 3485, 3474, 3279, 3436, 3768, 3389, 3363, 3356, 3308, 3289, 3287, 3437.
35 | 2014-09-14 | From last teleconference, CIDs with resolution ready for Motion MAC-AD: 3743, 3742, 3741, 3740, 3665, 3647.
36 | 2014-09-16 | Removed from Motion MAC-AC, for further review and discussion: 3225, 3224, 3014, 3432, 3308. Added to Motion MAC-AD, as correction to transposition error: 3041. Ready for Motion MAC-AE based on face-to-face discussion through Monday: 3484, 3480, 3134, 3028, 3027, 3025, 3015.
37 | 2014-09-17 | From face-to-face meeting, CIDs with resolution ready for Motion MAC-AE: 3033, 3012, 3203, 3201, 3151, 3134, 3206, 3071, 3207, 3031, 3028, 3027, 3025, 3023, 3015, 3074, 3269, 3480, 3470, 3468, 3401, 3345, 3204, 3318, 3484, 3267, 3265, 3262, 3261, 3218, 3208, 3322.
38 | 2014-09-18 | Fixed typo in resolution for CID 3265.
39 | 2014-09-18 | Updated comments on CID3209 and approved motions on Motion MAC-AE tab and CID 3774.
40 | 2014-10-28 | From teleconferences, CIDs with resolution ready for Motion MAC-AF: 3313, 3019, 3042, 3119, 3120, 3141, 3018, 3143, 3504, 3314, 3323, 3324, 3334, 3351, 3478, 3142.
41 | 2014-11-01 | From teleconferences: CIDs with resolution ready for Motion MAC-AF: 3321, 3152, 3224, 3225, 3308, 3779, 3355, 3457, 3458, 3776, 3777, 3778
42 | 2014-11-04 | From face-to-face meeting: CIDs with resolution ready for Motion MAC-AG: 3520, 3507, 3506, 3502, 3500, 3150, 3146, 3145, 3144, 3068, 3063, 3062, 3061. Added document references for all known, pending submissions
43 | 2014-11-04 | From face-to-face meeting: CIDs with resolution ready for Motion MAC-AG: 3014, 3094, 3099, 3100, 3102, 3233, 3237, 3240, 3524
44 | 2014-11-05 | From face-to-face meeting: CIDs with resolution ready for Motion MAC-AH: 3675, 3669, 3668, 3648, 3519, 3391, 3355, 3285, 3263, 3239, 3132, 3131, 3129, 3128. Moved Motion MAC-AF and Motion MAC-AG to EDITOR with Motion number entered.
45 | 2014-11-17 | Results from face-to-face meeting. Approved resolutions moved out (to EDITOR).
46 | 2014-12-22 | From teleconferences: CIDs with resolution ready for Motion MAC-AI: 3483, 3394, 3377, 3374, 3360, 3359, 3292, 3264, 3241, 3213, 3212, 3084.
47 | 2015-01-14 | From January teleconference, CID with ready for Motion MAC-AI: 3692. From face-to-face meeting in Atlanta, CIDs with resolution ready for Motion MAC-AJ: 3364, 3007, 3008, 3032, 3138, 3226, 3294, 3490, 3296, 3508, 3365, 3382, 3385, 3390, 3430, 3439, 3295.

## Motion MAC-AI
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3483 | Mark RISON | 202 | 3 | 8.4.2.26 | 823 | 6 | E | Y | 823.06 | 6 | 8.4.2.26 |  | V |  |  |  | "Max Number Of MSDUs In A-MSDU" only applies to VHT STAs | Add "VHT" before (also at 1295.42) | REVISED (MAC: 2014-12-05 15:18:10Z): Make the changes described in 11-14/1104r6 under "Proposed changes:" for CID 3483, which allow opportunistic use of this feature by non-VHT STAs. | MAC | Motion MAC-AI | Ready for motion | EDITOR_Q: 2014-09-04 00:13:37Z - this is a technical change and needs to be transferred to MAC. Regardless of whether the change was made by .11ac, the intention might have been to permit its use by pre-.11ac device. Otherwise this field would most likely have been defined in the VHT Capabilities element. |  |  |  | 2014-12-05 15:23 | MAC
3394 | Mark RISON | 202 | 3 | 8.4.2.67.5 | 903 | 56 | T | Y | 903.56 | 56 | 8.4.2.67.5 |  | V |  |  |  | "The TAG field of the MSG portion of the message is a 17 octet string containing the ASCII representation of the STA MAC address using hexadecimal notation with colons between octets." -- does this mean that bit-reversed representation (rather than usual hex representation) is to be used? | Either change to hyphens or add note to say that hex representation is to be understood even though colons are used (also in MIB) | REVISED (MAC: 2014-12-05 15:13:48Z): Incorporate changes as shown in 11-14/1041r10 for CID 3394. | MAC | Motion MAC-AI | Ready for motion |  |  |  |  | 2014-12-22 18:07 | MAC
3377 | Mark RISON | 202 | 3 | 9.7.7.4 | 1287 | 41 | T | Y | 1287.41 | 41 | 9.7.7.4 |  | V |  |  |  | "OperationalRateSet, which is a parameter of the MLME-JOIN.request primitive" -- also the START | Add "and MLME-START.request primitive" | REVISED (MAC: 2014-12-22 18:26:49Z): Make the changes described in 11-14/1104r9 under "Proposed Changes" for CID 3359, 3360 and 3377. These delete the text which links the operational rate set with MCSs and which omits the MLME-START.request primitive (1287.41). | MAC | Motion MAC-AI | Ready for motion | MAC: 2014-12-05 16:21:28Z: Make the changes described in 11-14/1104r7 under "Proposed Changes" for CID 3359, 3360 and 3377. These delete the text which links the operational rate set with MCSs and which omits the MLME-START.request primitive (1287.41). |  |  |  | 2014-12-22 18:30 | MAC
3374 | Mark RISON | 202 | 3 | 10.1.3.9 |  |  | T | Y | 1521.3 | 30 | 10.1.3.9 |  | V |  |  |  | Need to specify whether the worst-case TSF drift between two devices is 0.01% or 0.02% | Add a NOTE to confirm it's 0.02% | REVISED (MAC: 2014-12-22 18:51:00Z): Incorporate the text changes shown in 11-14/1104r8 for CIDs 3212, 3213, 3345, and 3374 | MAC | Motion MAC-AI | Ready for motion |  |  |  |  | 2014-12-22 18:53 | MAC
3360 | Mark RISON | 202 | 3 |  |  |  | T | Y |  |  |  |  | V |  |  |  | Fix OperationalRateSet to be the set of rates which the STA can receive at, and nothing more (specifically not anything about the maximum rate for transmit, for example -- see e.g. 1276.41, 1287.41, 2637.65) | As it says | REVISED (MAC: 2014-12-22 18:28:53Z): Make the changes described in 11-14/1104r9 under "Proposed Changes" for CID 3359, 3360 and 3377, which address the issue raised by the commenter. | MAC | Motion MAC-AI | Ready for motion | MAC: 2014-12-05 16:23:44Z: Make the changes described in 11-14/1104r6 under "Proposed Changes" for CID 3360, which address the issue raised by the commenter. |  |  |  | 2014-12-22 18:30 | MAC
3359 | Mark RISON | 202 | 3 | 9.7.7.4 | 1287 | 41 | T | Y | 1287.41 | 41 | 9.7.7.4 |  | V |  |  |  | The OperationalRateSet is a set of integers in the range 0-127 representing pre-11n datarates (as rate / 500 kbps) and hence does not contain anything to do with MCSes | Make sure that all references to "operational rate" or "OperationalRate" do not involve MCSes | REVISED (MAC: 2014-12-22 18:26:49Z): Make the changes described in 11-14/1104r9 under "Proposed Changes" for CID 3359, 3360 and 3377. These delete the text which links the operational rate set with MCSs and which omits the MLME-START.request primitive (1287.41). | MAC | Motion MAC-AI | Ready for motion | MAC: 2014-12-05 16:21:28Z: Make the changes described in 11-14/1104r7 under "Proposed Changes" for CID 3359, 3360 and 3377. These delete the text which links the operational rate set with MCSs and which omits the MLME-START.request primitive (1287.41). |  |  |  | 2014-12-22 18:30 | MAC
3292 | Kwok Shum Au | 202 | 3 | 8.4.1.55 | 698 | 61 | T | N | 698.61 | 61 | 8.4.1.55 |  | V |  |  |  | Is "Chanel Schedule Management element" a field or a RLQP-element? If it is the latter, it does make sense to make a Info ID field and a length field but it should be discussed in clause 8.5, rather than clause 8.4. If it is the former, the description on Length is not required. Note here that this comment is a follow-up comment from editorial review of draft 2.7. | As in comment. | REVISED (MAC: 2014-12-22 18:07:44Z): Incorporate the changes in 11-14/0780r3 under CID 3069. | MAC | Motion MAC-AI | Ready for motion |  |  |  |  | 2014-12-22 18:12 | MAC
3264 | Qi Wang | 202 | 3 | 9.7.7.2 | 1299 | 14 | T | Y | 1299.14 | 14 | 9.7.7.2 |  | J |  |  |  | "A STA transmitting an Ack frame or a BlockAck frame in response to a frame sent using the DMG SC modulation class or DMG OFDM modulation class shall use an MCS from the mandatory MCS set of the DMG SC modulation class and shall use the highest MCS index for which the Data Rate is the same as or lower than that of the frame that elicited the response." This statement requires the ACK or Block ACK frame to an MCS 10 data frame to be transmitted using MCS 4, but any MCS 1-4 is Ok for ACK and any MCS 2-4 is Ok for Block Ack (frame duration won't change), and lower MCS's bring more robustness. | Text contribution will be provided. | REJECTED (MAC: 2014-12-22 19:12:53Z): The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-AI | Ready for motion | MAC: 2014-12-22 19:13:05Z: Discussed Nov 21 |  |  |  | 2014-12-22 19:14 | MAC
3241 | Qi Wang | 202 | 3 | 9.12 | 1294 | 25 | T | Y | 1294.25 | 25 | 9.12 |  | V |  |  |  | The word "may" in the sentence has been used in a confusing way, creating an interpretation that "use of A-MSDUs for PCP forwarding" is optional, whereas what is optional is the "PCP forwarding" itself, and the only way to perform PCP forwarding is through A-MSDUs. | A non-PCP DMG STA in a PBSS may use the PCP of the PBSSan A-MSDU to forward frames to another non-PCP STA in the PBSS via the PCP of the PBSS if the value of the PCP Forwarding field within the PCP's DMG Capabilities element is equal to 1. A non-PCP DMG STA in a PBSS shall not use the PCP to forward framesdo the forwarding if the value of the PCP Forwarding field within the PCP's DMG Capabilities element is equal to 0. In order to forward frames through the PCP, a non-PCP STA shall send individually addressed or group addressed MSDUs as A-MSDU subframes within an individually addressed A-MSDU frame sent to the PCP. The A-MSDU shall be formatted as specified in 8.3.2.2 (Aggregate MSDU(11ad) (A-MSDU) format), with the A-MSDU subframe headers' DA address set to the target individual or group address. | REVISED (MAC: 2014-12-22 19:14:51Z): Incorporate changes as shown in 11-14/1413r3 for CID 3241. | MAC | Motion MAC-AI | Ready for motion |  |  |  |  | 2014-12-22 19:15 | MAC
3213 | Qi Wang | 202 | 3 | 10.1.3.9 | 1521 | 50 | T | Y | 1521.5 | 50 | 10.1.3.9 |  | V |  |  |  | "The accuracy of the TSF timer shall be no worse than +/-0.01%." State DMG requirements if different. | DMG defines aClockAccuracy as +/-20 ppm; if the same level of accuracy is meant for TSF in DMG, sentence should state the DMG requirement separately; for example, "The TSF timer accuracy shall be +/-20 ppm for DMG networks and +/-100 ppm for non-DMG networks" or similar (Accuracy requirements throughout the specification seem to have been defined in ppm; sugggest to use 100 ppm instead of .01% for consistency). | REVISED (MAC: 2014-12-22 18:51:00Z): Incorporate the text changes shown in 11-14/1104r8 for CIDs 3212, 3213, 3345, and 3374 | MAC | Motion MAC-AI | Ready for motion |  |  |  |  | 2014-12-22 18:52 | MAC
3212 | Qi Wang | 202 | 3 | 9.35.6.5 | 1442 | 37 | T | Y | 1442.37 | 37 | 9.35.6.5 |  | V |  |  |  | The formula for guard time calculation makes use of constant C, which is defined "equal to aClockAccuracy, in units of ppm". The aClockAccuracy parameter has been defined as +/-20 ppm, so it is not clear what C shoud be set to. | Remove the +/- sign from the definition of aClockAccuracy in DMG MAC sublayer parameter values. Also use a less generic name such as aDMGTSFAccuracy. | REVISED (MAC: 2014-12-22 18:51:00Z): Incorporate the text changes shown in 11-14/1104r8 for CIDs 3212, 3213, 3345, and 3374 | MAC | Motion MAC-AI | Ready for motion |  |  |  |  | 2014-12-22 18:51 | MAC
3084 | Adrian Stephens | 202 | 3 | 8.4.2.135 | 1006 | 58 | G | Y | 1006.58 | 58 | 8.4.2.135 |  | J |  |  |  | BRP stands for both a frame and a packet. Multiple references from within the MAC to "fields of a BRP packet", which is both confusion as to which structure is being referenced, and breaks the layer model. Such references should either be fields of a BRP frame, or parameters of the TXVECTOR. | Terminology needs to be improved, e.g. to "BRP PPDU containing one or more BRP MPDUs with the xyz field equal to abc." where the field is in the MPDU. | REJECTED (MAC: 2014-12-22 19:11:58Z): The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-AI | Ready for motion | MAC: 2014-12-22 19:11:58Z - Discussed Nov 21 |  |  |  | 2014-12-22 19:14 | MAC
3692 | David Hunter | 202 | 3 | 10.1.4.3.3 | 1525 | 13 | T | Y | 1525.13 | 13 | 10.1.4.3.3 |  | V |  | 11-14/1594r0 |  | "perform the basic access procedure defined ... prior to the transmission": as if we didn't know the definition was prior to the transmission. It also is unclear whether this procedure is to be followed just once or each time a Probe Request frame is to be transmitted, and exactly why there may be more than one transmission of a Probe Request frame. | Since "prior to the transmission" is not part of the procedure defined in 9.3.4.2, this really is a run-on sentence. Replace "9.3.4.2 (Basic access) prior to the transmission of each of one or more Probe Request frames, each with an SSID indicated in the SSID List and the BSSID from the MLME-SCAN.request primitive." with "9.3.4.2 (Basic access). Perform this procedure prior to each transmission of a Probe Request frame. Each of these transmitted Probe Request frames shall contain an SSID that was included in the SSID List parameter and the BSSID from the BSSID parameter of the received MLME-SCAN.request primitive. One Probe Request frame shall be transmitted for each SSID included in the received SSID List parameter.". | REVISED (MAC: 2015-01-07 14:47:21Z): Incorporate the changes as noted in 11-14/1594r2 for CID 3692. | MAC | Motion MAC-AI | Ready for motion | MAC: 2014-12-22 19:04:48Z - Discussed on Dec 12. Carlos will bring back. EDITOR: 2014-07-01 10:54:55Z - Was originally a Trivial Technical, but as it requires resolving a conflict in the number of probe responses, making this a technial and assigning to CarlosC. |  |  |  | 2015-01-07 14:48 | MAC

## Motion MAC-AJ
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3364 | Mark RISON | 202 | 3 |  |  |  | T | Y |  |  |  |  | J |  |  |  | Requirements on BW for anything but RTS/CTS frames and first frame in TXOP re not clear | State that control responses can use any BSS bandwidth, but other frames (from either side) must obey the width set by RTS/CTS, where applicable | REJECTED (MAC: 2015-01-12 20:27:34Z): The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-AJ | Ready for motion |  |  |  |  | 2015-01-12 20:28 | MAC
3007 | Adrian Stephens | 202 | 3 | 8.4.2.157.2 | 1032 | 5 | G | Y | 1032.05 | 5 | 8.4.2.157.2 |  | V |  |  |  | "For a TVHT STA, support for Short GI is mandatory" -- this statement should not be in clause 8. Also "support is mandatory" is being replaced stylistically with "A TVHT STA shall support Short GI". | Move statement out of clause 8 and reword as proposed, or delete if it is a duplicate. | REVISED (MAC: 2015-01-13 22:40:23Z): Delete the following text on pg 1032 line 5: "For a TVHT STA, support for Short GI is mandatory." Note to commenter, a change was made in 4.3.13 for CID 3139, to indicate that short GI is mandatory. | MAC | Motion MAC-AJ | Ready for motion |  |  |  |  | 2015-01-13 22:54 | MAC
3008 | Adrian Stephens | 202 | 3 | 8.4.2.161 | 1037 | 20 | T | Y | 1037.2 | 20 | 8.4.2.161 |  | V |  |  |  | According to 1037.59, the value 3 in Table 8-253 is reserved for TVHT STAs. | Indicate in table 8-253: "For VHT STAs, Local Maximum ... for 160/80+80 MHz. Reserved for TVHT STAs." | REVISED (MAC: 2015-01-13 22:59:18Z): At page 1037 line 24, Table 8-253, at the end of the value 3 "Field(s) present" entry, add "For TVHT STAs, reserved." | MAC | Motion MAC-AJ | Ready for motion |  |  |  |  | 2015-01-13 23:06 | MAC
3032 | Adrian Stephens | 202 | 3 | 10.16.12 | 1682 | 34 | T | Y | 1682.34 | 34 | 10.16.12 |  | J |  |  |  | "A VHT STA is not required to perform any of the behavior described in this subclause associated with Information Request and 20 MHz BSS Width Request" -- this statement either has no effect, or creates internal contradictions with "an HT STA shall" statements in this subclause. | Identify the exceptions in this subclause and replace "<a type of HT STA>..." with "<a type of HT STA> that is not a VHT STA..." where <a type of HT STA> might include things like "40MC HT AP 2G4" and similar abominations. | REJECTED (MAC: 2015-01-13 21:30:24Z): The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-AJ | Ready for motion |  |  |  |  | 2015-01-13 21:32 | MAC
3138 | Mitsuru Iwaoka | 202 | 3 | 9.7.9 | 1290 | 6 | T | N | 1290.0601 | 6 | 9.7.9 |  | V |  |  |  | For a TVHT STA, data rates available with non-HT PPDU are 6, 9, 12, 18, 24, 36, 48 and 54 Mb/s divided by 7.5 for 6 MHz and 7 MHz unit channels and by 5.625 for 8 MHz channels. It is necessary to scale Non-HT reference rate in Table 9-7. | Insert a new bullet at the end of the 3rd paragraph of the subclause 4.3.13 as follows; - non-HT data rate is divided by 7.5 for 6 MHz and 7 MHz unit channels and by 5.625 for 8 MHz channels. | REVISED (MAC: 2015-01-13 22:13:30Z): Add the following NOTE to the end of Table 9-7: "NOTE -- in a TVWS band, the non-HT reference rate is scaled as described in 23.2.4" | MAC | Motion MAC-AJ | Ready for motion |  |  |  |  | 2015-01-13 22:15 | MAC
3226 | Qi Wang | 202 | 3 | 10.33.2.2 | 1805 | 23 | E | Y | 1805.23 | 23 | 10.33.2.2 |  | V |  |  |  | Consider using PPDU | "... any other individually addressed PPDUA-MPDU, MPDU, or MMPDU to the responder ..." | REVISED (MAC: 2015-01-13 19:54:24Z): Delete "A-MPDU," and ", or MMPDU" at 1805.23. | MAC | Motion MAC-AJ | Ready for motion | EDITOR: 2014-09-05 12:12:45Z - This is not an editorial change. I would note that "individually addressed PPDU" is meaningless. Transferring to MAC. |  |  |  | 2015-01-13 19:56 | MAC
3294 | Nihar Jindal | 202 | 3 | 8.4.2.157.2 | 1029 | 47 | T | Y | 1029.47 | 47 | 8.4.2.157.2 |  | V |  |  |  | The architecture of an 80+80 receiver does not imply support for 160 MHz operation as is already suggeted by the current definitions of the values for 1 and 2. I.e. support for 160 does not imply support for 80+80 and similarly, support for 80+80 does not imply support for 160. I.e. the case for 80+80 only support is missing. | Change "The value of 3 is reserved" to "Set to 3 if the STA supports 80+80 MHz mode and not 160 MHz" Change "Set to 1 if the STA supports 160 MHz" to "Set to 1 if the STA supports 160 MHz and not 80+80 MHz" | REVISED (MAC: 2015-01-13 21:08:55Z): Incorporate changes in 11-14/954r3 for CIDs 3490, 3294, 3295, 3296. | MAC | Motion MAC-AJ | Ready for motion | REVISED (MAC: 2015-01-13 21:08:55Z): Incorporate changes in 11-14/954r3 for CIDs 3490, 3294, 3295, 3296. |  |  |  | 2015-01-13 21:25 | MAC
3490 | Tom Kolze | 202 | 3 | 8.4.2.157.2 | 1029 | 47 | T | Y | 1029.47 | 47 | 8.4.2.157.2 |  | V |  |  |  | The case for 80+80 support is missing. Support for 80+80 does not imply support for 160 and support for 160 does not imply support for 80+80. and similarly, support for 80+80 does not imply support for 160. | Change "The value of 3 is reserved" to "Set to 3 if the STA supports 80+80 MHz mode and not 160 MHz". IS: "Set to 1 if the STA supports 160 MHz" SHOULD BE: "Set to 1 if the STA supports 160 MHz and not 80+80 MHz" | REVISED (MAC: 2015-01-13 21:08:55Z): Incorporate changes in 11-14/954r3 for CIDs 3490, 3294, 3295, 3296. | MAC | Motion MAC-AJ | Ready for motion | REVISED (MAC: 2015-01-13 21:08:55Z): Incorporate changes in 11-14/954r3 for CIDs 3490, 3294, 3295, 3296. |  |  |  | 2015-01-13 21:26 | MAC
3296 | Matthew Fischer | 202 | 3 | 8.4.2.157.2 | 1029 | 47 | T | Y | 1029.47 | 47 | 8.4.2.157.2 |  | V |  |  |  | The universally complete set of architectures of 80+80 receivers does not imply support for 160 MHz operation as is already suggeted by the current definitions of the values for 1 and 2. I.e. support for 160 does not imply support for 80+80 and similarly, support for 80+80 does not imply support for 160. I.e. the case for 80+80 only support is missing. Same comment for TVHT (see 8.4.2.170) | Change "The value of 3 is reserved" to "Set to 3 if the STA supports 80+80 MHz mode and not 160 MHz" Change "Set to 1 if the STA supports 160 MHz" to "Set to 1 if the STA supports 160 MHz and not 80+80 MHz" - similar request for change to TVHT equivalent structures. | REVISED (MAC: 2015-01-13 21:08:55Z): Incorporate changes in 11-14/954r3 for CIDs 3490, 3294, 3295, 3296. | MAC | Motion MAC-AJ | Ready for motion | REVISED (MAC: 2015-01-13 21:08:55Z): Incorporate changes in 11-14/954r3 for CIDs 3490, 3294, 3295, 3296. |  |  |  | 2015-01-13 21:25 | MAC
3508 | Mark Hamilton | 202 | 3 | 8.4.2.3 | 711 | 5 | E | N | 711.05 | 5 | 8.4.2.3 |  | V |  |  |  | BSSMembershipSelector concept, added to Supported Rates element, really means the name "Suported Rates" is now misleading. Consider enhancing the name. | Change the element name from "Supported Rates" to "Supported Rates and PHYs" | REVISED (MAC: 2015-01-12 19:26:32Z): Replace all occurances of "Supported Rates element" with "Supported Rates and BSS Membership Selectors element". Replace all occurrences of "Extended Supported Rates element" with "Extended Supported Rates and BSS Membership Selectors element". | MAC | Motion MAC-AJ | Ready for motion | MAC: 2015-01-11 20:51:52Z - Proposed Resolution: Revised. Replace all occurances of “Supported Rates element” with “Supported Rates and BSS Membership Selectors element”. Replace all occurrences of “Extended Supported Rates element” with “Extended Supported Rates and BSS Membership Selectors element”. Suggest (perhaps): SRBMS = "Supported Rates and BSS Membership Selectors" (so, SRBMS element, Extended SRBMS element) There are some places where it says "Suppoted Rates element" but should say "Supported Rates or Extended Supported Rates elements", but those are therefore broken already, and this won't make it any worse. Probably a good item for a future comment, though. Not sure what other contexts might be a concern… EDITOR: 2014-12-15 06:26:42Z - Assigned to MAC EDITOR: 2014-10-07 09:22:12Z - While agreeing with the concept, I don't think the resolution has enough detail to be workable. This term occurs in different contexts, and I'm not sure the same change is applicable to all. Also the concept of a "selector" is not necessarily limited to PHY selection. It might be anything that we choose, such as support for extended block ack. Any name that attempts to explain this purpose is likely to be unweildy, and I recommend we create an abbreviation for this purpose - e.g. Support RBF, standing for "Rate and BSS Feature" or RBMS for "Rate and BSS Membership Selector". Marking "Submission Required". MGR: 2014-09-15 08:27:46Z - Is this changing the element name (throughout the spec) or actually the eponymous field in the element? What about Extended Supported Rates? |  |  |  | 2015-01-12 19:30 | MAC
3365 | Mark RISON | 202 | 3 | 8.6.2.3.1 | 1078 | 7 | T | Y | 1078.0699 | 7 | 8.6.2.3.1 |  | V |  | 11-14/1104r4 |  | There appears to be nothing to ensure that the UPs in multiple TCLAS elements in ADDTS Request (and any other frame which can carry multiple TCLAS elements) specify the same UP | Add something to that effect somewhere | REVISED (MAC: 2015-01-12 21:16:31Z): Incorporate the text changes in 11-14/1104r10 for CID 3365. | MAC | Motion MAC-AJ | Ready for motion |  |  |  |  | 2015-01-12 21:17 | MAC
3382 | Mark RISON | 202 | 3 | C.3 |  |  | T | Y | 2814.53 | 53 | C.3 |  | V |  | 11-14/1104r4 |  | dot11EDCATableTXOPLimit is not defined for Clause 20; dot11QAPEDCATableTXOPLimit is not defined for Clauses 20 or 21 | Add references to these clauses to the description | REVISED (MAC: 2015-01-12 21:26:35Z): Incorporate the text changes in 11-14/1104r10 for CID 3382. | MAC | Motion MAC-AJ | Ready for motion |  |  |  |  | 2015-01-12 21:27 | MAC
3385 | Mark RISON | 202 | 3 | 8.4.2.157.3 | 1032 | 7 | T | Y | 1032.0699 | 7 | 8.4.2.157.3 |  | V |  |  |  | Not clear whether the Supported VHT-MCS and NSS Set field refers to per-user or total N_SS, in the case of MU-MIMO | Suggest it be per-user | REVISED (MAC: 2015-01-13 22:00:46Z): Revised. Add "to a user" to the end of the cited sentence. | MAC | Motion MAC-AJ | Ready for motion |  |  |  |  | 2015-01-13 22:02 | MAC
3390 | Mark RISON | 202 | 3 | 9.22.2.8 | 1315 | 57 | E | Y | 1315.5699 | 57 | 9.22.2.8 |  | V |  |  |  | "3) A VHT MU PPDU carrying A-MPDUs to different users" -- wording is unclear | Change to "3) A VHT MU PPDU carrying single A-MPDUs to different users", matching 2) above | REVISED (MAC: 2015-01-12 21:12:00Z): Add after "carrying A-MPDUS to adiffernt users", "(a single A-MPDU to each user)". | MAC | Motion MAC-AJ | Ready for motion | EDITOR_Q: 2014-09-04 00:07:57Z - the proposed change can be inferred from the text. I believe it to be a technical change. Transferred to MAC |  |  |  | 2015-01-13 19:43 | MAC
3430 | Mark RISON | 202 | 3 | 11.3.5.4 | 1862 | 56 | E | Y | 1862.5601 | 56 | 11.3.5.4 |  | V |  |  |  | Having more than one thing (e.g. "KCK ¦¦ PMK") on the left of an equals sign is somewhat confusing | Use L() as in 11.6.1.3 | REVISED (MAC: 2015-01-13 20:08:34Z): Incorporate the text changes in 11-14/1104r11 for CID 3430. | MAC | Motion MAC-AJ | Ready for motion | EDITOR: 2014-11-19 14:11:42Z - Somehow, had failed to make the transfer. Transferred to MAC, really! EDITOR: 2014-10-23 15:27:48Z - This requires a technical interpretation of the meaning of these symbols. Transfer to MAC. Note the resolution "Replace "KCK ¦¦ PMK" with "(KCK ¦¦ PMK)"." has been speculatively edited. MGR: 2014-09-17 06:41:02Z - That doesn't really help address the confusion. As the proposed change says, you need to use L() as in 11.6.1.3, i.e. blah = KDF-512(zoo,zah,zing), KCK = L(blah, foo, bar), PMK = L(blah, baz, boing) | I | EDITOR_A: 2014-09-13 13:54:56Z |  | 2015-01-13 20:09 | MAC
3439 | Mark RISON | 202 | 3 | 11.6.1.7.2 |  |  | T | Y | 1937.23 | 23 | 11.6.1.7.2 |  | V |  | 11-14/1104r4 |  | It is not specified how to convert from a character string to a bit string (8.2.2 says nothing about this) | Specify (a) the encoding (ASCII?) and (b) whether the string is to be considered to have a terminating NUL (the answer to this is probably no, given things like ""FT-R0" is 0x46 0x54 0x2D 0x52 0x30.") In turn, things like that quoted in the previous parenthesis can be deleted | REVISED (MAC: 2015-01-12 19:42:03Z): Make the changes described in 11-14/1104r10 under "Proposed changes:" for CID 3439, which effect the change proposed by the commenter. | MAC | Motion MAC-AJ | Ready for motion | From teleconference: Propose to reject as no technical issue is identified; many interoperable implementations are available. Strings in 11r KDFs are all defined. Assign back to Mark Rison, submission required, if change is still desired. |  |  |  | 2015-01-12 19:43 | MAC
3295 | Nihar Jindal | 202 | 3 | 8.4.2.157.3 | 1032 | 10 | T | Y | 1032.1 | 10 | 8.4.2.157.3 |  | V |  |  |  | The architecture of an 80+80 MHz receiver does not imply support for certain capabilities when operating in 60 MHz mode as is already suggeted by the existence of the Highest Supported Long GI Data Rate fields. Some obvious combinations cannot currently be signaled. | Change the reserved field at bits 29-31 to become "Max NSS for 80+80 MHz" with the value in the field equal to nss supported for 80+80 MHz and a value of 0 to be used when 80+80 MHz is not supported. Change the reserved field at bits 61-63 to become "Max NSS for 160 MHz" with the value in the field equal to nss supported for 160 MHz and a value of 0 to be used when 160 MHz is not supported. Might also want to add a note saying that these values do not place an upper bound on the NSS supported for 20, 40, 80 MHz - those bounds are specified elsewhere. | REVISED (MAC: 2015-01-13 21:08:55Z): Incorporate changes in 11-14/954r3 for CIDs 3490, 3294, 3295, 3296. | MAC | Motion MAC-AJ | Ready for motion | REVISED (MAC: 2015-01-13 21:08:55Z): Incorporate changes in 11-14/954r3 for CIDs 3490, 3294, 3295, 3296. |  |  |  | 2015-01-13 21:25 | MAC

## WNM
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3209 | Gabor Bajko | 202 | 3 | 10.24.14 | 1733 | 52 | T | N | 1733.52 | 52 | 10.24.14 |  |  | Gabor Bajko |  |  | The Proxy ARP functionality does not address how to handle the ARP Announcement packets used for Address Conflict Detection and Address Defense. It should be described, to avoid inconsistent behaviour among different Proxy ARP implementation. | Submission will be provided. |  | MAC | WNM | Submission Required | MAC: 2014-09-18 11:34:18Z: Considered 11-14/1173r1. Jouni asked for further time to review. Mark H noted that the uplink announcements need to be explicitly 'blocked' at the AP (so that it doesn't duplicate if it generates one), and if the AP does generate one it needs to go to the DS (and thereby 'elsewhere'), and not just to this BSS. Same thing on the IPv6 case, of course. |  |  |  | 2014-09-18 11:36 | MAC

## VHT Capabilities
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3487 | Vinko Erceg | 202 | 3 | 8.4.2.157.3 | 1032 |  | T | Y | 1032 |  | 8.4.2.157.3 |  |  | Vinko Erceg |  |  | VHT capabilities for BW and Nss are coupled. However, same Nss does not have to apply for 80MHz, 160MHz and 80+80MHz BW. | Use reserved bits B29-B31 to indicate Max Nss for 80+80MHz BW (0 indicates that 80+80MHz BW is not supported). Use reserved bits B61-B63 to indicate Max Nss for 160MHz BW (0 indicates that 160MHz BW is not supported). |  | MAC | VHT Capabilities | Submission Required |  |  |  |  | 2014-06-25 09:28 | EDITOR
3486 | Vinko Erceg | 202 | 3 | 8.4.2.157.2 | 1029 |  | T | Y | 1029 |  | 8.4.2.157.2 |  |  | Vinko Erceg |  |  | VHT capabilities for BW and Nss are coupled. However, same Nss does not have to apply for 80MHz, 160MHz and 80+80MHz BW. | Use B2-B3 bits to indicate if 80+80MHz or 160MHz BWs are used. |  | MAC | VHT Capabilities | Submission Required |  |  |  |  | 2014-06-25 09:28 | EDITOR
3300 | Matthew Fischer | 202 | 3 | 8.4.2.157.2 | 1029 | 23 | T | Y | 1029.23 | 23 | 8.4.2.157.2 |  |  | Vinko Erceg |  |  | The universally complete set of architectures of VHT receivers does not imply identical spatial stream support for SU and MU cases. I.e. the ability to differentiate spatial stream support values for MU vs SU is missing. This comment also applies to TVHT. | Change bits 30-31 of the VHT Capabilities Info field from reserved to "MU NSS Reduction" with a definition of the "The value of MU NSS Reduction field is an unsigned integer representing the reduction in the maximum number of spatial streams that is supported by the STA when receiving or transmitting an MU PPDU as compared to the maximum number of spatial streams that are supported by the STA when receiving or transmitting an SU PPDU. The maximum number of spatial streams that are supported by the STA when receiving or transmitting an SU PPDU is equal to the smaller of the maximum number of spatial streams supported by the STA when receiving an SU PPDU and the maximum number of spatial streams supported by the STA when transmitting an SU PPDU. The maximum number of spatial streams supported by the STA when receiving an SU PPDU is the highest number of spatial streams for which the RX VHT-MCS map subfield does not contain the value of 3. The maximum number of spatial streams supported by the STA when transmitting an SU PPDU is the highest number of spatial streams for which the TX VHT-MCS map subfield does not contain the value of 3. " As an alternative, even though it seems odd, one could place these new bits in some of the reserved bit locations of the HT Cap IE in the Extended capabilities subfield where there are lots of bits available. All VHT STA must transmit this IE anyway. If the bits were placed in the HT IE location, then the field could be extended by one bit, and possibly even duplicated to differentiate TX from RX. Make similar changes for TVHT, e.g. 8.4.2.170 |  | MAC | VHT Capabilities | [5 empty] | 2014-06-25 09:28 | EDITOR
3297 | Matthew Fischer | 202 | 3 | 8.4.2.157.3 | 1032 | 10 | T | Y | 1032.1 | 10 | 8.4.2.157.3 |  |  | Vinko Erceg | 11-14/793r3 |  | The universally complete set of architectures of 80+80 receivers does not imply support for certain capabilities when operating in 160 MHz mode as is already suggested by the existence of the Highest Supported Long GI Data Rate fields. Some obvious combinations cannot currently be signaled. Also applies to TVHT (see, for example, 8.4.2.170) | Change the reserved field at bits 29-31 to become "Max NSS for 80+80 MHz" with the value in the field equal to nss supported for 80+80 MHz and a value of 0 to be used when 80+80 MHz is not supported. Change the reserved field at bits 61-63 to become "Max NSS for 160 MHz" with the value in the field equal to nss supported for 160 MHz and a value of 0 to be used when 160 MHz is not supported. Might also want to add a note saying that these values do not place an upper bound on the NSS supported for 20, 40, 80 MHz - those bounds are specified elsewhere. Note that similar changes should be executed for TVHT. |  | MAC | VHT Capabilities |  | See also 3298 |  |  |  | 2014-12-25 05:40 | MAC
3491 | Tom Kolze | 202 | 3 | 8.4.2.157.3 | 1032 | 10 | T | Y | 1032.1 | 10 | 8.4.2.157.3 |  |  | Vinko Erceg |  |  | Some obvious combinations of 80+80 receivers cannot currently be signaled. | Reserved field at bits 29-31 SHOULD BE: "Max NSS for 80+80 MHz" with the value in the field equal to NSS supported for 80+80 MHz and a value of 0 to be used when 80+80 MHz is not supported. The reserved field at bits 61-63 SHOULD BE: "Max NSS for 160 MHz" with the value in the field equal to NSS supported for 160 MHz and a value of 0 to be used when 160 MHz is not supported. Add note saying these values do not place an upper bound on the NSS supported for 20, 40, 80 MHz - those bounds are specified elsewhere. |  | MAC | VHT Capabilities | [5 empty] | 2014-06-25 09:28 | EDITOR

## VHT
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3477 | Mark RISON | 202 | 3 | 9.13.6 | 1298 | 33 | T | Y | 1298.33 | 33 | 9.13.6 |  |  | Vinko Erceg | 11-14/1104r4 |  | The second bullet appears to allow a VHT single MPDU (i.e. one with EOF = 1) to be followed by null subframes with EOF = 0. Once EOF has been signalled, it makes no sense to unsignal it (cf. 145.33) | Change "0 in the EOF field" to "the same value in the EOF field as the preceding A-MPDU subframe" |  | MAC | VHT | [5 empty] | 2014-11-04 05:07 | MAC

## TVHT
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3489 | Vinko Erceg | 202 | 3 | 8.4.2.170 | 1046 |  | T | Y | 1046 |  | 8.4.2.170 |  |  | Vinko Erceg |  |  | For TVHT different number of segments supported may have different number of Nss supported. Allow for this flexibility. | As in comment. I will bring contribution. |  | MAC | TVHT | Submission Required |  |  |  |  | 2014-06-25 09:21 | EDITOR
3035 | Adrian Stephens | 202 | 3 | 10.43 | 1829 | 56 | G | Y | 1829.5601 | 56 | 10.43 |  |  | Ron Porat |  |  | "A TVHT AP shall set the Channel Width subfield in the TVHT Operation Information field to indicate the BSS operating channel width and transmitted PPDU type depending on value of B0-B1 in TVHT-SIG-A1 field from those shown in Table 10-26 (TVHT BSS operating channel width" -- The MAC should not know about SIGNAL fields, only VECTOR parameters. | Replace: "of B0-B1 in TVHT-SIG-A1 field" with a reference to a TXVECTOR parameter. |  | MAC | TVHT | Submission Required |  |  |  |  | 2014-06-25 09:21 | EDITOR

## Rates
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3299 | Matthew Fischer | 202 | 3 | 8.4.2.3 | 711 | 60 | T | Y | 711.6 | 60 | 8.4.2.3 |  |  | Matthew Fischer |  |  | Add a BSS membership selector for "private network" with the membership requirement to join the private network found in a specific location, e.g. include a new IE which contains an OUI field and a type field which together are a reference to a VSIE that matches that OUI value and with the type octet matching the octet that immediately follows the OUI value in the VSIE. The VSIE provides further details of what is required for membership, expressed in a vendor-specific manner. (continuation of rejected LB199 CID 2473 - rejected due to insufficient information) | Add a row to Table 8-86 "BSS membership value encoding", the row to contain: value "125", feature "vendor specific", interpretation: "Support of vendor specific features is required in order to join the BSS that was the source of the Supported Rates element or Extended Supported Rates element containing this value. The vendor specific features are identified by the vendor specific OUI and type values listed in the Vendor Specific BSS Membership Selector Information Element" - add a new element "Vendor Specific BSS Membership Selector IE" with a body that contains a variable length list of N "vendor specific BSS membership selector reference" fields, with the description for "vendor specific BSS membership selector reference field" as: Each vendor specific BSS membership selector reference field has a three octet OUI value and a one octet type value, together each OUI/type pair describes a vendor specific element that matches the given OUI/type pair and which contains information that describes, in a vendor specific manner, BSS membership conditions. |  | MAC | Rates | [5 empty] | 2014-07-16 20:52 | MAC
3298 | Matthew Fischer | 202 | 3 | 8.4.2.157.3 | 1032 | 26 | T | Y | 1032.26 | 26 | 8.4.2.157.3 |  |  | Matthew Fischer | 11-14/793r3 |  | There is no text in this subclause to define the fields Rx Highest Supported Long GI Data Rate or Tx Highest Supported Long GI Data Rate. | Add a sentence or two indicating that the Rx Highest Supported Long GI Data Rate field and Tx Highest Supported Long GI Data Rate are defined in Table 8-251. |  | MAC | Rates |  | See also 3297 |  |  |  | 2014-12-25 05:40 | MAC

## Power Saving
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3523 | Mark Hamilton | 202 | 3 | 8.2.4.1.7 | 554 | 54 | T | Y | 554.54 | 54 | 8.2.4.1.7 |  |  | Mark Hamilton |  |  | The rules in 8.2.4.1.7 are not consistent with 10.2.2.2. The concepts "MMDU is bufferable" and "PM bit is reserved" need to be separated. It makes no sense to say that an Action MMDU sent by a non-AP STA is bufferable, for example, just because you want to be able to say that the PM is valid in the MPDUs used to send it. The exception for the PM bit in Probe Responses sent in response to unicast Probe Requests in an IBSS makes no sense It's not clear enough which Control MPDUs have non-reserved PM bits and when. Note for example that 8.2.4.1.7 implies the PM bit in ACKs sent by a non-AP STA are not reserved. | Consider documents 11-12/1199 and 11-13/0131 |  | MAC | Power Saving | Submission Required |  |  |  |  | 2014-11-04 04:33 | MAC
3460 | Mark RISON | 202 | 3 | 10.2.2.16.4 | 1551 | 44 | T | Y | 1551.4399 | 44 | 10.2.2.16.4 |  |  | Emily Qi |  |  | No behaviour is indicated for "Alternate Preferred, due to existing stream with different delivery interval", "Alternate Preferred, due to policy limits on AP" and "Alternate Preferred, due to AP changed the delivery interval" (and maybe others?) | Add normative behaviour for all statuses |  | MAC | Power Saving | Submission Required |  |  |  |  | 2015-01-13 02:13 | MAC
3459 | Mark RISON | 202 | 3 | 10.2.2.16.3 | 1551 | 21 | T | Y | 1551.21 | 21 | 10.2.2.16.3 |  |  | Mark Hamilton |  |  | There is no single "Alternate Preferred" status | Refer to the two specific statuses from table 8-203 |  | MAC | Power Saving | [5 empty] | 2015-01-13 02:13 | MAC
3301 | Matthew Fischer | 202 | 3 | 8.3.1.1 | 587 | 50 | T | Y | 587.5 | 50 | 8.3.1.1 |  |  | Matthew Fischer |  |  | Implementations can benefit through the addition of another dynamic PS mechanism which is receiver bandwidth based. Add a BW-based dynamice PS mechanism. | Change the definition of the FC bits in the RTS frame to allow the More Frag, More Data, Protected Frame and Order bits to be used collectively to form the "TXOP Width" subfield which signals the width of the upcoming MSDU-bearing PPDUs that follow the RTS. Each of the 4 bits indicates which portion of the BSS operating width is being used for the MSDU-bearing PPDUs such that one bit indicates use of the primary 20 MHz channel, another indicates use of the primary 40 MHz channel, the third the secondary 40 MHz channel and the 4th bit indicates use of the secondary 80 MHz channel. |  | MAC | Power Saving | Submission Required |  |  |  |  | 2014-07-16 20:52 | MAC

## Metrics
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3488 | Vinko Erceg | 202 | 3 |  |  |  | T | Y | [5 empty] | Vinko Erceg |  |  | In May 2014 IEEE 802.11 meeting, REVmc worked on a liaison letter from 3GPP. Throughput parameter was proposed to be used for network selection. However, this parameter needs to be defined in REVmc to be useful. | Define Throughput parameter in REVmc. I will bring contribution. |  | MAC | Metrics | Submission Required |  |  |  |  | 2014-06-25 09:29 | EDITOR

## MAC operation
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3231 | Qi Wang | 202 | 3 | 9.24.4 | 1349 | 43 | T | Y | 1349.4301 | 43 | 9.24.4 |  |  | Payam Torob Jahromi |  |  | If no MSDUs or A-MSDUs are passed up to the next MAC process after the receipt of the BlockAckReq frame and the starting sequence number of the BlockAckReq frame is newer than the NextExpectedSequenceNumber for that block ack agreement, then the NextExpectedSequenceNumber for that block ack agreement is set to the sequence number of the BlockAckReq frame. | The statement is of the form "if (A and B) then C"; Break the if and define behavior for all combinations of A and B, including any missing ele statements (pseudo code in 9.24.7.3 seems to have defined a behavior). |  | MAC | MAC operation | Submission Required |  |  |  |  | 2015-01-07 18:41 | MAC

## Location
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3471 | Mark RISON | 202 | 3 | 10.24.6.3 | 1717 | 53 | T | Y | 1717.53 | 53 | 10.24.6.3 |  |  | Brian Hart |  |  | There should be a mechanism to allow the initiating STA to known which parameter the responding STA is incapable of honouring | Use the Value field to indicate this (e.g. it could give the index of (one of) the field(s) which the rSTA is incapable of |  | MAC | Location | Submission Required |  |  |  |  | 2014-06-25 08:53 | EDITOR

## Frame formats
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3499 | Mark Hamilton | 202 | 3 | 8.6.22.2 | 1211 | 28 | T | Y | 1211.28 | 28 | 8.6.22.2 |  |  | Carlos Cordeiro | 11-14/1594r0 |  | "Multiple elements can appear in this frame." Like what? Anything? This is underconstrained. List what can, and makes sense, to put here; or something | Clarify what elements are sensible or expected in this frame. |  | MAC | Frame formats | Submission Required | MAC: 2014-12-22 19:01:51Z - Discussed Dec 12, still some open discussion (captured in 11-14/1568), Carlos will bring back. |  |  |  | 2014-12-22 19:04 | MAC

## Fragmentation
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3211 | George Vlantis | 202 | 3 | 20.4.4 | 2361 | 16 | T | Y | 2361.1599 | 16 | 20.4.4 |  |  | Mark Rison | 11-14/1104 |  | aMPDUMaxLength is not defined in Table 20-25 (nor wasn't it defined in the 802.11n amendment). So what is the maximum length of an un-aggregated MPDU for the HT PHY? In Clause 16, 17, 18, and 19 this parameter is defined in the PHY characteristics table. For 802.11a and 802.11g the value is 4096 octets. However, the dot11FragmentationThreshold MIB variable limits the longest transmission to be 2346, originally for both PHYs, under the rules of Clause 9, but this was later changed to be 3000 octets in 802.11REVmb, and changed again in 802.11n to 8000 octets. With this last increase to dot11FragmentationThreshold, aMPDUMaxLength = 4096 octets became the effective limit for these two PHYs. Now, in 802.11n, aMPUDMaxLength was not defined in the HT PHY parameters, although it is still required as one of the parameters in the initialization of the PHY primitive. aPSDUMaxLength = 65536, and the aPPDUMaxTime = 10ms were added, and the configurable dot11MaxAMSDUlength MIB variable = either 7935 or 3839 (default) was added. These 3 parameters, together, do limit the PHY transmission in both the aggregated and unaggregated cases, but then the default value for dot11FragmentationThreshold, which becomes the limit of an unaggregate packet, is ill-defined because aMPDUMaxLength is undefined for the Clause 20 HT PHY. All that is really known is that 8000 octets is the upper limit for dot11Fragmentation Threshold. (See the last sentence of the description of dot11FragmentationThreshold on page 3120, line 57, which gives the equation for calculating dot11FragmentationThreshold as a function of aMPDUMaxLength.) | Define aMPDUMaxLength for the HT PHY. In this way, the length of the maximum unaggregated MPDU (and the default maximum fragment as defined by the value of dot11FragmentationThreshold in the MIB) will be well-defined, as well as the parameter to the PHY initialization. (Sorry for not finding this in REVmb or earlier ballots of REVmc.) |  | MAC | Fragmentation | Submission Required | Some of the history is out-of-date. Nonetheless, the problem statement is accurate. Clauses 21, 22 and 23 probably have the same problem. Need a submission suggesting what the aMPDUMaxLength should be for HT, DMG, VHT and TVHT, and providing rationale for the selection(s). |  |  |  | 2014-12-23 17:33 | MAC

## Editorials objected to
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3462 | Mark RISON | 202 | 3 |  |  |  | E | Y | [5 empty] | Mark Rison |  |  | "Alternate Preferred" -- actually it's not a mere preference, it's an override | Change to "Overridden" throughout (10 instances in 8.4.2.76, 10.2.2.16.3, 10.2.2.16.4 and 10.24.8) | REVISED (EDITOR: 2014-08-14 10:14:52Z) - Change "Alternate Preferred" to "Alternate Proposed" throughout. In reply to the commenter, "Overridden doesn't quite catch the semantics. The AP has not created the FMS, but suggested or proposed parameters that might be accepted. 'Overridden' would suit different semantics in which the FMS was created with the alternate paramters, but this is not the case here." | MAC | Editorials objected to | Submission Required | EDITOR: 2014-11-19 14:39:21Z - This is turning into a technical debate. Transferring to MAC. MGR: 2014-09-15 08:27:46Z - Then I'm confused by 1551.20: "If the AP selects an alternate delivery interval or alternate maximum delivery interval from the value specified in the FMS Request, the FMS Status subelement shall be set to Alternate Preferred, and the FMS subelement shall indicate the AP selected value(s)." It sounds like the AP has made the decision, not that it wants the STA to ask for something else. | I | EDITOR: 2014-09-01 14:54:32Z |  | 2014-12-23 16:20 | MAC

## Editorials
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3674 | David Hunter | 202 | 3 | 9.38.2.5 | 1476 | 38 | E | Y | 1476.38 | 38 | 9.38.2.5 | [5 empty] | "When present, the Sector Sweep Ack (SSW-Ack) occurs following an SSW Feedback.": is this just a natural occurance? Need to indicate what STA issues this frame (and the fact that these two names are the names of frames). | Replace "(SSW-Ack) occurs following" with "(SSW-Ack) frame is issued after the STA receives an SSW Feedback frame." |  | MAC | Editorials |  | Need inputs from domain experts. Transferred to MAC. |  |  |  | 2014-09-04 23:13 | EDITOR_Q
3673 | David Hunter | 202 | 3 | 9.38.2.4 | 1475 | 57 | E | Y | 1475.5699 | 57 | 9.38.2.4 | [5 empty] | "Sector Sweep Feedback (SSW Feedback) occurs following each RSS.": is this just some naturally occuring phenonmenon? Need to indicate who issues the SSW Feedback frame, as well as the fact it is a frame. | Replace "(SSW Feedback) occurs following each RSS." with "(SSW Feedback) frame is issued by the STA after it completes each RSS." |  | MAC | Editorials |  | EDITOR_Q: 2014-09-04 23:12:01Z - Need input from the domain experts. Transferred to MAC. |  |  |  | 2014-09-04 23:12 | EDITOR_Q

## DMG
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3392 | Mark RISON | 202 | 3 | 9.6 | 1272 | 11 | T | Y | 1272.11 | 11 | 9.6 |  |  | Mark Rison | 11-14/1413r0 |  | "A STA shall support the concurrent reception of fragments of at least three MSDUs or MMPDUs. [...] The destination STA shall maintain a Receive Timer for each MSDU or MMPDU being received, for a minimum of three MSDUs or MMPDUs." -- does this always apply (e.g. DMG STAs -- see end of 9.5 and 9.22.2.1; also what about the risk of MSDU/MMPDU reordering caused by concurrent reception causing replay detection to discard MSDUs/MMPDUs)? | If it doesn't apply to all STAs, add suitable caveats |  | MAC | DMG | Submission Required | MAC: 2014-11-21 15:36:56Z - From telecon: Agree with the Reject proposal, as we are quite sure there is text somewhere else that does require this for all STAs. Need to recall that discussion (from the F2F in San Antonio) and find the cite. Will reconsider on the next telecon, and confirm that we've covered all the cases, and determined whether there are any special cases or not (after refreshing the memory of the F2F discussion, as well). Assigned to Mark R, for now. |  |  |  | 2014-12-12 16:44 | MAC

## Clause 6
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3521 | Mark Hamilton | 202 | 3 | 6.3.26.6.2 | 237 | 15 | T | Y | 237.15 | 15 | 6.3.26.6.2 |  |  | Mark Hamilton | 11-14/1358r1 |  | Get rid of all TIMEOUT ReasonCode values, unless there is explicit discussion of it in the protocol/behavior (and then give it a more descriptive name) | Get rid of all TIMEOUT ReasonCode values, unless there is explicit discussion of it in the protocol/behavior (and then give it a more descriptive name). I.e., change TIMEOUT in 6.3.26.6.2 (and 6.3.26.7.2, 6.3.27.6.2, 6.3.27.7.2, 6.3.29.6.2 and 6.3.29.7.2) ReasonCode to INACTIVITY_TIMEOUT; delete TIMEOUT from 6.3.93.10.2 and 6.3.93.11.2 (unless Relay links have a timeout semantics specified somewhere else); etc. |  | MAC | Clause 6 | Submission Required |  |  |  |  | 2014-11-05 00:47 | MAC

## Capabilities
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3479 | Mark RISON | 202 | 3 | 10.40.4 | 1823 | 9 | T | Y | 1823.09 | 9 | 10.40.4 |  |  | Mark Rison | 11-14/1104r4 |  | For non-VHT STAs to be able to fully benefit from the new power/regulatory/channel switching stuff, it is necessary for them e.g. to be able to receive a unicast (Extended) Channel Switch Announcement MMPDU with e.g. a VHT Transmit Power Envelope element | Add an Extended Capability bit to allow a non-VHT STA to indicate support for the VHT power/regulatory/channel switching stuff, and ensure the text requires VHT STAs to use the VHT power/regulatory/channel switching stuff with non-VHT devices which have indicated this capability |  | MAC | Capabilities | Submission Required |  |  |  |  | 2014-11-04 05:08 | MAC

## Comments
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3232 | Qi Wang | 202 | 3 | 8.4.2.136 | 1009 | 1 | T | Y | 1009.01 | 1 | 8.4.2.136 |  |  | Carlos Cordeiro | 11-14/1594r0 |  | It is not stated anywhere which frame(s) are used to carry the Awake Window element. | Add AwakeWindow to DMG Beacon and Announce frame body (Table 8-49 and Table 8-401), or state in 8.4.2.136 that the element can be carried in DMG Beacon and Announce frames, or other solution. |  | MAC |  |  | MAC: 2015-01-13 19:18:44Z - REVISED (MAC: 2015-01-13 19:05:19Z): Make the changes as noted in 11-14/1594r3 as noted for CID 3232. [Consider on Wed] MAC: 2014-12-22 19:01:51Z - Discussed Dec 12, still some open discussion (captured in 11-14/1568), Carlos will bring back. MAC: 2014-11-21 15:24:42Z: From telecon: Simple addition as proposed is not agreed; need to add to tables. Ordering of fields debated - will be considered separately (needs a new comment). |  |  |  | 2015-01-13 19:20 | MAC