## Slide 1: HEW Project Plan Discussion
Date: 2013-05-16
Authors:

## Slide 2: Abstract
Slides to provoke discussion on HEW Study Group project plan and timeline

## Slide 3: Objective of HEW SG
Per 802 P&P rules, objective is to develop PAR and 5C
Plan to Achieve Objective
Plan must identify steps and timeline to complete PAR and 5C
Focused on deliverables
Answer ‘Topicality’ and ‘Viability’ and you complete PAR and 5C

## Slide 4: Terms
Topicality: the ability to concisely define the topic
  Concisely define the topic
    Can we identify a focused problem to solve? Can we write concise text that accurately describes the problem?
    Precursor to PAR Scope and Purpose
  Value of the topic to the industry
    Is the problem worth solving? Does solving the problem provide meaningful improvement in the marketplace? Is the problem and its solution distinct?
    Assessment of 5C broad market potential and distinct identity
Viability: assessment of technical feasibility
  Make tentative assessment of ability to solve identified problem using technology
  Evaluation of sample technologies; non-exhaustive
  Complexity? Cost to performance? Proven technology? Possible to test? Reliability?
  Assessment of 5C technical feasibility and economic feasibility

## Slide 5: Sequence of Activities needed for HEW SG to complete work
Organization and Planning
Topicality1: Presentations/Discussions to explore the breadth of the contemplated scope-of-work
Topicality2: Presentations/Discussions for refinement and to gain common understanding on contemplated scope-of-work
Start PAR: Initial draft of PAR(s) and 5C; discuss and refine language on PAR(s) and 5C; initial drafts of supplemental documents, if any (simulation scenarios, requirements document, channel models, others?)
Viability: High level discussions of technologies, to provide confidence of our ability to solve identified problem(s)
Finish PAR: Finalize and approve PAR(s) and 5C; supplemental documents

## Slide 6
Focus of work
May Interim : Organization, Topicality1
July Plenary : Topicality2, Start PAR, Viability
Sept Interim (hard stop) : Viability, Finish PAR
Nov Plenary (hard stop) : pending 802 EC approval
Pre-SG Phase
HEW SG Timeline and Plan: Nov 2013 finish
Jan 2013
Jan 2014
March
May
July
Sept
Nov
Plenary
Plenary
Plenary
Interim
Interim
Interim
Interim
Study Group approved but pending start
Milestone: HEW SG Start
Milestone: HEW SG Finish

## Slide 7
Focus of work
May Interim : Organization, Topicality1
July Plenary : Topicality1,2
Sept Interim : Topicality2, Start PAR, Viability
Nov Plenary : Start PAR, Viability
Jan Interim (hard stop) : Finish PAR
Mar Plenary (hard stop) : pending 802 EC approval
Pre-SG Phase
HEW SG Timeline and Plan: Mar 2014 finish
Jan 2013
Jan 2014
March
May
July
Sept
Nov
Plenary
Plenary
Plenary
Interim
Interim
Interim
Interim
Study Group approved but pending start
Milestone: HEW SG Start
Milestone: HEW SG Finish
March

## Slide 8: Options Discussion
Nov 2013 option gives only two remaining meetings, July and September, to complete all work of the SG
Mar 2014 option gives four remaining meetings, Jul, Sept, Nov, Jan, to complete all work of SG
What is our achievable plan? How do we focus work during and between meetings to achieve plan?