## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-14/0975r3
Venue Date: | September 2014
First Author: | Jon Rosdahl, CSR
Subject: | REVmc Working Group Ballot Comments
Full Date: | 2014-10-14
Author(s): | Name(s) | Jon Rosdahl
| Company | CSR Technologies Inc.
| Address | 10871 N 570 W, Highland, UT 84003
| Phone: | +1-801-492-4023
Fax:
| email: | adrian.p.stephens@intel.com
Abstract:
This document contains the GenAdHoc comments received on LB202 for P802.11REVmc during working group letter ballot LB202 .
As comment resolutions are approved, comments are moved to the editor for implementation and this file then will shrink.

## Revision History
Revision | Date | Description
0 | 2014-07-16 | Initial version with LB202mc comments for Gen AdHoc - status as of Wednesday
1 | 2014-07-18 | Status of Comments after July Plenary (One CID missed - See Tab "Gen SD - B")
2 | 2014-09-14 | Update for Comment status after the Telecons for Aug-Sept. (See Tab "Gen Telecon - Aug")
3 | 2014-09-18 | Updalte for Comment Status through Wednesday Sept 18
4 | 2014-10-12 | Update with comment status through Athens and first Telecon 03 Oct 2014
5 | 2014-10-14 | Comments received on assigned Comments added - Mark RISON - 3426, 3325, 3137, 3136, 3052, 3051, 3050, 3049 and Change AdHoc STatus to Review for added proposed Resolutions to Adhoc notes for the following CIDs: 3438, 3372, 3528,3463, Note Submission required for CID: 3407, 3393, 3379, 3370,3368, 3369, 3561, 3056
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29

## Terminology
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3721 | David Hunter | 202 | 3 | 10.2.2.19 | 1556 | 45 | T | Y | 1556.45 | 45 | 10.2.2.19 |  |  | Eldad Perahia |  |  | "The VHT AP shall include a nav-set sequence": this clearly is statement of a formal requirement. However, there is no definition, anywhere in the standard, of exactly what a "nav-set sequence" is. How can a normative requirement be justified, when the thing being 'required' is undefined? (The only attempts at an elucidation of this term are several "e.g." parenthetical remarks distributed around the text. The most extensive of these is the page 1317 "e.g." that lists two possibilities. How many more possibilities there are is unknown.) | Unless a complete formal definition of this term is inserted somewhere before this location, just convert this statement into the friendly informative statement it otherwise appears to be: replace "shall include" with "usually includes" and in the next sentence replace "shall not" with "doesn't". |  | GEN | Terminology | Submission Required |  |  |  |  | 2014-06-25 08:56 | EDITOR
3393 | Mark RISON | 202 | 3 |  |  |  | E | Y | [8 empty] | References to "Clause <n> frames" (n = 16, 17, etc.) make no sense as frames are a MAC concept. "rates" is suspect too because a given rate may be used by more than one PHY (e.g. 11g and 11a, and probably some variants of 11a and 11n). Other forms like "Clause <n> waveforms" or "PPDUs" or "formats" make sense but should be consistent | Pick one valid term (I suggest PPDU) and use it consistently |  | GEN | Terminology | Submission Required | EDITOR: 2014-08-11 12:58:45Z - Changing terminology is not a purely editorial function. Transferring to GEN. EDITOR: 2014-08-04 08:59:26Z - Commenter adds: (not trivially tractable. Need to search for “Clause” closely followed by “frame” or “rate” or “waveform” or “format” (any others, assuming PPDU is chosen as the canonical form?), but the intervening thing could be a list of numbers and will also probably have stuff in parentheses. See e.g. the logorrhoea in the bottom half of page 1369, 1367.35, 1367.39, 1371.24, 1721.34, 2699.25, 2904.34, but the stuff on pages 883 and 1368 (except maybe 1368.11) is OK since it’s about the actual rates in the rate set. I found these instances by searching for “) frame” etc.) |  |  |  | 2014-10-13 14:15 | GEN
3379 | Mark RISON | 202 | 3 |  |  |  | E | Y | [8 empty] | There are still a bunch of desires (nearly 100), under the "desir" stem (desirable, desiring) | Change them in the same way as the CID 2051 resolution |  | GEN | Terminology | Submission Required | Rewording such has not proved a trivial task in the past, and turns out to require technical creativity. Transferring to GEN. |  |  |  | 2014-10-13 14:15 | GEN
3372 | Mark RISON | 202 | 3 |  |  |  | E | Y | [5 empty] | Jon Rosdahl |  |  | There are a bunch of "*BSS network"s, which seems pleonastic (about 22 instances) | Delete the "network"s |  | GEN | Terminology | Review | GEN: - Proposed Resolution: Reject - "network" in this context is descriptive and does not cause harm to the text and is not detrimental to the standard. Examples: 16.15 -"or two STAs in an independent basic service set (IBSS) network." 67.43 -"The key concept is that the ESS network appears the same to an LLC layer as an IBSS network." 68.14 -"Some examples are when an IBSS network is operating in a location that also has an ESS network," 99.43 - "The differences among the ESS, the PBSS, and the IBSS network environments are discussed separately in 4.7 (Differences among ESS, PBSS, and IBSS LANs). List of uses: "wireless network"; "access network"; "IBSS network"; "ESS network"; "PBSS network"; "MBSS network";" non-IBSS network";"public network"; "private network"; EDITOR: 2014-08-14 10:50:38Z - A BSS is: "basic service set (BSS):A set of stations (STAs) …" A network is: "a group of two or more computer systems linked together. " (Webopedia). The question is whether adding "network" adds anything in the contexts where it is used. This is not an editorial question. Transferring to GEN. |  |  |  | 2014-10-14 13:26 | GEN
3370 | Mark RISON | 202 | 3 |  |  |  | E | Y | [8 empty] | What is the point of saying "-compliant"? (11 instances) | Delete throughout (also at places where the hyphen is missing, e.g. 548.15, 1856.44, 2235.45, 2238.27, 2373.48, 2378.27, 3303.58) |  | GEN | Terminology | Submission Required | EDITOR: 2014-08-14 12:52:55Z - This is not an editorial question. Transferring to GEN. |  |  |  | 2014-10-14 13:04 | GEN
3368 | Mark RISON | 202 | 3 |  |  |  | E | Y | [8 empty] | Some parts of the spec, namely 160.58, 165.55, 1851.20 think dot11AuthenticationAlgorithm specifies a single algorithm; while this is technically true, it's in a table which lists allows algs, so should be worded as such; 1851.61 starts off well but refers to the variable not the table | Something along the lines of "If dot11AuthenticationAlgorithm does not include the value "Open System," might be good, but probably needs "Table" or something like that |  | GEN | Terminology | Submission Required | EDITOR: 2014-08-14 12:54:18Z - This is not an editorial issue, as it relates to expressing the difference between a table and a single value. Transferring to GEN. |  |  |  | 2014-10-14 13:23 | GEN
3463 | Mark RISON | 202 | 3 |  |  |  | E | Y | [5 empty] | Jon Rosdahl |  |  | It's not a "Burst Timeout" (4 instances) | Change to "Burst Duration" |  | GEN | Terminology | Review | GEN: Proposed resolution: Revise:(D3.2 line numbers) Change "Burst Timeout" with "Burst Duration" at 1057.52 (Note Figure 8-567 is split across page needs anchor to be on one page) 1058.62, 1058.64, 1059.1 (name of table), 1746.26 - EDITOR: 2014-08-14 10:08:45Z - I would recommend making this change. However, I do know that the authors of the FTM mechanism spent some time discussing terminology, so I think this needs to be discussed in the group whether "timeout" carries some subtlety not realized by "duration". Transferring to GEN to facilitate this discussion. |  |  |  | 2014-10-14 13:19 | GEN

## support for 11b
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3124 | Graham Smith | 202 | 3 | 20.1 | 2267 | 20 | T | Y | 2267.2 | 20 | 20.1 |  |  | Graham Smith |  |  | Clause 20 specifies mandatory support of Clause 17, which I suppose also implies manatory support of clause 16, when operating in 2.4GHz band. Suggest that this coupling is removed. A ST that supports clauses 16/17/19 and 20 should be refer to as 11b/g/n, and it should be allowed to have a device that supports just 11g/n. This would comply nicely with industry certification and labelling. If an 11b STA was used, then it would be clear that an 11b/g/n (or at least 11b/g) AP would be needed. | A separate presentation will be made by the commenter |  | GEN | support for 11b | Submission Required |  |  |  |  | 2014-06-24 10:51 | EDITOR
3123 | Graham Smith | 202 | 3 | 19 | 2254 | 1 | T | Y | 2254.01 | 1 | 19 |  |  | Dorothy Stanley |  |  | Generally separate clause 19 from implicit support of Clauses 16/17. | A separate presentation will be made by the commenter |  | GEN | support for 11b | Submission Required |  |  |  |  | 2014-06-25 09:06 | EDITOR
3122 | Graham Smith | 202 | 3 | 19.1.2 | 2254 | 17 | T | Y | 2254.1699 | 17 | 19.1.2 |  |  | Dorothy Stanley |  |  | "Introduction". This clause specifies that a 2.4GHz OFDM clause 19 device must support DSSS and CCK. Commonly known as an 11b/g device. There is a good case that OFDM only devices could exist without the need for the extra hardware and software required to support DSSS and CCK, let's call it 11g. Similarly there is a good case that devices that support 11b as well could exist, let's call them 11b/g. Hence, it is time for the standard to allow this distinction. If vendors wish to make 11g devices, or 11b devices or 11b/g devices then the standard should allow that and the distinction is very clear. | Clause 19.1.2 to read "The ERP draws from Clause 18 (Orthogonal frequency division multiplexing (OFDM) PHY specification) to provide payload data rates of 6, 9, 12, 18, 24, 36, 48, and 54 Mb/s. |  | GEN | support for 11b | [5 empty] | 2014-06-25 09:06 | EDITOR
3121 | Graham Smith | 202 | 3 | 19.1.1 | 2254 | 9 | T | Y | 2254.0901 | 9 | 19.1.1 |  |  | Dorothy Stanley |  |  | Separate out the close coupling between Clause 19 and clauses 16 and 17. Clause 19 should refer to OFDM. If it is deemed that a Clause 19 device must support must also support clause 16 and 17 PHY then so be it, but let's state that sperately instead of this close coupling. It is time htat we made this clause agree with the common terminology that is used, i.e. 11b is Clause 16/17, and 11g is Clause 19 an, this is important 11b/g, is exactly what it says, a device that supports DSSS/CCK and OFDM at 2.4GHz. This comment is just for clause 19.1.1 "General" | Replace "This clause specifies further rate extension of the PHY for the DSSS system of Clause 16 (DSSS PHY specification for the 2.4 GHz band designated for ISM applications) and the extensions of Clause 17 (High rate direct sequence spread spectrum (HR/DSSS) PHY specification). Hereinafter the PHY defined in thisclause is known as the ERP. This PHY operates in the 2.4 GHz ISM band. " with "This clause specifies the PHY entity for an orthogonal frequency division multiplexing (OFDM) system operating in the 2.4GHz ISM band. Hereinafter the PHY defined in this clause is known as the ERP". |  | GEN | support for 11b | [5 empty] | 2014-06-25 09:06 | EDITOR

## Security
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3438 | Mark RISON | 202 | 3 |  |  |  | E | Y | [5 empty] | Jon Rosdahl |  |  | Is it PMK caching or PMKSA caching? | Be consistent (PMKSA caching seems more popular, 3 instances of the other one) |  | GEN | Security | Review | GEN: 2014-10-13 - Proposed Resolution: Revised: 104.19 - Change "PMK caching" to "PMKSA caching "; 104.42 - Change "pairwise master key (PMK) caching" to PMSKA caching"; 1934.24 - No Change - Generic use of the word cache. 2915.16 - Change "maximum lifetime of a PMK in the PMK cache." to "maximum lifetime of a PMK in the PMKSA cache." 3305.61 - No Change - Generic use of the word cache. Discussion Context items: PMK = pairwise master key (PMK): The key derived from a key generated by an Extensible Authentication Protocol (EAP) method or obtained directly from a preshared key (PSK). PMKSA = pairwise master key security association (PMKSA): The context resulting from a successful IEEE Std 802.1X authentication exchange between the peer and Authentication Server (AS) or from a preshared key (PSK). PMKSA: A result of a successful IEEE Std 802.lX exchange, SAE authentication, preshared PMK information, or PMK cached via some other mechanism. 4.10.7 PMKSA caching - Clause defining PMKSA caching Cache - A store of things that may be required in the future See http://en.wiktionary.org/wiki/cache See http://en.wikipedia.org/wiki/Cache -- EDITOR: 2014-08-11 12:31:43Z - Transferred to GEN. This is not an editorial issue, but a choice of terminology. EDITOR: 2014-08-04 09:07:56Z - Commenter adds: plus 2 instances of “PMK cache” |  |  |  | 2014-10-14 13:00 | GEN
3426 | Mark RISON | 202 | 3 |  |  |  | E | Y | [5 empty] | Mark Rison | 11-14/1104r2 |  | "HMAC-SHA-256" (6 instances) is confusing as 256 is not the output length | "HMAC-SHA256" |  | GEN | Security | Discuss | EDITOR: 2014-08-11 12:27:05Z - As this is creating an interpretation of the meaning of the hyphen in this context, it is not editorial. Transferring to GEN. |  |  |  | 2014-10-13 14:09 | GEN

## Protection mechanisms
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3352 | Mark RISON | 202 | 3 | 10.1.4.5 | 1528 | 60 | T | Y | 1528.6 | 60 | 10.1.4.5 |  |  | Jon Rosdahl |  |  | The new text forces an IBSS to the lowest common denominator, rather than allowing a higher denominator subject to protection, as envisaged in e.g. 9.26.2 Protection mechanism for non-ERP receivers | Add text to say that Beacons transmitted by an IBSS STA may contain PHY-related IEs not present in a received Beacon, subject to setting any "non-ERP-present"-like bits and to using appropriate protection mechanisms (see 9.24) |  | GEN | Protection mechanisms | Submission Required |  |  |  |  | 2014-07-15 01:23 | MAC

## PICS
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3407 | Mark RISON | 202 | 3 |  |  |  | E | Y | [8 empty] | Why are there duplicate PICS entries for 11ad, e.g. QoS Frame Format | Merge them (being careful with the references, which seem to be different) |  | GEN | PICS | Submission Required | EDITOR: 2014-08-11 10:58:17Z - Needs a submission. Probably worth doing. This is not an editorial issue, transferring to GEN. |  |  |  | 2014-08-11 10:59 | EDITOR
3325 | Mark RISON | 202 | 3 | B.4.17.1 | 2733 | 46 | T | Y | 2733.46 | 46 | B.4.17.1 |  |  | Mark Rison | 11-14/1104r2 |  | What does HTM17.1 mean when it says AP support for SMPS is mandatory? The implication of HTM17.3 and HTM17.4 is that this actually just means advertising the current state in the HT Capabilties | Clarify. See other comment on whether the thing being advertised is a capability or a state |  | GEN | PICS | Discuss |  |  |  |  | 2014-10-13 14:12 | GEN
3137 | Mitsuru Iwaoka | 202 | 3 | B.4.3 | 2629 | 26 | T | N | 2629.26 | 26 | B.4.3 |  |  | Mark Rison | 11-14/1104r2 |  | According to the resolutions of CID 5015-5017 of P802.11af Sponsor Ballot (see 11-12/1017r62), a TVHT STA is an HT STA, thus, CF16 shall be mandatory for CF30. | Insert a new "* CF16.3" row as follows; * CF16.3 ¦ HT operation in TVWS band ¦ ¦ CF30:M ¦ Yes [] No [] N/A [] |  | GEN | PICS | Discuss |  |  |  |  | 2014-10-13 14:10 | GEN
3136 | Mitsuru Iwaoka | 202 | 3 | B.4.3 | 2627 | 60 | T | N | 2627.6001 | 60 | B.4.3 |  |  | Mark Rison | 11-14/1104r2 |  | CF6 (OFDM) PHY shall be mandatory for TVHT PHY as it shall support non-HT PPDU format. | Add "CF30:M" to the Status column of the "* CF6" row. |  | GEN | PICS | Discuss |  |  |  |  | 2014-10-13 14:10 | GEN
3052 | Adrian Stephens | 202 | 3 | B.4.19 | 2762 | 47 | G | Y | 2762.47 | 47 | B.4.19 |  |  | Mark Rison | 11-14/1104r2 |  | "type equal to Fine Timing Measurement Range request/report" There is no such type. Ditto at 2762.53. | Reword "Initiator of Measurement request/report with type equal to Fine Timing Measurement Range request/report" to remove "/" and use only defined terms for reports and types. |  | GEN | PICS | Discuss |  |  |  |  | 2014-10-13 14:11 | GEN
3051 | Adrian Stephens | 202 | 3 | B.4.17.1 | 2731 | 14 | G | N | 2731.1399 | 14 | B.4.17.1 |  |  | Mark Rison | 11-14/1104r2 |  | The change made by .11ac (insertion of CF29:M) to HTM8 is redundant given the change from CID 187. I.e. a VHT STA is an HT STA, and CF16:M suffices. | Remove CF29:M at cited location. |  | GEN | PICS | Discuss |  |  |  |  | 2014-10-13 14:11 | GEN
3050 | Adrian Stephens | 202 | 3 | B.4.4.2 | 2651 | 12 | T | Y | 2651.1201 | 12 | B.4.4.2 |  |  | Mark Rison | 11-14/1104r2 |  | The changes to FR11 from CID 2425 leave the Status cell empty. | Specify an non-blank status. |  | GEN | PICS | Discuss |  |  |  |  | 2014-10-13 14:11 | GEN
3049 | Adrian Stephens | 202 | 3 | B.4.4.2 | 2647 | 29 | G | Y | 2647.29 | 29 | B.4.4.2 |  |  | Mark Rison | 11-14/1104r2 |  | Why is there are reference to Annex E? It doesn't seem relevant. Ditto at 2650.26. | Remove reference to Annex E. |  | GEN | PICS | Discuss |  |  |  |  | 2014-10-13 14:11 | GEN

## PHY (VHT)
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3187 | Sigurd Schelstraete | 202 | 3 | 22.3.8.3.5 | 2487 | 29 | T | N | 2487.29 | 29 | 22.3.8.3.5 |  |  | Vinko Erceg |  |  | P_VHTLTF not defined in (22-40) | Add "P_VHTLTF is defined in (22-43)" |  | GEN | PHY (VHT) | [5 empty] | 2014-06-25 08:56 | EDITOR
3179 | Sigurd Schelstraete | 202 | 3 | 22.3.7.4 | 2471 | 62 | T | N | 2471.6201 | 62 | 22.3.7.4 |  |  | Vinko Erceg |  |  | Clarify starting point of time offset | Replace "starting time of the corresponding field" with "starting time of the corresponding field relative to the start of L-STF" |  | GEN | PHY (VHT) | [5 empty] | 2014-06-25 08:56 | EDITOR
3180 | Sigurd Schelstraete | 202 | 3 | 22.3.8.2.2 | 2476 | 10 | T | N | 2476.1001 | 10 | 22.3.8.2.2 |  |  | Vinko Erceg |  |  | Clarify interpretation of N_TX for 80+80 | CSD values depend on N_TX (which determines the row in Table 22-10). Which value should be used for 80+80? For example, in Figure 22-9, a total of four transmit chains is shown. Per formula(22-20), the four signals would be labelled as (0,1), (0,2), (1,1) and (1,2), with the first number being the segment number and the second the antenna number. Is N_TX=4 or N_TX=2 in this case? Which row of Table 22-10 should be used? We propose that the correct intepretation of N_TX is the number of transmit chains per frequency segment and therefore N_TX=2 in the example of Figure 22-9. Using N_TX=4 in this case would result in 2x4 signals according to (22-20), with each of these signals requiring a transmit chain for its generation. |  | GEN | PHY (VHT) | Submission Required |  |  |  |  | 2014-06-25 08:56 | EDITOR
3181 | Sigurd Schelstraete | 202 | 3 | 22.3.8.2.2 | 2476 | 31 | T | N | 2476.3101 | 31 | 22.3.8.2.2 |  |  | Vinko Erceg |  |  | Use consistent naming for 80+80. Sometimes we use "noncontiguous transmission using two 80 MHz frequency segments". Other times, we use "noncontiguous 80+80 MHz VHT transmission" | Propose to use "noncontiguous 80+80 MHz VHT transmission" throughout |  | GEN | PHY (VHT) | Submission Required |  |  |  |  | 2014-06-25 08:56 | EDITOR
3182 | Sigurd Schelstraete | 202 | 3 | 22.3.8.2.2 | 2476 | 35 | T | N | 2476.3501 | 35 | 22.3.8.2.2 |  |  | Vinko Erceg |  |  | Clarify relationship between transmit chains and frequency segments | Replace "signal on frequency segment i_Seg in transmit chain i_TX" with "signal on transmit chain i_TX of frequency segment i_Seg". This is consistent with the interpretation of N_TX proposed in previous comment. |  | GEN | PHY (VHT) | [5 empty] | 2014-06-25 08:56 | EDITOR
3183 | Sigurd Schelstraete | 202 | 3 | 22.3.8.2.2 | 2477 | 20 | T | N | 2477.2 | 20 | 22.3.8.2.2 |  |  | Vinko Erceg |  |  | Add segment dependency | Replace "signal on transmit chain i_TX" with "signal on transmit chain i_TX of frequency segment i_Seg" |  | GEN | PHY (VHT) | [5 empty] | 2014-06-25 08:56 | EDITOR
3184 | Sigurd Schelstraete | 202 | 3 | 22.3.8.2.4 | 2478 | 12 | T | N | 2478.1201 | 12 | 22.3.8.2.4 |  |  | Vinko Erceg |  |  | Add segment and transmit chain dependency | Replace "The time domain waveform of the L-SIG field" with "The time domain waveform of the L-SIG field on transmit chain i_TX of frequency segment i_Seg" |  | GEN | PHY (VHT) | [5 empty] | 2014-06-25 08:56 | EDITOR
3178 | Sigurd Schelstraete | 202 | 3 | 22.3.7.4 | 2470 | 38 | T | N | 2470.3799 | 38 | 22.3.7.4 |  |  | Vinko Erceg |  |  | Clarify relationship between transmit chains and frequency segments | Change "the complex baseband signal of frequency segment i_Seg in transmit chain i_TX" with "the complex baseband signal on transmit chain i_TX of frequency segment i_Seg". The current wording suggests that both frequency segments appear on each transmit chain. |  | GEN | PHY (VHT) | [5 empty] | 2014-06-25 08:56 | EDITOR
3186 | Sigurd Schelstraete | 202 | 3 | 22.3.8.3.4 | 2484 | 57 | T | N | 2484.5701 | 57 | 22.3.8.3.4 |  |  | Vinko Erceg |  |  | Clarify relationship between transmit chains and frequency segments | Replace "signal on frequency segment i_Seg in transmit chain i_TX" with "signal on transmit chain i_TX of frequency segment i_Seg". |  | GEN | PHY (VHT) | [5 empty] | 2014-06-25 08:56 | EDITOR
3476 | Mark RISON | 202 | 3 | 22.3.19.5.2 | 2531 | 41 | T | Y | 2531.4099 | 41 | 22.3.19.5.2 |  |  | Vinko Erceg |  |  | This subclause starts "For the operating classes requiring CCA-Energy Detect (CCA-ED)" but examination of Annex E shows that the only operating classes requiring CCA-ED are in the 3G band and the maximum channel width is 20 MHz, so this subclause seems otiose at best and misleading at worst | Delete this subclause (also 23.3.19.6.2) |  | GEN | PHY (VHT) | [5 empty] | 2014-06-25 08:56 | EDITOR
3188 | Sigurd Schelstraete | 202 | 3 | 22.3.8.3.5 | 2487 | 52 | T | N | 2487.52 | 52 | 22.3.8.3.5 |  |  | Vinko Erceg |  |  | Clarify relationship between transmit chains and frequency segments | Replace "on frequency segment i_Seg in transmit chain i_TX" with "on transmit chain i_TX of frequency segment i_Seg". |  | GEN | PHY (VHT) | [5 empty] | 2014-06-25 08:56 | EDITOR
3192 | Sigurd Schelstraete | 202 | 3 | 22.3.10.5.2 | 2496 | 45 | T | N | 2496.45 | 45 | 22.3.10.5.2 |  |  | Vinko Erceg |  |  | N_ES is user dependent | Replace N_ES with N_ES,u |  | GEN | PHY (VHT) | [5 empty] | 2014-06-25 08:56 | EDITOR
3194 | Sigurd Schelstraete | 202 | 3 | 22.3.10.5.2 | 2496 | 58 | T | N | 2496.5801 | 58 | 22.3.10.5.2 |  |  | Vinko Erceg |  |  | Use correct terminology | "FEC input sequence" is not defined. Replace "FEC input sequence" with "BCC encoder parser output sequence" |  | GEN | PHY (VHT) | [5 empty] | 2014-06-25 08:56 | EDITOR
3196 | Sigurd Schelstraete | 202 | 3 | 22.3.10.9.1 | 2504 | 48 | T | N | 2504.48 | 48 | 22.3.10.9.1 |  |  | Vinko Erceg |  |  | The range of k in (22-84) is not correct for 160 MHz. (22-84) says that k =0, ..., N_SD-1 and l=0,1 for 160 MHz. This means there are 2 N_SD = 2x468 complex values per spatial stream and per symbol. | For 160 MHz, the range of k before segment deparsing is k=0, ..., N_SD/2 -1. Same comment on page 2509, lines 6 and 44 |  | GEN | PHY (VHT) | [5 empty] | 2014-06-25 08:56 | EDITOR
3197 | Sigurd Schelstraete | 202 | 3 | 22.3.10.11.1 | 2513 | 6 | T | N | 2513.0601 | 6 | 22.3.10.11.1 |  |  | Vinko Erceg |  |  | Add segment dependency | Replace "transmit chain i_TX" with "transmit chain i_TX of frequency segement i_Seg" |  | GEN | PHY (VHT) | [5 empty] | 2014-06-25 08:56 | EDITOR
3199 | Sigurd Schelstraete | 202 | 3 | 22.3.11.3 | 2517 | 5 | T | N | 2517.05 | 5 | 22.3.11.3 |  |  | Vinko Erceg |  |  | User correct terminology: replace NUM_USERS with N_user | As in comment |  | GEN | PHY (VHT) | Submission Required |  |  |  |  | 2014-06-25 08:56 | EDITOR
3200 | Sigurd Schelstraete | 202 | 3 | 22.3.21 | 2538 | 44 | T | N | 2538.4399 | 44 | 22.3.21 |  |  | Vinko Erceg |  |  | This statement should not be a note | Remove "NOTE -" |  | GEN | PHY (VHT) | [5 empty] | 2014-06-25 08:56 | EDITOR
3185 | Sigurd Schelstraete | 202 | 3 | 22.3.8.3.3 | 2480 | 51 | T | N | 2480.51 | 51 | 22.3.8.3.3 |  |  | Vinko Erceg |  |  | Add segment and transmit chain dependency | Replace "The time domain waveform for the VHT-SIG-A field in a VHT PPDU" with "The time domain waveform of the VHT-SIG-A field in a VHT PPDU on transmit chain i_TX of frequency segment i_Seg". [Editorial]: we propose to start this sentence on a new line, separate form the paragraph it currenlty belongs to. |  | GEN | PHY (VHT) | [5 empty] | 2014-06-25 08:56 | EDITOR

## PHY (TVWS)
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3311 | ron porat | 202 | 3 | 23.3.19.6.4 | 2608 | 47, 48 | T | Y | 2608.47 | 47 | 23.3.19.6.4 |  |  | Ron Porat |  |  | do not include TVHT_2W or TVHT_W+W in a subclause that refers to secondaryTVHT_2W channels because there are no secondaryTVHT_2W channels in TVHT_2W or TVHT_W+W. | Strike the terms TVHT_2W (TVHT_MODE_2C), TVHT_W+W (TVHT_MODE_2N) |  | GEN | PHY (TVWS) | [5 empty] | 2014-06-25 08:56 | EDITOR
3310 | ron porat | 202 | 3 | 23.3.19.6.4 | 2608 | 30 | T | Y | 2608.3 | 30 | 23.3.19.6.4 |  |  | Ron Porat |  |  | do not include TVHT_W in a subclause that refers to only non-primary channels because there is no non-primary channel in TVHT_W. | Strike the term TVHT_W and TVHT_MODE_1 |  | GEN | PHY (TVWS) | [5 empty] | 2014-06-25 08:56 | EDITOR
3276 | Jens Tingleff | 202 | 3 | 23.3.10.12 | 2597 | 46 | G | N | 2597.46 | 46 | 23.3.10.12 |  |  | Ron Porat |  |  | Not sure about this paragraph. I don't think that the CH_BANDWIDTH_IN_NON_HT parameter can have the values CBW... Since this does not occur in Tables 23-1 and 23-2. (In fact, CBW doesn't occur anywhere else in clause 23.) | Delete last para of 23.3.10.12 |  | GEN | PHY (TVWS) | [5 empty] | 2014-06-25 08:56 | EDITOR
3047 | Adrian Stephens | 202 | 3 | 23.1.2 | 2566 | 59 | G | Y | 2566.5901 | 59 | 23.1.2 |  |  | Ron Porat |  |  | " This function is supported by the physical layer convergence procedure (PLCP), which defines a method of mapping the PSDUs into a framing format (PPDU) suitable for sending and receiving PSDUs between two or more STAs using the associated PMD system" The PLCP and PMD distinction and the PMD interface have been removed. | Remove any mention of the PLCP and PMD from Clause 23. |  | GEN | PHY (TVWS) | Submission Required |  |  |  |  | 2014-06-25 08:56 | EDITOR
3046 | Adrian Stephens | 202 | 3 | 23.1.1 | 2565 | 31 | G | Y | 2565.3101 | 31 | 23.1.1 |  |  | Ron Porat |  |  | "The TVHT PHY is based on the VHT PHY as defined in 22.3 (VHT PHY), 22.4 (VHT PLME), 22.5 (Parameters for VHT-MCSs), and 22.6 and on Clause 18 (Orthogonal frequency division multiplexing (OFDM) PHY specification)." -- there is no 22.6 Ditto at line 37. | Replace 22.6 with some other reference, or delete it. |  | GEN | PHY (TVWS) | Submission Required |  |  |  |  | 2014-06-25 08:56 | EDITOR

## PHY (DMG)
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3260 | Qi Wang | 202 | 3 | 21.10.2.2 | 2423 | 45 | T | Y | 2423.45 | 45 | 21.10.2.2 |  |  | Eldad Perahia |  |  | [BRP, BRP-TX, BRP-RX usage] It seems the terms BRP-TX and BRP-RX have been defined to be able to refer to any .11ad frame that has TRN-T and TRN-R fields, but these terms (1) add confusion with the BRP frame, and (2) do not sufficiently capture that they can refer to any frame type/subtype with beam tracking. Note -- this is a general comment against all usages of BRP, BRP-TX and BRP-RX, including Section 21.10.2.2.3. | Few options: (1) do not use any special name and refer to these packets as "packets with beam training fields", (2) coin a new term such as "beam-training packet (BTP)" to be independent of BRP frames. |  | GEN | PHY (DMG) | Submission Required |  |  |  |  | 2014-06-25 09:07 | EDITOR
3259 | Qi Wang | 202 | 3 | 21.10.2.1 | 2423 | 28 | T | Y | 2423.28 | 28 | 21.10.2.1 |  |  | Eldad Perahia |  |  | Also indicate packet modulation for receive sector sweep. | Change the section title to "Sector-level sweep", and change the text to "Packets transmitted during transmit sector sweep are DMG control PHY packets. Packets transmitted during receive sector sweep are DMG control PHY or DMG SC PHY packets." |  | GEN | PHY (DMG) | [5 empty] | 2014-06-25 09:07 | EDITOR
3257 | Qi Wang | 202 | 3 | 21.6.3.2.3.3 | 2410 | 16 | T | Y | 2410.1599 | 16 | 21.6.3.2.3.3 |  |  | Eldad Perahia |  |  | [BRP, BRP-TX, BRP-RX usage] The minimum number of codewords N_Cwmin is applicable to any .11ad frame that has training fields appended and not just BRP frames (e.g., in beam tracking). It seems the terms BRP-TX and BRP-RX have been defined to be able to refer to any .11ad frame that has TRN-T and TRN-R fields, but these terms (1) add confusion with the BRP frame, and (2) do not sufficiently capture that they can refer to any frame type/subtype with beam tracking. Note -- this is a general comment against all usages of BRP, BRP-TX and BRP-RX, including Section 21.10.2. | With the current nomenclature, "BRP packet" on lines 16 and 24 needs to be replaced with something like "BRP-TX or BRP-RX packet", but this is still not ideal for the reasons explained. Few options: (1) do not use any special name and refer to these packets as "packets with beam training fields", (2) coin a new term such as "beam-training packet (BTP)" to be independent of BRP frames. |  | GEN | PHY (DMG) | Submission Required |  |  |  |  | 2014-06-25 09:07 | EDITOR
3254 | Qi Wang | 202 | 3 | 21.6.3.1.4 | 2408 | 49 | T | Y | 2408.49 | 49 | 21.6.3.1.4 |  |  | Eldad Perahia |  |  | Reference to N_CBPB in the entire Section 21.6.3.1.4 implies MCS-dependence, but header bytes always take two code blocks of 448 chip times. Also undefined are: symbols, guard symbols, and the N_GI parameter. | First sentence needs to be changed to something like "The header is transmitted using two Single-Carrier code blocks of 448 symbols with N_GI guard symbols."; ideal text should define what symbol is for single-carrier PHY (or remove it altogether and use chip time), have a constant such as N_SPCB (symbols per code block)defined as 448 and put in a table together with N_GI definition to 64, which is also missinng. |  | GEN | PHY (DMG) | Submission Required |  |  |  |  | 2014-06-25 09:07 | EDITOR
3251 | Qi Wang | 202 | 3 | 21.4.3.3.3 | 2391 | 14 | T | Y | 2391.1399 | 14 | 21.4.3.3.3 |  |  | Eldad Perahia |  |  | L_FDCW definition is missing; also the word "additional" is extra (6 bytes of data is added to header, but not additional). | (1) Change "L_FDCW is" to "L_FDCW=6 as", and (2) remove "additional". |  | GEN | PHY (DMG) | [5 empty] | 2014-06-25 09:07 | EDITOR
3250 | Qi Wang | 202 | 3 | 21.3.6.3 | 2384 | 5 | T | Y | 2384.05 | 5 | 21.3.6.3 |  |  | Eldad Perahia |  |  | Equations are not consistent with Figures 21-5 and 21-6 and the first paragraph of Section 21.3.6.3. | Change the last Gv512 in the equation on line 5 and the last Gu512 in the equation on line 8 to Gv128 (no waveform change). |  | GEN | PHY (DMG) | [5 empty] | 2014-06-25 09:07 | EDITOR
3249 | Qi Wang | 202 | 3 | 21.3.6.1 | 2382 | 54 | T | Y | 2382.54 | 54 | 21.3.6.1 |  |  | Eldad Perahia |  |  | Preamble is common to OFDM and SC PHY | Retitle the figure to "SC and OFDM preamble" |  | GEN | PHY (DMG) | [5 empty] | 2014-06-25 09:07 | EDITOR
3248 | Qi Wang | 202 | 3 | 21.6.3.1.4 | 2408 | 46 | T | Y | 2408.46 | 46 | 21.6.3.1.4 |  |  | Eldad Perahia |  |  | N_GI, which is also misspelled on the next page at line 12) is not defined. Similarly, "guard symbol" is undefined. In fact, "symbol" is undefined for DMG SC PHY. | Either define N_GI (I suspect intention was 64) and guard symbols, or eliminte them. |  | GEN | PHY (DMG) | Submission Required |  |  |  |  | 2014-06-25 09:07 | EDITOR
3247 | Qi Wang | 202 | 3 | 21.10.2.2.4 | 2425 | 44 | T | Y | 2425.4399 | 44 | 21.10.2.2.4 |  |  | Eldad Perahia |  |  | N_CBPS is not defined and used for single-carrier PHY. There is a reference to N_CBPS for low-power single-carrier, which probably is meant to be 1 for BPSK and 2 for QPSK modulations; the low-power single-carrier section (21.7) needs to define this parameter. | Remove the third column (with the header N_CBPS) from Table 21-23, and add proper definition of N_CBPS to the low-power single-carrier PHY section. |  | GEN | PHY (DMG) | Submission Required |  |  |  |  | 2014-06-25 09:07 | EDITOR
3246 | Qi Wang | 202 | 3 | 21.10.2.2.4 | 2425 | 32 | T | Y | 2425.3201 | 32 | 21.10.2.2.4 |  |  | Eldad Perahia |  |  | Minimum number of single carier codewords (NCWmin) defined in this section for "BRP packets" is meant to be applicable to any 802.11ad frame that carries AGC and training fields, including non-BRP frames (see Figures 9-81 and 9-82 for example). It seems "BRP packet" in this section loosely refers to any packet with AGC and traning fields attached - as evident by the first paragraph in the previous section 21.10.2.2.3, which throws the term "BRP packet". | Suggest to (1) remove the confusing term "BRP packet" altogether throughout the 802.11ad text, (2) use "BRP frame" only when referring to the management frame defined in Section 8.6.22.3 , and (3) use an appropriate term such as "beam training DMG packet" for all frames that carrry AGC and training fields, BRP frame or not. Sections 21.10.2.2.3 and 21.10.2.2.4 need to be revised at minimum |  | GEN | PHY (DMG) | Submission Required |  |  |  |  | 2014-06-25 09:07 | EDITOR
3245 | Qi Wang | 202 | 3 | 21.10.2.2.6 | 2427 | 49 | T | Y | 2427.49 | 49 | 21.10.2.2.6 |  |  | Eldad Perahia |  |  | The usage of TRN-R and TRN-T terms in the DMG PHY text is inconsistent. These terms used to refer to a block of 29 Golay-128 sequences (in the form of (CE,T,T,T,T) or (CE,R,R,R,R)), with multiple TRN-R or TRN-T fields (plural) appended to the end of a DMG frame (after AGC fields, another plural). All figures capturing DMG packet structures in Section 21 (Figures 21-2, 21-8, 21-10, and 21-12) still refer to the training field at the end of the packet as "TRN-R/T subfields" (plural), consistent with the original definitions of TRN-R and TRN-T fields in draft versions of .11ad. Sections 21.10.2.2.6 and 21.10.2.2.7 however define TRN-R and TRN-T as the group of 29 Golay-128 sequences above, with each DMG packet carrying a maximum of 1 TRN-R/T field (singular), and each TRN-R/T field including multiple "TRN-Unit"s. | Decide on one definition of TRN-R and TRN-T and remove inconsistencies. Commenter's opinion is to revert to original definition where a DMG packet is appended with multiple TRN-R/T fields (and in the process remove the ill-defined "TRN-Unit") for two reasons: (1) to stay consistent with AGC fields (multiple) preceding these fields, and (2) to possibly allow a mix of TRN-R and TRN-T fields appendded to DMG packets in future extensions. Otherwise, (1) all references to TRN-R and TRN-T (including the figures mentioned) need to be examined, and (2) two versions of "TRN-Unit" needs to be defined as the "TRN-Unit" in TRN-R is not the same as the "TRN-Unit" in TRN-T, for example TRN-R-Unit and TRN-T-Unit (defined respectively as (CE, R, R, R, R), and (CE, T, T, T, T)). |  | GEN | PHY (DMG) | Submission Required |  |  |  |  | 2014-06-25 09:07 | EDITOR
3242 | Qi Wang | 202 | 3 | 21.4.4.2.2 | 2393 | 18 | T | Y | 2393.1799 | 18 | 21.4.4.2.2 |  |  | Eldad Perahia |  |  | Common CCA requirement for all DMG PHY types | DMG CCA requirement is defined under the Control PHY section, but there should be one CCA requirement applicable to all DMG PHY types. |  | GEN | PHY (DMG) | Submission Required |  |  |  |  | 2014-06-25 09:07 | EDITOR

## Location
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3060 | Adrian Stephens | 202 | 3 | 6.3.58.3.2 | 338 | 34 | T | Y | 338.34 | 34 | 6.3.58.3.2 |  |  | Ganesh Venkatesan | 11-14/1014r0 |  | The (FINE)TIMINGMSMT primitives do not follow the usual 2 or 4 primitive model. There is no ".response" primitive. This brings into question where the values returned in the confirm come from. As shown in Figure 6-17, the .confirm is issues on receipt of an Ack. But where do the LCI Report, Location Civic Report, Fine Timing Measurement Parameter and Vendor Specific parameters come from? They are certainly not in the ACK. | Either: 1. Add a .response primitive, modify Figure 6-17 to show response primitive generating a management frame containing these parameters, or 2. Delete cited parameters from this primitive. |  | GEN | Location | Discuss |  |  |  |  | 2014-09-17 12:30 | GEN

## Gen Telecon - Oct
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3496 | Mark Hamilton | 202 | 3 | 8.4.2.6 | 713 | 40 | T | Y | 713.4 | 40 | 8.4.2.6 |  | V | Dorothy Stanley | 11-14/1041r3 |  | What does "prepared to deliver" mean? This occurs in 5 places. | Perhaps it needs to "stand" first? | REVISED (GEN: 2014-10-03) Incorporate the text changes for CID 3496 as detailed in 11-14/1041r3. | GEN | Gen Telecon - Oct | Ready for motion |  |  |  |  | 2014-10-03 22:46 | GEN
3058 | Adrian Stephens | 202 | 3 | 3.3 | 46 | 37 | G | Y | 46.37 | 37 | 3.3 |  | V | Dorothy Stanley | 11-14/1041r3 |  | Some of these definitions do not cite a regulatory domain. | Review the definitions in this subclause, and if any miss a regulatory qualifier "[xx]", move to 3.2. | REVISED (GEN: 2014-10-03 ) Proposed resolution: Incorporate the text changes for CID 3058 as detailed in 11-14/1041r3. | GEN | Gen Telecon - Oct | Ready for motion |  |  |  |  | 2014-10-03 22:50 | GEN
3057 | Adrian Stephens | 202 | 3 | 3.2 | 28 | 47 | T | Y | 28.47 | 47 | 3.2 |  | A | Dorothy Stanley | 11-14/1041r3 |  | Changes for CID 2443 should also be reflected in the definition of "extended rate physical layer (PHY) using OFDM modulation (ERP-OFDM):" | Change the definition of ERP-OFDM rom "A PHY operating under Clause 19 (Extended Rate PHY (ERP) specification) rules." to "A mode of operation of a PHY operating under Clause 19 (Extended Rate PHY (ERP) specification) rules, where MODULATION=ERP-OFDM. | ACCEPTED (GEN: 2014-10-03) | GEN | Gen Telecon - Oct | Ready for motion |  |  |  |  | 2014-10-03 22:47 | GEN

## Definitions
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3561 | David Hunter | 202 | 3 | 3.2 | 36 | 13 | E | Y | 36.13 | 13 | 3.2 | [5 empty] | The definition of nontransmitted BSSID is rather confused: "A basic service set identifier (BSSID) corresponding to one of the basic service sets (BSSs) when the multiple BSSID capability is supported, where the BSSID is not announced explicitly but can be derived from the information encoded in the transmitted Beacon frames." Also: the "BSSID" in the defined term needs to be defined. | Replace the definition of nontransmitted BSSID with: "nontransmitted basic service set (BSS) identifier (BSSID): When the multiple BSSID capability is supported, a BSSID that is not announced explicitly, but which corresponds to one of the BSSs and which can be derived from the information encoded in the transmitted Beacon frames." |  | GEN | Definitions | Submission Required | EDITOR: 2014-08-15 11:08:13Z - I spent some time trying to re-word this and couldn't come up with a good replacement. The proposal doesn't quite work for two reasons: 1. Starting a defintion with a conditional "When" is bad. 2. There is no antecedent for "the BSSs". Assigning to GEN. |  |  |  | 2014-10-14 13:27 | GEN
3528 | David Hunter | 202 | 3 | 3.1 | 8 | 23 | E | Y | 8.23 | 23 | 3.1 |  |  | Jon Rosdahl |  |  | Confusing use of sentence constructs: "mapping" is better used for the process than for the map itself; "and for which" is better replaced by "that is"; "reception" is better used for the whole MAC-PHY process (the definition above uses a more focused terminology); hopefully the history of the values are not actually part of their definition; etc. Rewrite is especially important because this definition will be in the IEEE dictionary. | Replace this defintion with: "A matrix that provides a space-time stream to transmit antenna map that is used by a transmitter to improve the received signal power or signal-to-noise ratio (SNR) at an intended receiver. |  | GEN | Definitions | Review | GEN: 2014-10-14 - Proposed Resolution: Revised: "A matrix determined using knowledge of the channel between a transmitter and an intended receiver that maps of space-time streams to transmit antennas with the goal of improving the signal power or signal-to-noise ratio (SNR) at the intended receiver." EDITOR: 2014-08-15 09:36:46Z - The map(ing) is determined using a knowledge of the channel. The rewrite loses this important aspect. However, the changes are not entirely editorial, so transferring to GEN with a proposed resolution of: "A matrix determined using knowledge of the channel between a transmitter and an intended receiver that maps of space-time streams to transmit antennas with the goal of improving the signal power or signal-to-noise ratio (SNR) at the intended receiver." |  |  |  | 2014-10-14 13:24 | GEN
3517 | Mark Hamilton | 202 | 3 | 3.1 | 9 | 20 | T | Y | 9.2 | 20 | 3.1 |  |  | Dorothy Stanley |  |  | "A quality-ofservice (QoS) BSS has one DCF and one HCF", no a QoS STA has one ... | Change "BSS" to "STA" |  | GEN | Definitions | [5 empty] | 2014-06-25 08:57 | EDITOR
3512 | Mark Hamilton | 202 | 3 | 3.1 | 12 | 25 | T | Y | 12.25 | 25 | 3.1 |  |  | Dorothy Stanley |  |  | Can there be more than one Portal? (See definition of infrastructure, and Annex Q, in particular) If no, how does an 802.11 LAN connect to more than one non-802.11 LAN (or VLANs, see Figure V-1)? (Is a bridge required?) If yes, how does the DS know how to route outbound traffic - does the DS perform 802.1Q functionality? Could the DS create a "bridge" between the non-802.11 LANs, independent of the WLAN, and can it result in loops, etc? | Clarify. Suggest that 802.11 assume there is only one portal (logically), so the DS can be well defined, and not require 802.1Q functions. Change the definition of "infrastrcture" and "WLAN system" to say "zero or one portal". Change Annex Q to match. Add a bridge in Figure V-1 to connect to the multiple VLANs. |  | GEN | Definitions | [5 empty] | 2014-06-25 08:57 | EDITOR
3493 | Mark Hamilton | 202 | 3 | 3.2 | 39 | 17 | T | Y | 39.17 | 17 | 3.2 |  |  | Dorothy Stanley |  |  | Why are RSNA and pre-RSNA devices referred to as "equipment" - or for that matter, why do we need to refer to the "device" and not the STA? | Change "equipment" to "STA" here, and in RSNA equipment definitions, and uses in clause 11. |  | GEN | Definitions | Submission Required |  |  |  |  | 2014-10-14 13:29 | GEN
3369 | Mark RISON | 202 | 3 | 3.2 | 24 | 34 | E | Y | 24.34 | 34 | 3.2 | [5 empty] | "active mode" has multiple meanings in the spec, but only one of them is given in the glossary | Add the other meanings to the glossary entry |  | GEN | Definitions | Submission Required | EDITOR: 2014-08-15 10:11:12Z - Creation of content is not an editorial function. Transferring to GEN. |  |  |  | 2014-10-14 13:21 | GEN
3353 | Mark RISON | 202 | 3 | 3.2 | 21 | 35 | T | Y | 21.35 | 35 | 3.2 |  |  | Dorothy Stanley |  |  | The definition for 20 MHz mask PPDU for "A Clause 18 PPDU transmitted by a VHT STA using the transmit spectral mask defined in Clause 22." does not specify the width | Add "20 MHz" as for the other bullets |  | GEN | Definitions | Submission Required |  |  |  |  | 2014-10-14 13:28 | GEN
3346 | Mark RISON | 202 | 3 | 3 | 26 | 1 | T | Y | 26.01 | 1 | 3 |  |  | Dorothy Stanley |  |  | The CBAP definition suggests EDCA is sometimes not used, but at least in an IBSS EDCA is always used, right? | Clarify |  | GEN | Definitions | Submission Required |  |  |  |  | 2014-06-25 08:57 | EDITOR
3282 | Guido Hiertz | 202 | 3 | 3.4 | 61 | 31 | T | N | 61.31 | 31 | 3.4 |  |  | Dorothy Stanley |  |  | Since its 2012 revision the 802.11 standard defines "WDS" as a *vernacular* term. The term WDS doesn't have any meaning anymore. This term is not specified at all and the standard does not explain how to establish, configure, or use a WDS. 802.11 should not list abbreviations just for fun. | Delete the term WDS from the standard. |  | GEN | Definitions | Submission Required |  |  |  |  | 2014-10-14 13:29 | GEN
3281 | Guido Hiertz | 202 | 3 | 3.1 | 20 | 50 | T | N | 20.5 | 50 | 3.1 |  |  | Dorothy Stanley |  |  | Since its 2012 revision the 802.11 standard defines "WDS" as a *vernacular* term. The term WDS doesn't have any meaning anymore. This term is not specified at all and the standard does not explain how to establish, configure, or use a WDS. The term occurs in the definitions and abbreviations section only. It's not used anywhere else. Thus, it is not needed and is no longer required. | Delete the term WDS from the standard. |  | GEN | Definitions | [5 empty] | 2014-06-25 08:57 | EDITOR
3056 | Adrian Stephens | 202 | 3 | 3.2 | 27 | 35 | E | N | 27.35 | 35 | 3.2 | [5 empty] | "dynamic frequency selection (DFS) owner (DO) station (STA)" - this definition is very similar to the previous one. | Merge the definitions or delete one of them. |  | GEN | Definitions | Submission Required | EDITOR: 2014-08-15 10:22:49Z - I don't see how to merge them as an editorial action. The DO definition starts "A STA", but it has a different meaning to a "DO STA", which is 5 GHz-specific. Most references are to a DO STA, but two are not, i.e. 1233.34, 1260.59. Transferring to GEN. |  |  |  | 2014-10-14 13:28 | GEN

## Clause 4
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3288 | Guido Hiertz | 202 | 3 | 4.7 | 109 | 48 | T | N | 109.48 | 48 | 4.7 |  |  | Carlos Cordeiro |  |  | The sentence "There can be no more than 254 STAs associated with a DMG AP or with a PCP." leaves the reader asking himself what about non-DMG APs? The sentence neither sets an upper limit nor does it explain any differences to non-DMG BSSs or where these differences would come from. | Delete the sentence "There can be no more than 254 STAs associated with a DMG AP or with a PCP." as it does not add any relevant information. |  | GEN | Clause 4 | [5 empty] | 2014-06-25 09:05 | EDITOR
3286 | Guido Hiertz | 202 | 3 | 4.3.19 | 91 | 8 | T | N | 91.08 | 8 | 4.3.19 |  |  | Carlos Cordeiro |  |  | This standard does not provide any justification for the following sentence "A DMG STA is not a mesh STA." | Delete the sentence "A DMG STA is not a mesh STA." |  | GEN | Clause 4 | [5 empty] | 2014-06-25 09:05 | EDITOR
3139 | Mitsuru Iwaoka | 202 | 3 | 4.3.13 | 77 | 38 | T | N | 77.38 | 38 | 4.3.13 |  |  | Ron Porat |  |  | The second sentence states that a TVHT STA supports all mandatory and optional features of a VHT STA as mandatory and optional features except channel widths. Though, subclause 23.2.2 specifies that an HT-mixed format PPDU (mandatory for a VHT STA) and an HT-greenfield format (optional for a VHT-STA) is not supported by the TVHT STA. | Modify the first two sentences of the 2nd paragraph of 4.3.13 as follows; -- A TVHT STA supports all mandatory features of a VHT STA as mandatory features except for an HT-mixed format and 20 MHz, 40 MHz, and 80 MHz channel widths. A TVHT STA supports all optional features of a VHT STA as optional features except for an HT-greenfield format, 160 MHz or 80+80 MHz channel widths and more than 4 spatial streams. |  | GEN | Clause 4 | [5 empty] | 2014-06-25 09:01 | EDITOR
3087 | Adrian Stephens | 202 | 3 | 4.10.3.3 | 119 | 46 | G | N | 119.46 | 46 | 4.10.3.3 |  |  | Dan Harkins |  |  | "The AKM confirmed in the Association Request" -- how can a request also contain a confirmation? | Because there is the potential for confusion, please expand on the fact that although this is a request from the viewpoint of the association protocol, is contains a confirmation from the viewpoint of the SAE key management protocol. |  | GEN | Clause 4 | Submission Required |  |  |  |  | 2014-06-25 08:58 | EDITOR