## Slide 1: IEEE 802.11TGai Closing Report
Date: 2014-7-18
Authors:
Name | Company | Address | Phone | email
Hiroshi MANO | Koden Techno Info K.K. | Fuji Blg 28 2F, 2-7-26 Kita-Aoyama, Minato-ku, Tokyo, 107-0061, Japan | +81-3-6890-0594 | mano@koden-ti.com hiroshi@manosan.org

## Slide 2: Abstract
This presentation is the closing report for the San Diego meeting of the IEEE 802.11 TGai.

## Slide 3: IEEE 802.11 FILS TGai – July 2014 San Diego meeting
Goals for the Meeting:
  Approve minutes of past meeting and teleconference
  Officer Election
  Comment resolution of WG LB for D2.0.
  Approve Timeline
  Approve Teleconference schedule
  Approve Plan for July

## Slide 4: Accomplishments TGai 1/2
1adhoc + 9 regular slots
Approve the minutes of past meetings
  Approve TGai Meeting Minutes (11-14/633r0) for the IEEE 802.11 Waikoloa meeting:
  Approve TGai teleconference meeting minutes Waikoloa to San Diego meeting (11-14/731r5)
  Approve meeting minutes San Diego Ad-Hoc meeting (11-14/884r0)

## Slide 5: Accomplishments TGai 2/2
1186 comments were received by WG LB201
  This week
    956 without resolution (all CIDs were assigned to champions )
    467 editorial
    489 Technical
  47 open
Approved Plan for Sep
Approved Time line
Approved Teleconference schedule

## Slide 6: Plan for Sep
Goals for the Meeting:
  Approve minutes of past meeting and teleconference
  Comment resolution of WG
  Approve to forward the draft to WG Recirc LB
  Approve Timeline
  Approve Teleconference schedule
  Approve Plan for Nov

## Slide 7: Time line of TGai
  PAR Approved, Modified, or Extended 2010-12-08
  WG Letter Ballots Initial / Recirc Mar14/Sep14/Jan15
  MEC Done Nov14
  Form Sponsor Ballot Pool / Reform Mar15
  IEEE-SA Sponsor Ballots Initial / Recirc Jul15/ Sep 15
  Final 802.11 WG Approval Nov 15
  final or Conditional 802 EC Approval Nov 15
  RevCom & Standards Board Final or Continuous Process Approval Mar 16
  ANSI Approved N/A

## Slide 8: Teleconference Schedule
Motion:
  Approve the following schedule of weekly teleconferences between July 29th to Sep 9th.
  Tuesdays 10:00 ET
  Duration 1Hour
  Using WEB-EX that will be provided by Task Group Chair
Approved by unanimous consent

## Slide 9: Reference
Motions
  14-1186r5 TGai-Motion-deck
TGai LB201 comments for Draft 2.0
  14-0565r18 TGai LB201 comments for Draft 2.0