## Slide 1: IEEE 802.11mc Closing Report for July 2014
Date: 2014-07-17
Authors:

## Slide 2: Abstract
This document contains the TGmc closing report for July 2014.

## Slide 3: Status
Began processing comments received in LB 202 – Second recirculation (779 comments, approximately 400 editorial)
  Approximately 60 CID resolutions approved; many more developed and ready for review. Also considered MDR comments (11-14-781).
Developed
  3GPP Liaison response https://mentor.ieee.org/802.11/dcn/14/11-14-0936-03-000m-liaison-response-followup-to-3gpp-tsg-ran-wg2.docx
  Changes for shwmp code point request, https://mentor.ieee.org/802.11/dcn/14/11-14-0848-01-000m-shwmp-text-changes-and-ana-allocation.docx
Agenda, includes motions and list of comment submissions ready to review
  in https://mentor.ieee.org/802.11/dcn/14/11-14-0747-06-000m-tgmc-july-2014-agenda.pptx

## Slide 4: LB 202 CID Assignees – more to be added
Gabor Bajko
Carlos Cordiero
Peter Ecclesine
Vinko Erceg
Matthew Fischer
Mark Hamilton
Dan Harkins
Brian Hart
VK Jones
Stephen McCann
Michael Montemurro
Eldad Perahia
Ron Porat
Mark Rison
Jon Rosdahl
Yongho Seok
Graham Smith
Dorothy Stanley
Adrian Stephens
Bo Sun
Fei Tong
Qi Wang
Menzo Wentink

## Slide 5: TGmc Plan of Record
Slide 5
20 July 2012 – 12 Sept 2012 – Call for Comment/Input
29-30 Aug 2012 – NesCom, SASB PAR Approval
Sept 2012 – Begin to process input
Sept 2012 – 11aa, 11ae integration
Jan – First WG Letter ballot - without 11ad
Dec 2012 – March/May 2013 – 11ad integration
Sept 2013 – Letter ballot on D2.0
Dec 2013 – May 2014 – 11ac, 11af integration – D3.0 in May 2014
July 2014 – Mandatory Draft Review
Jul - Aug 2014 – Form Sponsor Pool (45 days)
Nov 14 – Initial Sponsor Ballot
July 2015– WG/EC Final Approval
Dec 2015 – RevCom/SASB Approval
Notes: doc.: IEEE 802.11-10/0503r4
May 2010
        Michael Montemurro, Research in Motion
Page 5

## Slide 6: TGmc Plan of Record – changes
Slide 6
Form Sponsor Ballot Pool: Open Sept 15th, Close end Oct 2014 – Form Sponsor Pool (45 days); good for 6 months (end of April 2015)
Nov 2014 – D4.0 Recirculation, follow with D5.0 changed if needed, D6.0 unchanged
EC unconditional SB approval March 2015
Initial SB March 2015
Nov 2015/March 2016 – WG/EC Final Approval
March 2016 – RevCom/SASB Approval
Notes: doc.: IEEE 802.11-10/0503r4
May 2010
        Michael Montemurro, Research in Motion
Page 6

## Slide 7: Teleconferences
Conference Calls 10am Eastern (2 hours)
  August 1, 8, 15, 22, 29
  September 5

## Slide 8: Motion – shwmp liaison text changes and ANA allocation
  Move to approve the text changes in https://mentor.ieee.org/802.11/dcn/14/11-14-0848-01-000m-shwmp-text-changes-and-ana-allocation.docx
  And approve the request that the ANA administer the Active Path Selection Protocol Identifier values, and assign the reserved shwmp value.
Moved: Stephen McCann
Seconded: Guido Hiertz
Result: 29-0-2 Passes

## Slide 9: Motion – 3GPP liaison
  Approve the liaison statement in https://mentor.ieee.org/802.11/dcn/14/11-14-0936-03-000m-liaison-response-followup-to-3gpp-tsg-ran-wg2.docx
  And request that the WG chair send the liaison as indicated, with editorial license.
Moved: Youhan Kim
Seconded: Matthew Fischer
Result: 30-7-7 Passes

## Slide 10: Next Steps
Complete comment resolution of comments received from WGLB on P802.11REVmc D3.0