## Slide 1: IEEE 802.11ah Closing Report for July 2014
Date: 2014-07-18
Authors:

## Slide 2: Abstract
This presentation is the closing report for the San Diego meeting of the IEEE 802.11 TGah.

## Slide 3: Activity in TGah
Letter Ballot 203 for Draft 2.0 closed July 7th
  1214 comments received
Total 366 comments with 12 submissions addressed in this week)
  848 comments unresolved after July F2F meeting
  LB203 comment spreadsheet: 11-14/79r3
Instructed the editor to generate Draft 2.1

## Slide 4: Going forward
Continue to address LB203 comments and start Initial WG Recirculation Letter Ballot in September

## Slide 5: Teleconference
July 29 (Tuesday), 8PM ET for 2 hour
August 5 (Tuesday), 8PM ET for 2 hour
August 12 (Tuesday), 8PM ET for 2 hour
August 19 (Tuesday), 8PM ET for 2 hour
August 26 (Tuesday), 8PM ET for 2 hour
September 2 (Tuesday), 8PM ET for 2 hour
September 9 (Tuesday), 8PM ET for 2 hour

## Slide 6: TGah Timeline – No change
Internal Task Group Ballot : May 2013
Initial Letter Ballot : September 2013
Initial Recirculation Letter Ballot : September 2014
Initial Sponsor Ballot : February 2015
Initial Recirculation Sponsor Ballot : November 2015
EC Approval : January 2016
Revcom Approval : March 2016