## Slide 1: IEEE 802.11mc Closing Report for November 2014
Date: 2014-11-06
Authors:

## Slide 2: Abstract
This document contains the TGmc closing report for November 2014.

## Slide 3: Status
Continued processing comments received in LB 202 – Second recirculation (779 comments, approximately 400 editorial)
  600+ CID resolutions approved; 75 editorial and 100 technical remain
  Approved element ID extensions proposal, see 11-13-1353-03
  Approved text changes and liaison related to 3GPP reference liaison, see 11-13-1421 and 11-14-1520
  Approved resolutions to ISO comments on 11ac and 11af, see 11-13-0123r7
Agenda, includes motions
  https://mentor.ieee.org/802.11/dcn/14/11-14-1321-07-000m-tgmc-agenda-november-2014.pptx

## Slide 4: TGmc Plan of Record - modified
Slide 4
20 July 2012 – 12 Sept 2012 – Call for Comment/Input
29-30 Aug 2012 – NesCom, SASB PAR Approval
Sept 2012 – Begin to process CC input, 11aa, 11ae integration
Dec 2012 – March/May 2013 – 11ad integration
Jan 2013 – First WG Letter ballot - without 11ad – on D1.0
Sept 2013 – Letter ballot on D2.0
Dec 2013 – May 2014 – 11ac, 11af integration – D3.0 in May 2014
July 2014 – Mandatory Draft Review
Jan 2015 – D4.0 Recirculation, goal to follow with D5.0 unchanged (was Nov 2014)
Form Sponsor Pool: Open Dec 15th or so, close Feb 2015 – (min 45 days); good for 6 months (end of July 2015)
EC conditional SB approval March 2015
*new* - plan ad-hoc comment resolution meeting July 2015
Nov 2015/March 2016 – WG/EC Final Approval
March 2016 – RevCom/SASB Approval
Notes: doc.: IEEE 802.11-10/0503r4
May 2010
        Michael Montemurro, Research in Motion
Page 4

## Slide 5: Teleconferences and next steps
Conference Calls 10am Eastern (2 hours)
  Nov 21, Dec 5, 12, 19 and Jan 9
January 2015
  Complete comment resolution of comments received from WGLB on P802.11REVmc D3.0 and approve letter ballot recirculation on D4.0