## Slide 1: IEEE 802 JTC1 SC closing report (Jan 2015)
Date: 2015-1-16
Authors:

## Slide 2: Abstract
Closing report for IEEE 802 JTC1 SC for January 2015 in Atlanta

## Slide 3: The SC did not have a great deal of work this week and only one session was required
Reviewed status of PSDO pipeline
  A number of ballots close before March plenary
Noted lack of recent new proposal activity in SC6
  No activity on WLAN Cloud or Optimization technology in WLAN
Agreed to invite SC6 participants to join 802.11m Sponsor Ballot pool
  Motion for 802.11 later
Agreed that IEEE 802 should be consulted on the proposed revised PSDO agreement
  Motion being considered by IEEE 802 EC
Noted next SC6 meeting is in Belgium in May

## Slide 4: IEEE 802 has pushed ten standards completely through the PSDO ratification process …
IEEE 802 standard | 60 day pre-ballot | 5 month FDIS ballot
802.11 | Passed (2012) | Passed in 2012
802.1X | Passed (2013) | Passed (21 Oct 2013)
802.1AE | Passed (2013) | Passed (21 Oct 2013)
802.1AB | Passed (May 2013) | Passed (18 Dec 2013)
802.1AR | Passed (May 2013) | Passed (18 Dec 2013)
802.1AS | Passed (May 2013) | Passed (18 Dec 2013)
802.3 | Passed (2013) | Passed (16 Feb 2014)
802.11aa | Passed (Feb 2013) | Passed (28 Jan 2014)
802.11ad | Passed (Feb 2013) | Passed (28 Jan 2014)

## Slide 5: … and IEEE 802 has ten standards in the pipeline for ratification under the PSDO process
IEEE 802 standard | 60 day pre-ballot | 5 month FDIS ballot
802.11ac | Passed (Sep 2014) | Waiting for start
802.11af | Passed (Sep 2014) | Waiting for start
802.1AEbw | Passed (Jan 2014) | Closes 1 Feb 2015
802.1AEbn | Passed (Jan 2014) | Closes 1 Feb 2015
802.1Xbx | Starting soon | -
802.1Q-Rev | Closes 13 March 2015 | -
802 | Passed (Oct 2014) | Starting soon
802.3.1 | Passed (Oct 2014) | Closes 19 June 2015
802.22 | Passed (May 2014) | Closes 15 Feb 2015
802.22a | Waiting for 802.22 | -
802.1 WG
802.3 WG
Comment resolution responsibility in March 2015
802.22 WG
802.1 WG

## Slide 6: The SC will focus in Berlin on PSDO responses and SC6 meeting prep
Process any comments on IEEE submissions to SC6 under PSDO process
  802.1AEbw, 802.1AEbn, 802.22
Report on status of teleconferences in SC6/WG7 on
  Virtual AP
  Optimization technology in WLAN
Prepare for SC6 meeting in Belgium in May
  Appoint delegation
  Prepare WG updates
  Review agenda

## Slide 7: The SC approved a motion for a liaison inviting participation in 802.11mc Sponsor Ballot
Motion
  The IEEE 802 JTC1 SC recommends to the IEEE 802.11 WG that the IEEE 802.11 WG Chair be authorised to send a liaison to ISO/IEC JTC1/SC6:
    Noting that the Sponsor Ballot Pool for IEEE 802.11mc has opened
    Explaining how participants in SC6 or participants in SC6 NBs may join the Sponsor Ballot Pool
  Result: Approved 9/0/0
The IEEE 802.11 WG Chair subsequently asked the SC Chair to actually write the liaison 
The following page contains proposed text…

## Slide 8: The SC Chair has drafted text for the agreed liaison to SC6
Proposed liaison text (from IEEE 802.11 WG Chair)
  Dear DY Kim
  The IEEE 802.11 WG values the ongoing review by SC6 National Bodies of IEEE 802.11 standards and amendments.
  Indeed, any comments received from SC6 National Bodies are processed by the IEEE 802.11 WG in the exactly the same way as comments from members of the official ballot pools.
  However, individuals associated with SC6 National Bodies also have an ongoing opportunity to participate directly in the balloting process by joining various IEEE 802.11 Sponsor Ballot pools.
  …

## Slide 9: The SC Chair has drafted text for the agreed liaison to SC6
Proposed liaison text (from IEEE 802.11 WG Chair)
  …
  The Sponsor Ballot pool for the next IEEE 802.11 revision standard has just opened, and provides an excellent opportunity for interested individuals to participate directly in the balloting process
  If any individuals associated with SC6 National Bodies are interested in the joining the Sponsor Ballot pool for the next IEEE 802.11 revision then they are invited to follow the instructions at http://standards.ieee.org/develop/balloting.html, or contact me for assistance
  Your sincerely …

## Slide 10: The WG is asked to approve the text of a liaison to SC6
Motion
  The IEEE 802.11 WG approves the IEEE 802.11 WG Chair liaising the text on slides 8 & 9 (with appropriate editorial changes) of 802.11-15/0194r0 to ISO/IEC JTC1/SC6
  Moved: Myles
  Seconded: