## Slide 1: IEEE 802.11TGai Closing Report
Date: 2015-3-12
Authors:
Name | Company | Address | Phone | email
Hiroshi MANO | Koden Techno Info K.K. | Fuji Blg 28 2F, 2-7-26 Kita-Aoyama, Minato-ku, Tokyo, 107-0061, Japan | +81-3-6890-0594 | mano@koden-ti.com hiroshi@manosan.org

## Slide 2: Abstract
This presentation is the closing report for the Berlin meeting of the IEEE 802.11 TGai.

## Slide 3: IEEE 802.11 FILS TGai – March 2015 Berlin
Goals for the Meeting:
  Approve minutes of past meeting and teleconference
  Comment resolution of WG Recirc LB209
  Approve to forward the draft to WG Recirc LB
  Approve Timeline
  Approve Teleconference schedule
  Approve Plan for May

## Slide 4: Accomplishments TGai 1/2
11 regular slots
Approved TGai Meeting Minutes for the IEEE 802.11 Atlanta meeting:
  January 2015 Atlanta Session Minutes 11-15/0246r1
Approved TGai teleconference meeting minutes of Atlanta to Berlin meeting.
  January-March Teleconferences Minutes 11-15/0390r0

## Slide 5: Accomplishments TGai 2/2
Received 491 comments byWG LB209
  Resolved 471 comments
  17 open comments
Approved the TGai MDR Report
  11-15/0248r1
Approved Plan for May
Approved Time line
Approved Teleconference schedule

## Slide 6: Plan for May
Goals for the Meeting:
  Approve minutes of past meeting and teleconference
  Comment resolution of WG recirc LB
  Approve to forward the draft to Sponsor Ballots
  Approve Timeline
  Approve Teleconference schedule
  Approve Plan for July

## Slide 7: Time line of TGai (No change)
  PAR Approved, Modified, or Extended 2010-12-08
  WG Letter Ballots Initial / Recirc Mar14/Sep14/Jan15/Mar15
  MEC Done Nov14
  Form Sponsor Ballot Pool / Reform Jan15
  IEEE-SA Sponsor Ballots Initial / Recirc Jul15/ Sep 15
  Final 802.11 WG Approval Nov 15
  final or Conditional 802 EC Approval Nov 15
  RevCom & Standards Board Final or Continuous Process Approval Mar 16
  ANSI Approved N/A
Approved by unanimous consent

## Slide 8: Teleconference Schedule
Motion:
  Approve the following schedule of weekly teleconferences between Mar 24th to May 19th.
  Tuesdays 10:00 ET
  Duration 1.0Hour
  Using WEB-EX that will be provided by Task Group Chair

## Slide 9: Reference
Motions (11-13-1186r23)
  https://mentor.ieee.org/802.11/dcn/13/11-13-1186-23-00ai-tgai-motion-deck.pptx
TGai LB209 comments for Draft 4.0 (11-15/0281r14)
  https://mentor.ieee.org/802.11/dcn/15/11-15-0281-14-00ai-tbai-lb209-comments-on-draft-d4-0.xlsx