## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-15/665r16
Venue Date: | December 2015
First Author: | Jon Rosdahl, CSR Technologies Inc. A Qualcomm Company
Subject: | REVmc Sponsor Ballot Comments
Full Date: | 2015-12-08
Author(s): | Name(s) | Jon Rosdahl
| Company | CSR Technologies Inc. - a Qualcomm Company
| Address | 10871 N 570 W, Highland, UT 84003
| Phone: | +1-801-492-4023
| email: | jrosdahl@ieee.org
Abstract:
This document contains the GenAdHoc comments received for the REVmc Sponsor ballot for P802.11REVmc.
As comment resolutions are approved, comments are moved to the editor for implementation and this file then will shrink.

## Revision History
Revision | Date | Description
0 | 2015-05-13 | Initial version with Sponsor Ballot comments for Gen AdHoc - status as of Tuesday
1 | 2015-05-14 | Status as of Thursday end of Vancouver Mtg
2 | 2015-06-17 | Status as of Wednesday
3 | 2015-06-19 | Updated after Face to Face in Hillsboro, Oregon - Motion on Thursday resolved 3 Tabs - "Vancouver A", "May-June Telecon" and "Hillsboro-A" tabs
4 | 2015-06-30 | Update after the June 26 Telecon and updated with items from May that were previously missed.
5 | 2015-08-20 | Update after the July Plenary and Aug F2F BRC - premotion
6 | 2015-08-22 | Update after the August F2F BRC - post motions -- only outstanding GEN CIDs remain
7 | 2015-08-25 | Missed updates from Aug 14 telecon -- CIDs updated to match.
8 | 2015-09-01 | Update through August 28th Telecon
9 | 2015-09-14 | Added proposed resolutions from 11-15/1010r7 -- also updated some assignments - proposed resolutions for discussion during the 802 Wireless Interim in Bangkok
10 | 2015-09-10 | Comment groups changed to reflect major assignments (other than for Vinko - PHY) Updated to the status as of Tuesday Sept 15, 2015
11 | 2015-10-02 | Update through the Oct 2 2015 telecon (also includes Bangkok and Sept 25th updates).
12 | 2015-10-09 | Update through the Oct 9 2015 Telecon (Ready for motion Tabs: "GEN Bangkok B; GEN Telecon Sept-Oct"
13 | 2015-10-16 | Updated through the Oct 14-16 F2F in Cambridge - (Ready for Motion Tabs: "GEN Cambridge F2F-2)
14 | 2015-11-14 | Updates include the Oct 30 telecon which resolved the GEN Cambridge F2F-2 tab and moved that set of CIDs to Editor Also the proposed resolutions from the 802 Plenary in Dallas Session are updated in this revision. Note potential rejection of CIDs that are marked "submission needed" has been included in the Ad hoc notes as a default response for CIDs that do not have information provided in a timely manner
15 | 2015-12-07 | Comment update through Monday 7 Dec F2F
16 | 2015-12-08 | Comment update through Tuesday 8 Dec F2F BRC - Also updated all open CIDs with default resolutions.
17
18
19
20
21
22
23
24
25
26
27
28
29

## GEN Telecon Oct-Nov
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
6819 | RISON, Mark | 1000 | 4 | 3.2 |  |  | T | Y | 21 | 31 | 3.2 |  | V | Mark Rison | 11-15/0762r12 |  | "individually addressed bufferable unit (BU): An individually addressed MSDU, individually addressed A-MSDU (HT STAs only) or individually addressed bufferable MMPDU." needs to say "DMG STAs" as for bufferable unit (BU). | As it says in the comment | REVISED (GEN: 2015-10-30) Make the changes shown under "Proposed changes" for CIDs 6788, 6819, 6298, 6561 in https://mentor.ieee.org/802.11/dcn/15/11-15-0762-12-000m-resolutions-for-some-comments-on-11mc-d4-0-sbmc1.docx, which effect the requested change. | GEN | GEN Telecon Oct-Nov | Ready for motion | GEN: 2015-09-09 <email-adrian-11-15/1010r7> Proposed Resolution: Revised. Replace “HT STAs only” with “HT STAs and DMG STAs only”. GEN: 2015-09-03 Mark Rison Request assignment see 11-15/0762 |  |  |  | 2015-11-03 15:53 | GEN
6788 | RISON, Mark | 1000 | 4 |  |  |  | T | Y |  |  |  |  | V | Mark Rison | 11-15/762r12 |  | "bufferable" v. "buffered" -- there is confusion in these terms. Probably move to "buffered" for most cases | As it says in the comment | REVISED (GEN: 2015-10-30 ) - Make the changes shown under "Proposed changes" for CIDs 6788, 6819, 6298, 6561 in https://mentor.ieee.org/802.11/dcn/15/11-15-0762-12-000m-resolutions-for-some-comments-on-11mc-d4-0-sbmc1.docx. | GEN | GEN Telecon Oct-Nov | Ready for motion | MAC: 2015-10-26 23:01:33Z 9.8.6.1.1 Note while CID 6467is listed in the same section of the submission as the other 4 CIDs, it is not resolved at this point in the document, but is included here to remind people that it exists and is similar to the other CIDs 9.8.6.2 Review Proposed changes 9.8.6.3 Concern for “informally” be deleted – it was 9.8.6.4 Discussion on the direction of the resolutions. 9.8.6.5 ACTION ITEM #8: Mark HAMILTON: Move 6788 and 6298 to GEN 9.8.6.6 If others have feedback please send to Mark R. EDITOR: 2015-09-14 03:55:48Z - Transferring to MAC. This is part of a bigger discussion. The comment is marked technical. EDITOR: 2015-05-28 14:22:24Z - The comment fails to identify a specific issue to be addressed. It fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. As far as I can tell there is a necessary difference between these terms, and I don't see obvious confustion. |  |  |  | 2015-11-03 15:52 | GEN
6561 | RISON, Mark | 1000 | 4 |  |  |  | T | Y |  |  |  |  | V | Mark Rison | 11-15/762r12 |  | MMPDUs are not MPDUs and hence are not "frame"s | Change all places in the document which refer to "frame"s incorrectly to refer to "MMDU"s instead. As a first step, check all "<Management frame subtype> frame"s and change most if not all to "<Management frame subtype> MMDU"s | REVISED (GEN: 2015-10-30) Make the changes shown under "Proposed changes" for CIDs 6788, 6819, 6298, 6561 in https://mentor.ieee.org/802.11/dcn/15/11-15-0762-12-000m-resolutions-for-some-comments-on-11mc-d4-0-sbmc1.docx. These clarify that MMPDUs are often loosely referred to as frames. | GEN | GEN Telecon Oct-Nov | Ready for motion |  |  |  |  | 2015-11-03 15:57 | GEN
6323 | RISON, Mark | 1000 | 4 | 3.2 | 43 | 10 | T | Y | 43.1 | 10 | 3.2 |  | V | Mark Rison | 11-15/0762r12 |  | The definition of "STSL" appears to preclude a direct link between STAs in a PBSS | Add "or PCP" after "AP" at 43.12 | REVISED (GEN: 2015-10-28) Make the changes the changes shown under "Proposed changes" for CID 6323 and 6459 in https://mentor.ieee.org/802.11/dcn/15/11-15-0762-12-000m-resolutions-for-some-comments-on-11mc-d4-0-sbmc1.docx. These restrict the scope of STSLs to direct links in an infrastructure BSS, that have not been set up using TDLS, and obsolete such links. | GEN | GEN Telecon Oct-Nov | Ready for motion | GEN: 2015-09-09 Adrian to ask Solomon GEN: 2015-09-09 Mark R requests please assign to me (in 15/0762) |  |  |  | 2015-11-03 17:44 | GEN
6298 | RISON, Mark | 1000 | 4 |  |  |  | G | Y |  |  |  |  | V | Mark Rison | 11-15/762r12 |  | People keep confusing MPDUs, MSDUs, MMPDUs, A-MSDUs and A-MPDUs | Say something somewhere like "An MSDU or MMPDU is transmitted in one or more MPDUs. An MSDU may be carried in an A-MSDU. An A-MSDU is transmitted in one MPDU. An MSDU or MMPDU may be carried (in an MPDU) in an A-MPDU." | REVISED (GEN: 2015-10-30) Make the changes shown under "Proposed changes" for CIDs 6788, 6819, 6298, 6561 in https://mentor.ieee.org/802.11/dcn/15/11-15-0762-12-000m-resolutions-for-some-comments-on-11mc-d4-0-sbmc1.docx. These clarify that MMPDUs are often loosely referred to as frames. | GEN | GEN Telecon Oct-Nov | Ready for motion | MAC: 2015-10-26 23:01:33Z 9.8.6.1.1 Note while CID 6467is listed in the same section of the submission as the other 4 CIDs, it is not resolved at this point in the document, but is included here to remind people that it exists and is similar to the other CIDs 9.8.6.2 Review Proposed changes 9.8.6.3 Concern for “informally” be deleted – it was 9.8.6.4 Discussion on the direction of the resolutions. 9.8.6.5 ACTION ITEM #8: Mark HAMILTON: Move 6788 and 6298 to GEN 9.8.6.6 If others have feedback please send to Mark R. |  |  |  | 2015-11-03 15:58 | GEN

## GEN Dallas - A
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
5942 | Schelstraete, Sigurd | 1000 | 4 | 23.3.8.2 | 2612 | 52 | T | N | 2612.52 | 52 | 23.3.8.2 |  | V | Sigurd Schelstraete | 11-15/1270 |  | Change "Non-TVHT portion of VHT format preamble" to "Non-TVHT portion of VHT format in TVWS bands preamble" | See comment | REVISED (GEN: 2015-11-10 22:09:37Z) at 2612.52 change “VHT Format” to “TVHT Format” | GEN | GEN Dallas - A | Ready for motion |  |  |  |  | 2015-11-14 22:05 | GEN
5020 | Seok, Yongho | 1000 | 4 | 22.3.10.6 | 2522 | 42 | T | Y | 2522.4199 | 42 | 22.3.10.6 |  | A | Hongyuan Zhang | 11-15/1384r0 |  | In Line 42, there is a minor error on the definition of K'. k' = k - N_Block*N_ES*s 's' should be 'S' (capital S). | Replace "N_Block*N_ES*s" with "N_Block*N_ES*S" in Line 42. | ACCEPTED (GEN: 2015-11-10 22:31:31Z) | GEN | GEN Dallas - A | Ready for motion |  |  |  |  | 2015-11-10 22:32 | GEN
5951 | Schelstraete, Sigurd | 1000 | 4 | 23.3.12 | 2620 | 17 | T | N | 2620.1699 | 17 | 23.3.12 |  | V | Sigurd Schelstraete | 11-15/1270r1 |  | VHT-SIG-A should be TVHT-SIG-A | Correct | REVISED (GEN: 2015-11-10 22:22:37Z) incorporate the changes in 11-15/1270r1 for CID 5950, 5951, 5952 | GEN | GEN Dallas - A | Ready for motion |  |  |  |  | 2015-11-14 22:15 | GEN
5950 | Schelstraete, Sigurd | 1000 | 4 | 23.3.12 | 2620 | 12 | T | N | 2620.1201 | 12 | 23.3.12 |  | V | Sigurd Schelstraete | 11-15/1270r1 |  | VHT-LTF should be TVHT-LTF | Correct | REVISED (GEN: 2015-11-10 22:22:29Z) incorporate the changes in 11-15/1270r1 for CID 5950, 5951, 5952 | GEN | GEN Dallas - A | Ready for motion |  |  |  |  | 2015-11-14 22:12 | GEN
5949 | Schelstraete, Sigurd | 1000 | 4 | 23.3.10.11 | 2618 | 45 | T | N | 2618.45 | 45 | 23.3.10.11 |  | V | Sigurd Schelstraete | 11-15/1270r1 |  | "For TVHT transmissions, the signal (...) shall be as specified in Equation (22-96)." Need to add the substitutions given in Table 23-8 + Table 23-12. | See comment | REVISED (GEN: 2015-11-10 22:20:55Z) - incorporate the changes in 11-15/1270r1 for CID 5949 | GEN | GEN Dallas - A | Ready for motion |  |  |  |  | 2015-11-10 22:22 | GEN
5946 | Schelstraete, Sigurd | 1000 | 4 | 23.8.3 | 2614 | 1 | T | N | 2614.01 | 1 | 23.8.3 |  | V | Sigurd Schelstraete | 11-15/1270r1 |  | Change "TVHT portion of VHT format preamble" to "TVHT portion of VHT format in TVWS bands preamble" | See comment | REVISED (GEN: 2015-11-10 22:16:41Z) change "VHT format" to "TVHT format" | GEN | GEN Dallas - A | Ready for motion |  |  |  |  | 2015-11-14 22:09 | GEN
5945 | Schelstraete, Sigurd | 1000 | 4 | 23.3.8.2.2 | 2613 | 15 | T | N | 2613.1499 | 15 | 23.3.8.2.2 |  | V | Sigurd Schelstraete | 11-15/1270r1 |  | In additon to the substitution of Gamma, Delta_F in (22-20) should also be replaced with the value in Table 23-8. Similar comment for 23.3.8.2.3, 23.3.8.2.4, 23.3.8.3.4, 23.3.8.3.5 | Correct. | REVISED (GEN: 2015-11-10 22:14:57Z) incorporate the changes in 11-15/1270r1 [https://mentor.ieee.org/802.11/dcn/15/11-15-1270-01-000m-tvht-comment-resolutions.docx] for CID 5945. | GEN | GEN Dallas - A | Ready for motion |  |  |  |  | 2015-11-15 01:04 | GEN
5953 | Schelstraete, Sigurd | 1000 | 4 | 23.5 | 2631 | 24 | T | N | 2631.24 | 24 | 23.5 |  | V | Sigurd Schelstraete | 11-15/1270r1 |  | Note is probably not correct. The number of symbols (740) is obtained by dividing 20msec by 27usec. However, 27usec is the short GI symbol length for 6/7 MHz, while the note uses 32 MHz for calculation of the number of bytes (20.25 usec sumbol duration). Also, this calculation makes no provisions for the preamble length. | Correct | REVISED (GEN: 2015-11-10 22:28:51Z) at 2631.22 change "1 065 600" to "1 401 120" and at 2631.25 change "740" to "973" | GEN | GEN Dallas - A | Ready for motion |  |  |  |  | 2015-11-14 22:17 | GEN
5943 | Schelstraete, Sigurd | 1000 | 4 | 23.3.38.2.1 | 2612 | 57 | T | N | 2612.5701 | 57 | 23.3.38.2.1 |  | V | Sigurd Schelstraete | 11-15/1270r0 |  | Change VHT-SIG-A to TVHT-SIG-A (also on line 59) | See comment | REVISED (GEN: 2015-11-10 22:12:55Z) at 2612.57 and 2612.59 change “VHT-SIG-A” to “TVHT-SIG-A” | GEN | GEN Dallas - A | Ready for motion |  |  |  |  | 2015-11-12 12:49 | GEN
5971 | Ecclesine, Peter | 1000 | 4 | E.1 | 3337 | 63 | T | Y | 3337.6299 | 63 | E.1 |  | V | Peter Ecclesine | 11-15/828r1 |  | It is hard to manage a mixed BSS where some STAs only understand a regional Operating Class table, and others understand the Global Operating Class Table. It is difficult to signal measurement requests and responses for operating classes in more than one table. Add an explicit requirement that multi-domain capable STAs support Table E-4 Global Operating Classes going forward, and that use of non-Global Operating Classes may be deprecated in future revisions of the standard. | Add an explicit requirement that multi-domain capable STAs support Table E-4 Global Operating Classes going forward, and that use of non-Global Operating Classes may be deprecated in future revisions of the standard. | REVISED (GEN: 2015-11-11 20:31:45Z) Incorporate Changes in 11-15/828r3 <https://mentor.ieee.org/802.11/dcn/15/11-15-0828-03-000m-sb0-ecclesine-resolutions.docx> under CID 5971. | GEN | GEN Dallas - A | Ready for motion | GEN: 2015-11-11 20:24:49Z - Move to MAC to group CIDs 5969, 5970 and 5972 together. GEN: 2015-09-08 <e-mail> - Revised. At 1320.50 insert: 9.21.3a Operation with multiple country elements Where a BSS includes STAs that do not support global operating classes, then all requests and Action frames to those STAs that convey elements containing operating classes shall use nonglobal operating class values. Where a BSS includes STAs that support global operating classes, then all requests and Action frames to those STAs that convey elements containing operating classes shall use global operating class values. When dot11OperatingClassesImplemented is true, the following statements apply: — When dot11OperatingClassesRequired is false, or where operating classes domain information is not present in a STA, that STA is not required to change its operation in response to an element or element-specific Information field that contains an operating class. — When dot11OperatingClassesRequired is true and the STA supports some global operating classes, or where global operating classes domain information is present in a STA, the STA shall indicate current operating class information in the Country element and Supported Operating Classes element using the country string for the global operating classes, except that a VHT STA may omit, from the Country element, any Operating Triplet field for an Operating Class for which the Channel spacing (MHz) column indicates 80 MHz or wider and for which the Behavior limits set column in the applicable table in Annex E contains only a blank entry or either or both of “80+” and “UseEirpForVHTTxPowEnv.” At 2730.54, insert: “OC8 Operation with multiple country elements 9.21.3a OC1:O Yes  No  N/A  ==================== GEN: 2015-05-11 23:37:03Z Possible Resolution: At 3337.63 insert "A STA for which dot11MultiDomainCapabilityActivated is true shall support Table E-4 (Global operating classes). Use of non-Global Operating Classes is deprecated and may be removed in a future revision of the standard." And insert Table E-1 classes 16, 17, 18 into Table E-4. |  |  |  | 2015-11-14 22:55 | GEN
5938 | Schelstraete, Sigurd | 1000 | 4 | 22.3.11.2 | 2539 | 42 | T | N | 2539.4199 | 42 | 22.3.11.2 |  | V | Bo Sun | 11-15/1317r1 |  | "The beamformee decides the tone grouping value to be used in the beamforming feedback matrix V. A STA with dot11VHTSUBeamformerOptionImplemented equal to true shall support all tone grouping values and Codebook Information values." The first sentence is a transmit requirement, while the second is a receive requirement. | Clarify | REVISED (GEN: 2015-11-10 23:02:06Z) at 2539.42 replace "A STA with dot11VHTSUBeamformerOptionImplemented equal to true shall support all tone grouping values and Codebook Information values." with "A beamformer shall support all tone grouping values and Codebook Information values." Delete the Note at 2539.46 | GEN | GEN Dallas - A | Ready for motion |  |  |  |  | 2015-11-10 23:06 | GEN
5928 | Schelstraete, Sigurd | 1000 | 4 | 22.3.8.3.4 | 2506 | 6 | T | N | 2506.0601 | 6 | 22.3.8.3.4 |  | A | Hongyuan Zhang | 11-15/1384r0 |  | Replace "The frequency domain sequence used to construct the VHT-STF field in a 20 MHz transmission is identical to the L-STF field" with "The frequency domain sequence used to construct the VHT-STF field in a 20 MHz transmission is identical to the HT-STF field". This makes it consistent with (22-29). (and yes, HT-STF is identical to L-STF) | See comment | ACCEPTED (GEN: 2015-11-10 22:52:46Z) | GEN | GEN Dallas - A | Ready for motion |  |  |  |  | 2015-11-10 22:53 | GEN
5925 | Schelstraete, Sigurd | 1000 | 4 | 22.3.7.4 | 2496 | 24 | T | N | 2496.24 | 24 | 22.3.7.4 |  | V | Hongyuan Zhang | 11-15/1384r1 |  | Add the parameter M_u, which also appears in (22-13). Reference Table 22-6 for the meaning of M_u. | See comment | REVISED (GEN: 2015-11-10 22:50:54Z) - Add the following Sentence at P2496.24 "Mu is defined in Table 22-6 (Frequently used parameters)." | GEN | GEN Dallas - A | Ready for motion |  |  |  |  | 2015-11-14 22:32 | GEN
5921 | Schelstraete, Sigurd | 1000 | 4 | 22.3.6 | 2486 | 41 | T | N | 2486.4099 | 41 | 22.3.6 |  | J | Hongyuan Zhang | 11-15/1384r0 |  | Table 22-5 is called "Timing-releated constants". Many of the values in the table are not timing-related at all. | Use more appropriate caption for table | REJECTED (GEN: 2015-11-10 22:45:16Z) the same caption has been used for the same table in 11a and HT | GEN | GEN Dallas - A | Ready for motion |  |  |  |  | 2015-11-10 22:46 | GEN
5225 | Adachi, Tomoko | 1000 | 4 | 8.4.2.157.2 | 1039 |  | E | N | 1039 |  | 8.4.2.157.2 |  | V | Hongyuan Zhang | 11-15/1384r0 |  | It is not clearly explained that an MU beamformer/beamformee is also an SU beamformer/beamformee. The descriptions of Beamformee STS Capability and Number of Sounding Dimensions in Table 8-240 each says "If SU beamformee capable, ... . Otherwise, reserved." and a reader may misdeem that when a STA is a MU beamformer/beamformee, these fields are not used. It is written that when the MU Beamformee Capable in VHT Capabilities element is set to 1, then the SU Beamformee Capable is also set to 1, but it is just saying about the settings. | Add a note to Table 8-240 and state that a MU beamformer/beamformee is a SU beamformer/beamformee. | REVISED (GEN: 2015-11-10 22:43:38Z) in Clause 8.4: On P1040L48 (CID #5225): change the encoding field of “Beamformee STS Capability” to “If the SU Beamformee Capable field is set to 1…”, and On P1040L60 (CID #5225) change the encoding field of “Number of Sounding Dimensions” to be “If the SU Beamformer Capable field is set to 1…” | GEN | GEN Dallas - A | Ready for motion |  |  |  |  | 2015-11-14 22:30 | GEN
5067 | Stephens, Adrian | 1000 | 4 | 18.3.2.5 | 2238 | 64 | G | Y | 2238.6399 | 64 | 18.3.2.5 |  | V | Adrian Stephens | 11-15/1207r5 |  | "The normative specifications of generating the transmitted waveforms shall utilize the rectangular pulse shape" Who is responsible for actioning this "shall". I claim, as written, it is a "shall" directed at the authors of this specification. | Rewrite so that the normative requirements on an implementer are clear, and avoid creating normative specifications for the authors of this documents. | REVISED (GEN: 2015-11-09 21:14:40Z) At cited location replace “The normative specifications of generating the transmitted waveforms shall utilize the rectangular pulse shape.” with “This standard describes transmitted waveforms using a rectangular pulse shape.” Also change the following sentence to read: “In a typical implementation, a higher TTR is used in order to smooth the transitions between consecutive subsections.” | GEN | GEN Dallas - A | Ready for motion | GEN: 2015-11-08 Revised. At cited location replace “The normative specifications of generating the transmitted waveforms shall utilize the rectangular pulse shape.” with “This standard describes transmitted waveforms using a rectangular pulse shape.” Also change the following sentence to read: “In a typical implementation, a higher TTR is used in order to smooth the transitions between consecutive subsections.” |  |  |  | 2015-11-09 21:17 | GEN
5058 | Stephens, Adrian | 1000 | 4 |  | 2561 | 50 | T | Y | 2561.5 | 50 | 22.3.20 |  | A | Hongyuan Zhang | 11-15/138r0 |  | "If signal loss occurs during reception prior to completion of the PSDU reception, the error condition PHYRXEND.indication(CarrierLost) primitive shall be reported to the MAC. After waiting for the end of the PSDU as determined by Equation (22-106), the PHY shall set the PHY-CCA.indication(IDLE) primitive and return to the RX IDLE state." 1. "shall be reported" is not how primitives are referred to. 2. "shall set the xyz primitive" is meaningless | Change to: "If signal loss occurs during reception prior to completion of the PSDU reception, the error condition shall be reported to the MAC using a PHYRXEND.indication(CarrierLost) primitive. After waiting for the intended end of the PSDU as determined by Equation (22-106), the PHY shall generate a PHYCCA.indication(IDLE) primitive and return to RX IDLE state." (This mirrors the language used in 2376.34). | ACCEPTED (GEN: 2015-11-10 22:34:48Z) Note to editor to insert dash in PHY-RXEND | GEN | GEN Dallas - A | Ready for motion |  |  |  |  | 2015-11-10 22:36 | GEN
5944 | Schelstraete, Sigurd | 1000 | 4 | 23.3.8.2.2 | 2613 | 14 | T | N | 2613.1399 | 14 | 23.3.8.2.2 |  | V | Sigurd Schelstraete | 11-15/1270r1 |  | Wrong reference. Reference to (20-20) should probably be (22-20) | Correct | REVISED (GEN: 2015-11-10 22:12:44Z) at 2613.14 change reference "20-20" to "22-20" | GEN | GEN Dallas - A | Ready for motion | GEN: 2015-09-15 Cited Sentence: The time domain representation of the signal on BCU in transmit chain is specified in Equation (20-20) 20-20 = The frequency sequences are shown in Equation (20-19) and Equation (20-20). 22-20 = The time domain representation of the signal on frequency segment oftransmit chain shall be as specified in Equation (22-20). |  |  |  | 2015-11-14 22:06 | GEN
6294 | RISON, Mark | 1000 | 4 | 17.2.3.6 | 2202 | 35 | T | Y | 2202.3501 | 35 | 17.2.3.6 |  | V | Adrian Stephens | 11-15/1207r5 |  | It says "if the rounding performed by the Ceil() operation took less than 8/11 or a 1 if the rounding took more than or equal to 8/11." -- what does it mean for rounding to take more or less than a number? | Clarify (perhaps it refers to the difference between the rounded number and the original number?). Also replace Ceil() with the floor symbols | REVISED (GEN: 2015-11-12 20:49:49Z) Replace "the service field (b7) bit shall indicate a 0 if the rounding performed by the Ceil() operation took less than 8/11 or a 1 if the rounding took more than or equal to 8/11." with: "the service field (b7) bit is 0 if (Length - (number of octets x 8/11)) < 8/11 and is 1 otherwise." | GEN | GEN Dallas - A | Ready for motion | GEN: 2015-11-08 Revised. Replace “the service field (b7) bit shall indicate a 0 if the rounding performed by the Ceil() operation took less than 8/11 or a 1 if the rounding took more than or equal to 8/11.” with: “the length extension bit is 0 if ((number of octets x 8/11)-Length) < 8/11 and is 1 otherwise.” |  |  |  | 2015-11-15 | GEN
6802 | RISON, Mark | 1000 | 4 |  |  |  | T | Y |  |  |  |  | V | Mark Rison | 11-15/762r14 |  | In clauses other than clause 8, it is not clear that reserved fields are ignored on reception (some honourable exceptions, e.g. in Table 21-11--Control PHY header fields and 18.3.4.4 Parity (P), Reserved (R), and SIGNAL TAIL fields). | Make the behaviour at the receiver clear for reserved bits in all clauses | REVISED (GEN: 2015-11-11 21:13:26Z) Incorporate the changes in 11-15/762r13 < https://mentor.ieee.org/802.11/dcn/15/11-15-0762-14-000m-resolutions-for-some-comments-on-11mc-d4-0-sbmc1.docx> for CID 6802 and 6803 | GEN | GEN Dallas - A | Ready for motion |  |  |  |  | 2015-11-11 21:16 | GEN
6678 | RISON, Mark | 1000 | 4 | 22 |  |  | T | Y | 2455 | 1 | 22 |  | V | Bo Sun | 11-15/1317r1 |  | "Table 22-2--- PPDU format as a function of CH_BANDWIDTH parameter" only talks of CBW_n even for HT formats, but the CBW for HT formats is HT_CBW_n. | Use the correct terminology | REVISED (GEN: 2015-11-10 23:48:17Z) - at 2539.38 change "CBW20" to "CBW20 when FORMAT is VHT; HT_CBW20 when FORMAT is HT_MF or HT_GF" At 2539.45 change "CBW40" to "CBW40 when FORMAT is VHT; HT_CBW40 when FORMAT is HT_MF or HT_GF" | GEN | GEN Dallas - A | Ready for motion |  |  |  |  | 2015-11-11 00:11 | GEN
6607 | RISON, Mark | 1000 | 4 | 17 |  |  | T | Y | 2198 | 1 | 17 |  | J | Adrian Stephens | 11-15/1207r5 |  | Some bits of the spec state/imply "HR/DSSS/short" is included in "HR/DSSS", others exclude it | Be consistent | REJECTED (GEN: 2015-11-09 21:06:56Z)The comment asserts an inconsistency, but does not back this up with references. The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | GEN | GEN Dallas - A | Ready for motion | GEN: 2015-11-08 -- Rejected. The comment asserts an inconsistency, but does not back this up with references. The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-11-09 21:13 | GEN
6466 | RISON, Mark | 1000 | 4 | 20.5 | 2385 | 9 | E | Y | 2385.0901 | 9 | 20.5 |  | V | Adrian Stephens | 11-15/1207r8 |  | "NOTE---The 400 ns GI rate values are rounded to 1 decimal place." applies to more than the table this is in | Promote the NOTE to the main text of the referenced subclause, and add it to Clauses 21 to 23 too | REVISED (GEN: 2015-11-12 20:56:27Z) At 2384.55, delete "(see NOTE)". At 2385.09 delete the last table row containing the NOTE. At 2384.13 insert a new para: "In the MCS parameter tables that follow, data rates for a 400 ns GI are rounded to 1 decimal place." At 2631.47 insert a new para: "In the MCS parameter tables that follow, data rates for a 400 ns GI are rounded to 1 decimal place." | GEN | GEN Dallas - A | Ready for motion | GEN: 2015-11-08 - Revised. At 2384.55, delete “(see NOTE)”. At 2385.09 delete the last table row containing the NOTE. At 2384.13 insert a new para: “In the MCS parameter tables that follow, data rates for a 400 ns GI are rounded to 1 decimal place.” EDITOR: 2015-08-13 15:58:46Z - I don't know why this ended up transferred to the editor. It still needs technical consideration of which tables are rounded to 1 decimal place for short GI. Transferring back to GEN, but please see input below on editorially correct instructions for the Clause 20 change. A possible change in Clause 20 is as follows: Delete "NOTE--" paragraph at 2385.09 and "(see NOTE)" at 2384.55. At 2384.13 insert a new paragraph: "In the tables that follow in this subclause rate values shown for a 400 ns GI are rounded to 1 decimal place." EDITOR: 2015-06-23 15:51:06Z - There are two issues here: 1) which of the tables are rounded to 1 decimal place; 2) how to indicate this in the text. As the indication of which tables are rounded is not an editorial function, transferring to GEN for resolution. A resolution had been written (and edited) as follows: REVISED (EDITOR_A: 2015-05-03 11:38:59Z) - In clause 20, this sentence is moved to the paragraph just before Table 20-27. In clause 20, this sentence is moved to the paragraph just before Table 22-30. This sentence is not required in clauses 21 and 23 because there are no 400 ns GI options there. EDITOR_A: 2015-05-03 11:44:59Z |  | EDITOR: 2015-08-13 16:02:20Z- Rework will be required. EDITOR: 2015-06-23 15:49:23Z- Reviewed. Assigning to GEN for resolution. The draft was edited according to this resolution: REVISED (EDITOR_A: 2015-05-03 11:38:59Z) - In clause 20, this sentence is moved to the paragraph just before Table 20-27. In clause 20, this sentence is moved to the paragraph just before Table 22-30. This sentence is not required in clauses 21 and 23 because there are no 400 ns GI options there. EDITOR_A: 2015-05-03 11:45:01Z |  | 2015-11-15 00:34 | GEN
6465 | RISON, Mark | 1000 | 4 | 20.5 | 2384 | 40 | T | Y | 2384.3999 | 40 | 20.5 |  | V | Adrian Stephens | 11-15/1207r8 |  | "NOTE---Support of 400 ns GI is optional on transmit and receive." applies to more than the table this is in | Promote the NOTE to the main text of the referenced subclause, and add it to Clauses 21 to 23 too | REVISED (GEN: 2015-11-12 20:52:57Z) At 2569.32, 2573.33, and 2577.33 after "400 ns GI" insert "(See NOTE)" At 2569.52, 2573.53, and 2577.53 insert a new last table row, merged, containing: "NOTE—Support of 400 ns GI is optional on transmit and receive" In reply to the commenter, The NOTE applies specifically to this table because it is the only Clause 20 MCS table that includes “mandatory” in its caption, and reminds the reader that support of short GI is not mandatory. Change to Clauses 21 and 23 are not necessary, because these do not label their MCS tables with “mandatory”. | GEN | GEN Dallas - A | Ready for motion | GEN: 2015-11-08 Revised At 2569.32, 2573.33, and 2577.33 after “400 ns GI” insert “(See NOTE)” At 2569.52, 2573.53, and 2577.53 insert a new last table row, merged, containing: “NOTE—Support of 400 ns GI is optional on transmit and receive” In reply to the comment The NOTE applies specifically to this table because it is the only Clause 20 MCS table that includes “mandatory” in its caption, and reminds the reader that support of short GI is not mandatory. Change to Clauses 21 and 23 are not necessary, because these do not label their MCS tables with “mandatory”. |  |  |  | 2015-11-15 00:29 | GEN
6423 | RISON, Mark | 1000 | 4 | 16.4.5.5 | 2191 | 27 | T | Y | 2191.27 | 27 | 16.4.5.5 |  | V | Vinko Erceg | 11-15/1400r0 |  | What is "B90/2pi"? Any is it formatted correctly? | Clarify, and change the pi to a symbol; should the 90 be superscript or something? | REVISED (GEN: 2015-11-11 21:03:58Z) Revise Change: "Channel 14 is unique. The Japanese standard ARIB RCR-STD 33 (5.0) [B7] states that B90/2pi normalized to the ‘transmission speed of modulation signal’ shall be > 10." To: "Channel 14 is unique. The Japanese standard ARIB RCR-STD 33 (5.0) [B7] states that B90/2pi normalized to the ‘transmission speed of modulation signal’ shall be > 10, where B90 is the 90% occupied channel bandwidth." Editor – please change “pi” to symbol. (two locations) | GEN | GEN Dallas - A | Ready for motion |  |  |  |  | 2015-11-14 23:08 | GEN
5952 | Schelstraete, Sigurd | 1000 | 4 | 23.3.12 | 2620 | 19 | T | N | 2620.1899 | 19 | 23.3.12 |  | V | Sigurd Schelstraete | 11-15/1270r1 |  | VHT-SIG-B should be TVHT-SIG-B | Correct | REVISED (GEN: 2015-11-10 22:22:45Z) incorporate the changes in 11-15/1270r1 for CID 5950, 5951, 5952 | GEN | GEN Dallas - A | Ready for motion |  |  |  |  | 2015-11-10 22:24 | GEN
6296 | RISON, Mark | 1000 | 4 | 22.3.8.3.3 | 2502 | 1 | T | Y | 2502.01 | 1 | 22.3.8.3.3 |  | V | Bo Sun | 11-15/1317r1 |  | If STBC is set in VHT-SIG-A then GID needs to indicate SU and the SU NSTS needs to be even -- there should at least be a NOTE to that effect | Add a NOTE to that effect | REVISED (GEN: 2015-11-10 23:26:01Z) at 2503.12 insert "(see 22.3.10.9.4 Space-time block coding)" after "Set to 1 if space time block coding ". | GEN | GEN Dallas - A | Ready for motion |  |  |  |  | 2015-11-10 23:29 | GEN
6803 | RISON, Mark | 1000 | 4 |  |  |  | T | Y |  |  |  |  | V | Mark Rison | 11-15/762r14 |  | Sometimes the value of reserved bits is not specified in the PHY. | Specify them | REVISED (GEN: 2015-11-11 21:13:26Z) Incorporate the changes in 11-15/762r13 < https://mentor.ieee.org/802.11/dcn/15/11-15-0762-14-000m-resolutions-for-some-comments-on-11mc-d4-0-sbmc1.docx> for CID 6802 and 6803 | GEN | GEN Dallas - A | Ready for motion | have provided a list of candidate locations to Adrian |  |  |  | 2015-11-11 21:27 | GEN
6281 | RISON, Mark | 1000 | 4 | 18.3.12 | 2269 | 55 | T | Y | 2269.55 | 55 | 18.3.12 |  | A | Vinko Erceg | 11-15/1400r0 |  | It says "Once the SIGNAL is detected, without any errors detected by a single parity (even), FEC decode shall be initiated and the PHY SERVICE fields and data shall be received, decoded (a Viterbi decoder is recommended), and checked by ITU-T CRC-32. If the FCS by the ITU-T CRC-32 check fails, the PHY receiver shall return to the RX IDLE state, as depicted in Figure 18-19 (Receive PHY)." but ITU CRC-32 is not defined or referenced. Is any of this blurb necessary anyway (it's not in any other PHY)? | Delete the cited text | ACCEPTED (GEN: 2015-11-11 20:52:09Z) | GEN | GEN Dallas - A | Ready for motion |  |  |  |  | 2015-11-11 20:53 | GEN
6268 | RISON, Mark | 1000 | 4 | 20.3.16 | 2360 | 26 | T | Y | 2360.26 | 26 | 20.3.16 |  | V | Adrian Stephens | 11-15/1207r5 |  | It says "The OFDM PHY" | Change to "The HT PHY" | REVISED (GEN: 2015-11-09 21:17:01Z) At 2360.25 delete subclause 20.3.16 (Transmit and receive in-band and out-of-band spurious transmissions) in its entirety. | GEN | GEN Dallas - A | Ready for motion | GEN: 2015-11-08 Revised. At 2360.25 delete subclause 20.3.16 (Transmit and receive in-band and out-of-band spurious transmissions) in its entirety. |  |  |  | 2015-11-09 21:19 | GEN
6267 | RISON, Mark | 1000 | 4 | 22.3.18.3 | 2553 | 21 | T | Y | 2553.21 | 21 | 22.3.18.3 |  | V | Bo Sun | 11-15/1317 |  | It says "For a conforming OFDM PHY" | Change to "For a VHT PHY" | REVISED (GEN: 2015-11-10 23:20:58Z) Change "For a conforming OFDM PHY, the" to "The" at the locations: 2367.42, 2368.6, 2552.12, 2553.23 | GEN | GEN Dallas - A | Ready for motion |  |  |  |  | 2015-11-14 21:35 | GEN
6265 | RISON, Mark | 1000 | 4 | 22.3.18.2 | 2552 | 10 | T | Y | 2552.1001 | 10 | 22.3.18.2 |  | V | Bo Sun | 11-15/1317r1 |  | It says "For a conforming OFDM PHY" | Change to "For a VHT PHY" | REVISED (GEN: 2015-11-10 23:19:47Z) Change "For a conforming OFDM PHY, the" to "The" at the locations: 2367.42, 2368.6, 2552.12, 2553.23 | GEN | GEN Dallas - A | Ready for motion |  |  |  |  | 2015-11-10 23:21 | GEN
6241 | RISON, Mark | 1000 | 4 | 18.3.5.7 | 2247 | 52 | T | Y | 2247.52 | 52 | 18.3.5.7 |  | A | Vinko Erceg | 11-15/1400r0 |  | In Equation (18-16) for j in the second permutation for data interleaving, the closing parenthesis should be moved from immediately after the "mod s" to immediately before, matching Equation (22-78) | As it says in the comment | ACCEPTED (GEN: 2015-11-11 20:47:23Z) | GEN | GEN Dallas - A | Ready for motion |  |  |  |  | 2015-11-11 20:48 | GEN
6225 | RISON, Mark | 1000 | 4 | 21.4.3.3.3 | 2413 | 18 | T | Y | 2413.1799 | 18 | 21.4.3.3.3 |  | V | Vinko Erceg | 11-15/1400r0 |  | The exposition is unclear and the example is poor (makes the middle and last codeword the same size) | Change the exposition to: 1) LCWD=128 is the maximal number of data bits in each LDPC codeword. LHDR=5 is the length of the header (including HCS) in octets. LFDCW=6 is the length of the additional data in the first LDPC codeword in octets. 2) The total (header and additional data) number of bits in the first LDPC codeword is LDPFCW=(LHDR+LFDCW)x8=88. 3) The number of LDPC codewords is NCW=<blah>. 4) The number of bits in the second and any subsequent LDPC codeword (if present), except the last, is LDPCW=<blah>. 5) The number of bits in the last LDPC codeword is LDPLCW=<blah>. Change the example to: NOTE---For example, if Length = 128, then NCW=<blah>=7, LDPCW=163 and LDPLCW=161. In the first LDPC block the 88 bits of LDPFCW consist of 40 header+HCS bits along with 48 bits of data. | REVISED (GEN: 2015-11-11 20:43:32Z) Revise. Change the exposition to: 1) LCWD=168 is the maximal number of data bits in each LDPC codeword. LHDR=5 is the length of the header (including HCS) in octets. LFDCW=6 is the length of the additional data in the first LDPC codeword in octets. 2) The total (header and additional data) number of bits in the first LDPC codeword is LDPFCW=(LHDR+LFDCW)x8=88. 3) The number of LDPC codewords is NCW=<blah>. 4) The number of bits in the second and any subsequent LDPC codeword (if present), except the last, is LDPCW=<blah>. 5) The number of bits in the last LDPC codeword is LDPLCW=<blah>. Change the example to: NOTE---For example, if Length = 128, then NCW=<blah>=7, LDPCW=163 and LDPLCW=161. In the first LDPC block the 88 bits of LDPFCW consist of 40 header+HCS bits along with 48 bits of data. | GEN | GEN Dallas - A | Ready for motion |  |  |  |  | 2015-11-11 20:47 | GEN
6222 | RISON, Mark | 1000 | 4 | 23.3.9.2 | 2616 | 12 | T | Y | 2616.1201 | 12 | 23.3.9.2 |  | A | Sigurd Schelstraete | 11-15/1240r1 |  | "Transmission of HT PPDU with any number of antennas is not supported" is ambiguous (does it merely mean you can't have a million antennas?) and irrelevant (there are plenty of other things which are not supported) and confusing (it's in a subclause titled "Transmission of HT format PPDUs with more than four antennas") | Delete the referenced subclause | ACCEPTED (GEN: 2015-11-10 22:19:19Z) | GEN | GEN Dallas - A | Ready for motion | Similar to 6782 |  |  |  | 2015-11-10 22:20 | GEN
6409 | RISON, Mark | 1000 | 4 |  |  |  | T | Y |  |  |  |  | J | Vinko Erceg | 11-15/1400r0 |  | The various PHYs have various energy detect thresholds, even for the same PPDU formats | Align the thresholds for various PHYs (or at least make it clear which threshold is to be used when a PHY includes the waveforms of an earlier PHY, at least for things like preamble detect) | REJECTED (GEN: 2015-11-11 21:00:39Z) Reason for rejection: In each PHY ED levels are clearly specified. Those ED levels should be used for corresponding PPDUs. | GEN | GEN Dallas - A | Ready for motion |  |  |  |  | 2015-11-11 21:02 | GEN

## GEN Dec F2F BRC - Piscataway
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
6623 | RISON, Mark | 1000 | 4 | 1.5 |  |  | T | Y | 3 | 1 | 1.5 |  | V | Jon Rosdahl |  |  | If you do insist on using exp(), define it in Subclause 1.5 | As it says in the comment | REVISED (GEN: 2015-12-07 16:57:45Z) - Add to 1.5 "exp (x) is e to the power x, where e is the base of natural logarithms.", where x and e are italicised. | GEN | GEN Dec F2F BRC - Piscataway | Ready for motion | GEN: 2015-09-17 - REVISED Add to 1.5 "exp (x) is e to the power x, where e is the base of natural logarithms.", where x and e are italicised. GEN: 2015-09-03 <e-mail Mark R> what more detail is needed? The sentence would be something like "exp (x) is e to the power x, where e is the base of natural logarithms.", where x and e are italicised GEN: 2015-08-28 - Proposed resolution: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-12-07 17:06 | GEN
6416 | RISON, Mark | 1000 | 4 | 3.2 | 41 | 19 | T | Y | 41.19 | 19 | 3.2 |  | V | Jon Rosdahl |  |  | The definition of RSNA key management seems incomplete. 4WH, GTK, PeerKey, FT4WH and FT auth are included, but what about IGTK, SAE, etc.? | Add everything, or make the definition more generic | REVISED (GEN: 2015-12-07 17:01:42Z) at 41.19 add ‘authenticated mesh peering exchange, Mesh Group Key Handshake, ’ between ‘Group Key Handshake,’ and ‘and the Peer Key Handshake’ | GEN | GEN Dec F2F BRC - Piscataway | Ready for motion | GEN: 2015-09-18 Revised; at 41.19 add ‘AMPE, Mesh Group Key Handshake, ’ between ‘Group Key Handshake,’ and ‘and the Peer Key Handshake’ Notes: The IGTK is a key (like the GTK) and both of them are handled with the Group Key Handshake, which is mentioned in the location you specified. SAE is sort of like 802.1X, it does authentication and key establishment. After SAE one does the 4WHS just like one does after 802.1X (unless doing mesh, then it does AMPE and the Mesh Group Key Handshake). |  |  |  | 2015-12-07 17:06 | GEN
6266 | RISON, Mark | 1000 | 4 | 22.3.18.3 | 2553 | 20 | T | Y | 2553.2 | 20 | 22.3.18.3 |  | A | Adrian Stephens | 11-15/1207r10 |  | It says "compliant with the OFDM PHY" | Change to "compliant with the VHT PHY" | ACCEPTED (GEN: 2015-12-07) | GEN | GEN Dec F2F BRC - Piscataway | Ready for motion | GEN: 2015-11-11- Assign CID 6464 and 6266 to Adrian for resolving in a consistent way with 6260 and 6262. |  |  |  | 2015-12-08 04:03 | GEN
6264 | RISON, Mark | 1000 | 4 | 22.3.18.2 | 2552 | 9 | T | Y | 2552.0901 | 9 | 22.3.18.2 |  | A | Adrian Stephens | 11-15/1207r10 |  | It says "compliant with the OFDM PHY" | Change to "compliant with the VHT PHY" | ACCEPTED (GEN: 2015-12-07) | GEN | GEN Dec F2F BRC - Piscataway | Ready for motion |  |  |  |  | 2015-12-08 04:03 | GEN
6263 | RISON, Mark | 1000 | 4 | 20.3.20.3 | 2368 | 5 | T | Y | 2368.05 | 5 | 20.3.20.3 |  | V | Adrian Stephens | 11-15/1207r10 |  | It says "For a conforming OFDM PHY" | Change to "For an HT PHY" | REVISED (GEN: 2015-12-07) Change "For a conforming OFDM PHY, the" to "The" at the cited location. (Note to editor: this is a subset of the changes in CID 6257) | GEN | GEN Dec F2F BRC - Piscataway | Ready for motion | GEN: 2015-11-08 Accepted (Note to editor, these changes are a subset of the changes for CID 6260) |  |  |  | 2015-12-08 04:03 | GEN
6262 | RISON, Mark | 1000 | 4 | 20.3.20.3 | 2368 | 4 | T | Y | 2368.04 | 4 | 20.3.20.3 |  | V | Adrian Stephens | 11-15/1207r10 |  | It says "compliant with the OFDM PHY" | Change to "compliant with the HT PHY" | REVISED (GEN: 2015-12-07) At 2368.05 change "OFDM PHY" to "HT PHY". At 2367.55 change "the interfering signal" to "an interfering signal of 20 MHz bandwidth". At 2367.64 change "the interfering signal" to "an interfering signal of 40 MHz bandwidth". These changes address both the format and width of the interfering signal | GEN | GEN Dec F2F BRC - Piscataway | Ready for motion | GEN: 2015-11-08 Revised. At 2367.41, 2367.42, 2368.05, 2368.06 change “OFDM PHY” to “HT PHY”. At 2367.25, 2367.55 change “the interfering signal” to “an interfering signal of 20 MHz bandwidth”. At 2367.35, 2367.64 change “the interfering signal” to “an interfering signal of 40 MHz bandwidth”. At 2552.09, 2552.12, 2553.20, 2553.23 change “OFDM PHY” to “VHT PHY” |  |  |  | 2015-12-08 04:03 | GEN
6261 | RISON, Mark | 1000 | 4 | 20.3.20.2 | 2367 | 42 | T | Y | 2367.4199 | 42 | 20.3.20.2 |  | V | Adrian Stephens | 11-15/1207r10 |  | It says "For a conforming OFDM PHY" | Change to "For an HT PHY" | REVISED (GEN: 2015-12-07) Change "For a conforming OFDM PHY, the" to "The" at the cited location. (Note to editor: this is a subset of the changes in CID 6257) | GEN | GEN Dec F2F BRC - Piscataway | Ready for motion | GEN: 2015-11-08 Accepted. (Note to editor, these changes are a subset of the changes for CID 6260) |  |  |  | 2015-12-08 04:02 | GEN
6260 | RISON, Mark | 1000 | 4 | 20.3.20.2 | 2367 | 41 | T | Y | 2367.4099 | 41 | 20.3.20.2 |  | V | Adrian Stephens | 11-15/1207r10 |  | It says "compliant with the OFDM PHY" | Change to "compliant with the HT PHY" | REVISED (GEN: 2015-12-07) At 2367.41 change "OFDM PHY" to "HT PHY". At 2367.25 change "the interfering signal" to "an interfering signal of 20 MHz bandwidth". At 2367.35 change "the interfering signal" to "an interfering signal of 40 MHz bandwidth". These changes address both the format and width of the interfering signal. | GEN | GEN Dec F2F BRC - Piscataway | Ready for motion | GEN: 2015-11-08 Revised. At 2367.41, 2367.42, 2368.05, 2368.06 change “OFDM PHY” to “HT PHY”. At 2367.25, 2367.55 change “the interfering signal” to “an interfering signal of 20 MHz bandwidth”. At 2367.35, 2367.64 change “the interfering signal” to “an interfering signal of 40 MHz bandwidth”. At 2552.09, 2552.12, 2553.20, 2553.23 change “OFDM PHY” to “VHT PHY” |  |  |  | 2015-12-08 04:02 | GEN
6259 | RISON, Mark | 1000 | 4 | 19.4.8.3 | 2284 | 5 | T | Y | 2284.05 | 5 | 19.4.8.3 |  | A | Adrian Stephens | 11-15/1207r10 |  | It says "For an OFDM PHY" | Change to "For an ERP" | ACCEPTED (GEN: 2015-12-07) | GEN | GEN Dec F2F BRC - Piscataway | Ready for motion |  |  |  |  | 2015-12-08 04:02 | GEN
6258 | RISON, Mark | 1000 | 4 | 19.4.8.3 | 2284 | 4 | T | Y | 2284.04 | 4 | 19.4.8.3 |  | A | Adrian Stephens | 11-15/1207r10 |  | It says "compliant with the OFDM PHY" | Change to "compliant with the ERP" | ACCEPTED (GEN: 2015-12-07) | GEN | GEN Dec F2F BRC - Piscataway | Ready for motion |  |  |  |  | 2015-12-08 04:02 | GEN

## GEN Dec F2F BRC - Piscataway -1
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
6299 | RISON, Mark | 1000 | 4 |  |  |  | G | Y |  |  |  |  | V | Mark Rison | 11-15/762r15 |  | What is a "frame exchange" (anything with not more than one non-Control frame?)? What is a "frame exchange sequence" (anything with SIFS/RIFS separation?)? | Clarify (see strawmen in comment) | REVISED (GEN: 2015-12-08 15:23:02Z) Make the changes the changes shown under “Proposed changes” for CID 6299 in 11-15/762r15 <https://mentor.ieee.org/802.11/dcn/15/11-15-0762-14-000m-resolutions-for-some-comments-on-11mc-d4-0-sbmc1.docx>, which add a definition of the term “frame exchange sequence” and add “exchange” where missing in “frame sequence” (but do not address the meaning of the term “frame exchange”). | GEN | GEN Dec F2F BRC - Piscataway -1 | Ready for motion | GEN: 2015-11-14 - The following resolution is proposed as a default, if no alternative resolution is proposed: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-12-08 15:25 | GEN

## Gen Assigned Graham Smith
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
5226 | Adachi, Tomoko | 1000 | 4 | C.3 | 2910 |  | T | N | 2910 |  | C.3 |  |  | Graham Smith | 11-15/1004r5 |  | Isn't dot11RSNABIPMICErrors the same with dot11RSNAStatsCMACICVErrors? The reason of thinking like that is because, in 11.4.4.6 BIP reception d), it is said that "... If the result does not match the received MIC value, then the receiver shall discard the frame and increment the *dot11RSNAStatsCMACICVErrors* counter by 1, and terminate BIP processing for this reception." and BIP uses CMAC integrity check. The parameter, dot11RSNAStatsCMACICVErrors, is the counter that is used when there is an error in BIP CMAC integrity check and dot11RSNABIPMICErrors seems to be unnecessary. | Delete dot11RSNABIPMICErrors. |  | GEN | Gen Assigned Graham Smith | Submission Required | GEN: 2015-12-09 05:05:12Z - Proposed Resolution: REVISED Deprecate: dot11RSNABIPMICErrors. Delete “dot11RSNABIPMICErrors” at the following locations: P2907 line 65 P2910 Lines 21 to line 31, P3314 Line 51 GEN: 2015-08-14: from minutes : The resolution was discussed. 1. The question was raised as to whether references to dot11RSNAStatsCMACICVErrors in the text should (in part or all) reference dot11RSNABIPMICErrors, in which case it would be wrong to delete the MIB variable. A. Action: Dorothy to ask Dan to think about this. 2. C: deleting MIB variables might be the wrong thing to do. Mark deprecated, and delete from any object groups cited from a current compliance statement. Add reason for deprecation. |  |  |  | 2015-12-09 05:06 | GEN

## GEN Assigned to Mark RISON
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
6747 | RISON, Mark | 1000 | 4 |  |  |  | T | Y | [5 empty] | Mark Rison |  |  | Does "positive" include 0 (apparently not)? | Clarify (perhaps in Subclause 1.4 or 1.5?) |  | GEN | GEN Assigned to Mark RISON | Submission Required | GEN: 2015-11-14 - The following resolution is proposed as a default, if no alternative resolution is proposed: Rejected. The definitions of positive, negative and zero are well defined outside this standard. The comment fails to identify a specific issue to be addressed. It fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. GEN: 2015-09-08 20:19:45Z - <email-Adrian-11-15/1010r7> -- Rejected. The definitions of positive, negative and zero are well defined outside this standard. The comment fails to identify a specific issue to be addressed. It fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-11-15 01:33 | GEN
6720 | RISON, Mark | 1000 | 4 |  |  |  | T | Y | [5 empty] | Mark Rison |  |  | Does "non-VHT" imply "non-TVHT"? | Clarify |  | GEN | GEN Assigned to Mark RISON | Submission Required | GEN: 2015-11-14 -The following resolution is proposed as a default, if no alternative resolution is proposed: Rejected. The comment fails to identify a specific issue to be addressed. It fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. GEN: 2015-09-09 <email-Adrian-11-15/1010r7 Proposed Resolution: Rejected. The comment fails to identify a specific issue to be addressed. It fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-11-15 01:33 | GEN
6677 | RISON, Mark | 1000 | 4 |  |  |  | T | Y | [5 empty] | Mark Rison | 11-15/762 |  | Get rid of the wacko HT modes signalled by CH_OFF_20U/L, since they're not used. | As it says in the comment |  | GEN | GEN Assigned to Mark RISON | Submission Required | GEN: 2015-11-14 - The following resolution is proposed as a default, if no alternative resolution is proposed: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-11-15 01:40 | GEN
6676 | RISON, Mark | 1000 | 4 |  |  |  | T | Y | [5 empty] | Mark Rison | 11-15/762 |  | How do "CH_OFFSET_ABOVE/BELOW/NONE" relate to "CH_OFF_20/40/20L/20U"? | Clarify |  | GEN | GEN Assigned to Mark RISON | Submission Required | GEN: 2015-11-14 - The following resolution is proposed as a default, if no alternative resolution is proposed: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-11-15 01:39 | GEN
6657 | RISON, Mark | 1000 | 4 |  |  |  | T | Y | [5 empty] | Mark Rison |  |  | Various editorial issues were raised in yellow stuff in 14/1104 | Address these editorial issues |  | GEN | GEN Assigned to Mark RISON | Submission Required | GEN: 2015-11-14 - The following resolution is proposed as a default, if no alternative resolution is proposed: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-11-15 01:40 | GEN
6656 | RISON, Mark | 1000 | 4 |  |  |  | T | Y | [5 empty] | Mark Rison |  |  | Various technical issues were raised in yellow stuff in 14/1104 | Address these technical issues |  | GEN | GEN Assigned to Mark RISON | Submission Required | GEN: 2015-11-14 - The following resolution is proposed as a default, if no alternative resolution is proposed: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-11-15 01:40 | GEN
6632 | RISON, Mark | 1000 | 4 |  |  |  | G | Y | [5 empty] | Mark Rison |  |  | Canonical codepoints should be used, to help searching | Canonicalise the use of Unicode characters (e.g. different ways to represent "micro", "delta", "degree", "multiply"); I can provide a list of locations |  | GEN | GEN Assigned to Mark RISON | Submission Required | GEN: 2015-11-14 - The following resolution is proposed as a default, if no alternative resolution is proposed: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-11-15 01:39 | GEN
6631 | RISON, Mark | 1000 | 4 |  |  |  | G | Y | [5 empty] | Mark Rison |  |  | Proprietary codepoints should not be used, as this complicates searching (especially with non-Adobe tools) | Replace Unicode characters in the private use area(s) with their canonical equivalents; I can provide a list of locations |  | GEN | GEN Assigned to Mark RISON | Submission Required | GEN: 2015-11-14 - The following resolution is proposed as a default, if no alternative resolution is proposed: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-11-15 01:39 | GEN
6574 | RISON, Mark | 1000 | 4 | B.4 |  |  | E | Y | 2647 | 1 | B.4 |  |  | Mark Rison |  |  | We cleaned up the PICS (especially the CF section) in the early phases of TGmc, and then amendments came in and made it all messy and inconsistent again | Fix all the damage done by the later amendments |  | GEN | GEN Assigned to Mark RISON | Submission Required | GEN: 2015-11-15- The following resolution is proposed as a default, if no alternative resolution is proposed: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. EDITOR: 2015-05-28 15:06:22Z - Needs a submission. I don't think this should be considered editorial, particularly if "inconsistencies" are technical. Transferring to GEN. EDITOR_A: 2015-05-03 04:39:31Z |  |  |  | 2015-11-15 01:36 | GEN
6542 | RISON, Mark | 1000 | 4 |  |  |  | T | Y | [5 empty] | Mark Rison |  |  | There is a zoo of terminology: "operating [band]width", "channel [band]width", "operating channel width", "BSS operating width" (and probably other more esoteric forms) | Pick one term and humanely kill all the others |  | GEN | GEN Assigned to Mark RISON | Submission Required | GEN: 2015-11-14 - The following resolution is proposed as a default, if no alternative resolution is proposed: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-11-15 01:40 | GEN
6467 | RISON, Mark | 1000 | 4 |  |  |  | T | Y | [5 empty] | Mark Rison |  |  | The word "frame" is used too loosely. Sometimes it refers to a MSDU or MMPDU, rather than an MPDU (which might form just part of a fragmented MSDU or MMPDU). This affects, for example, whether the PM mode can change during a fragmented MSDU or MMPDU. | Make sure that "frame" is never used to refer to an MSDU or MMPDU. |  | GEN | GEN Assigned to Mark RISON | Submission Required | GEN: 2015-11-14 - The following resolution is proposed as a default, if no alternative resolution is proposed: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-11-15 01:38 | GEN
5761 | Hunter, David | 1000 | 4 | 16.3.7 | 2185 | 3 | E | Y | 2185.03 | 3 | 16.3.7 |  |  | Mark RISON |  |  | "PHY shall indicate a busy medium for the intended duration of the transmitted frame as indicated by the LENGTH field.": this doesn't say how this indication is to be made, and fields don't indicate things (though their values do). | Replace "shall indicate a busy medium" with "shall issue a PHY-RXEND indication to notify the MAC of a busy medium". Also, on the next line replace "for intended duration of the transmitted frame as indicated by the LENGTH field. The intended duration is indicated by the LENGTH field (length x 1 us)." with "for the intended frame transmission duration, as indicated by the value of the LENGTH field (length x 1 us)." |  | GEN | GEN Assigned to Mark RISON | Submission Required | GEN: 2015-11-15 -The following resolution is proposed as a default, if no alternative resolution is proposed: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. GEN: 2015-11-11 20:41:05Z - assigned to Mark RISON EDITOR: 2015-05-28 09:48:03Z - This is not a editorial comment. Transferring to GEN. |  |  |  | 2015-11-15 01:35 | GEN

## GEN CCA
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
6306 | RISON, Mark | 1000 | 4 |  |  |  | E | Y | [5 empty] | Mark Rison | 11-15/1155 |  | "CCA-ED" just confuses everyone, because everyone thinks it means CCA using ED, when in fact it means some wacko mode of operation in wacky regulatory domains/bands | Rename CCA-ED to something more obscure, so that people can use this term for the CCA-ED which is actually used in practice |  | GEN | GEN CCA | Submission Required | GEN: 2015-11-14 - The following resolution is proposed as a default, if no alternative resolution is proposed: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. EDITOR: 2015-05-12 00:18:23Z - Transferring to GEN to consider with 6305. |  |  |  | 2015-11-15 01:39 | GEN
6305 | RISON, Mark | 1000 | 4 |  |  |  | T | Y | [5 empty] | Mark Rison | 11-15-1155 |  | There is a zoo of inconsistent terminology for "carrier sense", whch makes it hard to understand exactly what is meant where and how the various PHYs compare: CS, CCA, CS/CCA, energy detect, ED, PHYED, CCA-ED, CCA Mode 1-5 | First rename CCA-ED to PHYRED (regulatory ED). Then call the ED which everybody uses PHYED, and the preamble detect PHYPD. Call the combination of things which yield the PHY part of "carrier sense" PHYCS. Kill the terms CS, CCA, CS/CCA, CCA Mode, ED. Make it clear how "I'm currently transmitting" fits into "carrier sense", and whether "I've received the PPDU header so I know how long to consider the medium busy even though the energy has gone away" is considered part of PHYCS or part of MACCS/virtual CS |  | GEN | GEN CCA | Submission Required | GEN: 2015-11-14 - The following resolution is proposed as a default, if no alternative resolution is proposed: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-11-15 01:40 | GEN
6303 | RISON, Mark | 1000 | 4 | 17.3.8.5 | 2227 | 34 | T | Y | 2227.3401 | 34 | 17.3.8.5 |  |  | Mark Rison | 11-15/1155 |  | It says "the timer of CCA Mode 2 shall be overridden by this requirement." but there is no timer in CCA Mode 2 (in fact, there is no CCA Mode 2 in HR/DSSS) | Change "2" to "4" in the cited text |  | GEN | GEN CCA | Submission Required |  |  |  |  | 2015-10-14 14:09 | GEN
6302 | RISON, Mark | 1000 | 4 |  |  |  | E | Y | [5 empty] | Mark Rison | 11-15/1155 |  | "is being received at the antenna" -- PPDUs can't be received anywhere else | Delete "at the antenna" in both instances of the cited text |  | GEN | GEN CCA | Discuss | GEN: 2015-11-14 - The following resolution is proposed as a default for Dec 10th if no alternative resolution is proposed: REJECTED; The use of "at the antenna" is correctly used in the context at 2227.10 and 2281.31. GEN: 2015-06-18 21:48:11Z - updated proposed resolution Pending time for Mark RISON to send comment to reflector: -REJECTED (GEN: 2015-06-18 21:39:27Z) The use of "at the antenna" is correctly used in the context at 2227.10 and 2281.31. . GEN: 2015-06-06 - Proposed Resolution: Reject: the two instances cited are in context correctly noted. 2227.10 and 2281.31 EDITOR: 2015-05-28 12:49:30Z - I think reception can occur at any entity of the architecture. But this thought is not an appropriate one for a humble editor to have. Transferring to GEN. |  |  |  | 2015-11-14 21:43 | GEN
6216 | RISON, Mark | 1000 | 4 |  |  |  | E | Y | [5 empty] | Mark Rison |  |  | The terms PHYCS and PHYED are defined but barely used | Delete them from subclause 3.4 and replace them in the other locations with their full-fat equivalents, i.e. physical CS and physical ED (4 instances each) |  | GEN | GEN CCA | Submission Required | GEN: Pulled from Motion in July, the following resolution is proposed as a default if no alternative resolution is proposed - REJECTED (EDITOR: 2015-05-28 12:44:40Z) - These terms are useful in providing clarity to the discussion in 16.3.7. |  | (Was previously Edit status = N) |  | 2015-11-15 01:37 | GEN
6215 | RISON, Mark | 1000 | 4 |  |  |  | E | Y | [5 empty] | Mark Rison |  |  | Use "CS" rather than "carrier sense" except when defined etc. | Use "CS" rather than "carrier sense" at 74.14, 833.8, 1239.15, 1664.39, 1664.40, 3187.59 (2x), 860.43, 864.52, 1378.5, 1679.57, 2184.52, 2437.59 |  | GEN | GEN CCA | Submission Required | GEN:Pulled from a motion in July, The following resolution is proposed as a default if no alternative resolution is proposed. -- REJECTED (EDITOR: 2015-05-28 12:45:39Z) - The comment does not indicate a problem to be addressed. The use of this term does not create a problem. |  | (Was previously Edit status = N) |  | 2015-11-15 01:40 | GEN
6214 | RISON, Mark | 1000 | 4 |  |  |  | T | Y | [5 empty] | Mark Rison | 11-15/1155 |  | There are references to "physical carrier sense", "virtual carrier sense" and "physical CS" and "virtual CS" but the terms are never defined | Define the terms. Arguably, virtual CS is defined at 1247.61 (though why it is "referred to as the NAV" is unclear -- or maybe virtual CS also includes considering the medium busy for the duration indicated in a received PPDU header?), but physical CS is not well-defined. 1247.57 says each PHY provides the details, but the term is only used at 2280.45 and merely reflects back to the PHY. Something needs to tie "physical CS" with the zoo of CS/CCA/energy detect/ED/blahblahblahPHYwibblings terminology used in each PHY |  | GEN | GEN CCA | Submission Required | GEN: 2015-11-14 - The following resolution is proposed as a default, if no alternative resolution is proposed: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-11-15 01:40 | GEN
6129 | Fischer, Michael | 1000 | 4 | 3.1 | 12 | 35 | E | N | 12.35 | 35 | 3.1 |  |  | Mark Rison | 11-15/1155 |  | "Carrier sense" is not defined herein | Either change "carrier sense (CS)" to "clear channel assessment (CCA)" or provide a definition for "carrier sense (CS)" |  | GEN | GEN CCA | Submission Required | EDITOR: 2015-06-11 10:35:15Z - Definitions can assume IEEE Std 100, which defines it as: "In a local area network, an ongoing activity of a data station to detect whether another station is transmitting." We could change as Michael indicates, but I think there is a technical difference between CCA, which is a specific process, and carrier sense, which is generic. Transferring to GEN. |  |  |  | 2015-10-14 14:11 | GEN

## GEN Reviewdiscuss
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
5237 | Hunter, David | 1000 | 4 | 2 | 4 | 44 | E | Y | 4.44 | 44 | 2 |  |  | Jon Rosdahl |  |  | Since this standard uses the externally defined term "Address Resolution Protocol", it needs to provide reference to the source of that term. | Insert the line: "IETF RFC 826, An Ethernet Address Resolution Protocol, David C. Plummer, November 1982." |  | GEN | GEN Review/discuss | Review | GEN: 2015-12-09 02:32:14Z - Revise At 4.43, Insert "IETF RFC 826, An Ethernet Address Resolution Protocol, David C. Plummer, November 1982 At 1753.26, Change "ARP request packet" to "ARP request packet (RFC 826)" At 3374.25, Change "802-2001" to "802-2014" At 569.57 and 1539.14, Change "9.2" to "8.2" and "802-2001" to "802-2014" At 570.15, Change "802-2001" to "802-2014" GEN: 2015-09-17 07:03:08Z - Need to prepare the resolution text to add the reference and the citation. GEN: 2015-07-09 15:08:10Z - From Email exchange: The first normative reference to ARP is 828.16. Definitions (such as this definition of the Capabilities field) are normative. In addition 1753.26 refers to the ARP request packet, which is defined in RFC 826. Without a definition of "ARP", there is no such thing as "Proxy ARP". So, if there is some hitherto unknown rule that references are not cited in definitions clauses, then the reference needs to be added to 1753.26 (replace "packet" with "packet (RFC 826)". (But then, if there were such a rule, of course a number of other RFC references would need to be pulled from clause 2.) By the way, the only version of IEEE Std 802 mentioned in the normative reference list is Std 802-2014. But there are no references to that document in the text -- though there are several references to "Std 802-2001". If each standard listed in Clause 2 is required to be referenced in the normative text, then one of the following is needed: a reference to Std 802-2001 needs to be added, or "802-2014" needs to be changed to "802-2001", or the various instances of "802-2001" in the text need to be changed to match the citation in clause 2. GEN: 2015-06-18 22:22:55Z - The closest "normative reference" 1868.57 where it is in an "example". GEN: 2015-06-06 - Proposed Resolution: Accept EDITOR: 2015-04-28 07:02:30Z - Adding a normative reference is not editorial. Transferring to GEN. |  |  |  | 2015-12-09 04:03 | GEN

## MIB
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
6752 | RISON, Mark | 1000 | 4 | C.3 |  |  | T | Y | 2841 | 55 | C.3 |  |  | Dorothy Stanley |  |  | Why are there two "dot11CurrentChannelWidth"s et al.? | Delete one of them |  | GEN | MIB | Discuss | GEN: 2015-12-09 - The following resolution is proposed as a default, if no alternative resolution is proposed: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-12-09 04:59 | GEN
6743 | RISON, Mark | 1000 | 4 | C.3 |  |  | T | Y | 2841 | 55 | C.3 |  |  | Dorothy Stanley |  |  | Why wasn't dot11AuthenticationAlgorithm made the same as dot11AuthenticationAlgorithmIndex? Can we make this change now? | As it says in the comment |  | GEN | MIB | Discuss | GEN: 2015-12-09 - The following resolution is proposed as a default, if no alternative resolution is proposed: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-12-09 05:00 | GEN
6705 | RISON, Mark | 1000 | 4 | C.3 |  |  | T | Y | 2841 | 55 | C.3 |  |  | Dorothy Stanley |  |  | Why is dot11TVHTMaxMPDULength needed? Why is dot11MaxMPDULength not good enough? Ditto maybe other TVHT MIB variables. | Remove the spurious MIB variables |  | GEN | MIB | Discuss | GEN: 2015-12-09 - The following resolution is proposed as a default, if no alternative resolution is proposed: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-12-09 04:59 | GEN
6690 | RISON, Mark | 1000 | 4 | C.3 |  |  | T | Y | 2841 | 55 | C.3 |  |  | Dorothy Stanley |  |  | The format of the REFERENCES in the MIB is not consistent (and some are doubtless missing). | Make those which are there consistent, and add those which are missing |  | GEN | MIB | Submission Required | GEN: 2015-12-09 - The following resolution is proposed as a default, if no alternative resolution is proposed: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-12-09 04:55 | GEN
6689 | RISON, Mark | 1000 | 4 | C.3 |  |  | G | Y | 2841 | 55 | C.3 |  |  | Dorothy Stanley |  |  | Cross-references in the MIB are not good because (a) they do not immediately indicate the spec revision and (b) they are not easily accessible (getIEEE might be discontinued). | Give the information directly, not by cross-reference |  | GEN | MIB | Discuss | GEN: 2015-12-09 - The following resolution is proposed as a default, if no alternative resolution is proposed: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-12-09 05:00 | GEN
6538 | RISON, Mark | 1000 | 4 | C |  |  | T | Y | 2841 | 1 | C |  |  | Dorothy Stanley |  |  | C.2 says "When an object is deprecated, add a line to the Description indicating why (IETF convention)." -- there is not always such a line | Add missing justifications |  | GEN | MIB | Discuss | GEN: 2015-12-09 - The following resolution is proposed as a default, if no alternative resolution is proposed: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-12-09 05:02 | GEN
6474 | RISON, Mark | 1000 | 4 | C |  |  | T | Y | 2841 | 1 | C |  |  | Dorothy Stanley |  |  | Slurp out all words starting with "dot11" in 802.11-2011 in all Clauses/Annexes other than Annex C. Slurp out all words following "SYNTAX" in Annex C. Compare | If anything is in one list but not the other, address the discrepancy (in some cases there may be good reasons for the discrepancy, and the simple recipe given in the comment will certainly produce false alerts) |  | GEN | MIB | Discuss | GEN: 2015-12-09 The following resolution is proposed as a default, if no alternative resolution is proposed: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-12-09 05:02 | GEN
6249 | RISON, Mark | 1000 | 4 | C.3 |  |  | T | Y | 2841 | 55 | C.3 |  |  | Dorothy Stanley |  |  | What does "DEFVAL { short }" mean in for dot11MaxMPDULength? More generally, there shouldn't be defaults for things which are entirely implementation-dependent | Remove the DEFVAL for dot11MaxAMSDULength, dot11MaxMPDULength, dot11TVHTMaxMPDULength and any other implementation-dependent capabilities |  | GEN | MIB | Discuss | GEN: 2015-12-09 - The following resolution is proposed as a default, if no alternative resolution is proposed: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-12-09 05:01 | GEN
6205 | RISON, Mark | 1000 | 4 | C.3 | 3184 | 43 | T | Y | 3184.4299 | 43 | C.3 |  |  | Dorothy Stanley |  |  | dot11PNWarningThreshold and dot11PNExhaustionThreshold (p. 3185) are 32-bit but the PN is 48-bit and there is no reason to stop using a PTKSA after 32 bits have been used up. | Change their SYNTAX to "Integer64 (1..281474976710655)" |  | GEN | MIB | Discuss | GEN: 2015-12-09 - The following resolution is proposed as a default, if no alternative resolution is proposed: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-12-09 05:09 | GEN
6069 | Hamilton, Mark | 1000 | 4 | C.3 | 3173 | 12 | T | Y | 3173.1201 | 12 | C.3 |  |  | Dorothy Stanley |  |  | With respect to dot11EDCATableTXOPLimit, it doesn't make sense to have a MIB attribute that is a "control variable" but written by the MAC. | If it is at all useful to expose this value externally, make it a status variable. Otherwise, consider removing the MIB attribute completely, as it is only used for the MAC to indicate the value to itself - and that is just a local variable, and not in the MIB. |  | GEN | MIB | Discuss | GEN: 2015-12-09 - The following resolution is proposed as a default, if no alternative resolution is proposed: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-12-09 05:09 | GEN
5055 | Stephens, Adrian | 1000 | 4 | C | 2841 | 1 | G | N | 2841.01 | 1 | C |  |  | Dorothy Stanley |  |  | The large numbers of warnings in the MIB makes it difficult for amendments to determine if they are causing any additional warnings. Such additional warnings are not allowed by the 802.11 MDR process. | Compile the MIB. Remove all "not in a group" and "not in a compliance statement" by adding a "bucket" group with optional support from the 802.11 compliance statement. |  | GEN | MIB | Discuss | GEN: 2015-12-09 - The following resolution is proposed as a default, if no alternative resolution is proposed: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-12-09 05:03 | GEN
5021 | Seok, Yongho | 1000 | 4 | C.3 | 3319 | 48 | T | Y | 3319.48 | 48 | C.3 |  |  | Dorothy Stanley |  |  | In dot11SMTbase13, please includes the followings. dot11DMGOptionImplemented dot11VHTOptionImplemented dot11TVHTOptionImpelemented Also, check other missing features. | Check whether dot11SMTbase13 has missing other features. At least, please include the followings. dot11DMGOptionImplemented dot11VHTOptionImplemented dot11TVHTOptionImpelemented |  | GEN | MIB | Discuss | GEN: 2015-12-09 - The following resolution is proposed as a default, if no alternative resolution is proposed: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-12-09 05:09 | GEN

## PHY
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
6821 | RISON, Mark | 1000 | 4 |  |  |  | T | Y | [5 empty] | Youhan Kim |  |  | In Clause 22 have "Set to 1 if a beamforming steering matrix is applied to the waveform in an SU transmission as described in 20.3.11.11.2 (Spatial mapping)." and "Set to 1 if a Beamforming steering matrix is applied to the waveform in an SU transmission as described in 20.3.11.11.2 (Spatial mapping)" i.e. ref to Clause 20, not Clause 22 spatial mapping. Ditto Clause 23. Also why uppercase "Beamforming"? | Refer to the correct subclause in 22 (and 23); fix the case of "beamforming" |  | GEN | PHY | Submission Required | GEN: 2015-11-14 - The following resolution is proposed as a default, if no alternative resolution is proposed: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-11-15 01:40 | GEN
6782 | RISON, Mark | 1000 | 4 |  |  |  | E | Y | [5 empty] | Sigurd Schelstraete |  |  | It says "Transmission of HT PPDU with" and "Transmission of HT PPDU is" | Change "PPDU" to "PPDUs" in both cases |  | GEN | PHY | Discuss | GEN: 2015-09-09 03:09:10Z - see also CID 6222 EDITOR: 2015-05-28 13:18:43Z - I would prefer the singular form. However, the cited location makes no sense technically: "Transmission of HT PPDU with any number of antennas is not supported in Clause 23 (Television Very High Throughput (TVHT) PHY specification)." This can be read that transmission of an HT PPDU is not supported. Period. Transferring to GEN to see if they can beat some sense into this sentence. |  |  |  | 2015-12-09 05:18 | GEN
6674 | RISON, Mark | 1000 | 4 | 20.2.3 | 2297 |  | T | Y | 2297 |  | 20.2.3 |  |  | Youhan Kim |  |  | What does "or CH_OFFSET is not present" mean? a) This table seems to be about tx, and the xXVECTOR table says this is always present in the TXVECTOR. b) If this is supposed to be about rx, then how does it work, since that table says this is never present in the RXVECTOR -- how does the MAC know what offset it was? | Clarify |  | GEN | PHY | Submission Required | REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-12-09 04:39 | GEN
6640 | RISON, Mark | 1000 | 4 | 7.3 | 543 | 28 | T | Y | 543.28 | 28 | 7.3 |  |  | Youhan Kim |  |  | PHY-TXBUSY is missing from Table 7-2 at 544.8 and its parameters from Table 7-3 at 544.34 | Add the missing information |  | GEN | PHY |  | GEN: 2015-12-09 Proposed Resolution: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-12-09 04:08 | GEN
6495 | RISON, Mark | 1000 | 4 | 20.3.20.5 | 2368 | 34 | T | Y | 2368.3401 | 34 | 20.3.20.5 |  |  | Youhan Kim |  |  | The HT rules for CCA as they pertain to non-HT transmissions are not clear. The issue is that if you don't know you're dealing with a non-HT transmission (which you don't know unless you successfully pick up the preamble) you don't know you have to apply the rules ("CCA sensitivity requirements for non-HT PPDUs") | Make it clear that the energy detect rules (not the CCA-ED rules, which are something different) from 18 and 19 apply even if you can't work out what type of PPDU/energy you're dealing with (these are "detect a medium busy condition within 4 us of any signal with a received energy that is 20 dB above the minimum modulation and coding rate sensitivity" for 2.4 GHz and -- hm, 19.4.6 has no energy detect requirement, that's in 19.3.4 ... but there's no just energy detect requirement there too. Does this mean HT has no just energy detect requirements (again, not talking of CCA-ED here) in the 5 GHz band? |  | GEN | PHY | Submission Required |  |  |  |  | 2015-12-09 04:41 | GEN
6477 | RISON, Mark | 1000 | 4 |  |  |  | T | Y | [5 empty] | Youhan Kim |  |  | aRxPHYStartDelay is an implementation-dependent quantity, not something which is fixed for a given PHY | Change 534.28 to "The delay, in microseconds, from start of the PPDU at the antenna to the PHY-RXSTART.indication primitive." Change 2187.52, 2214.37, 2274.23, 2287.20, 2382.46, 2453.35 to "Implementation dependent" |  | GEN | PHY | Discuss | GEN: 2015-12-09 - Proposed Resolution: Accept |  |  |  | 2015-12-09 05:20 | GEN
6431 | RISON, Mark | 1000 | 4 | 16 |  |  | T | Y | 2173 | 1 | 16 |  |  | Youhan Kim |  |  | Why does the DSSS PHY have such a big max MPDU length? All other PHYs (including HR/DSSS) have a maximum of 4095, and furthermore it's not clear what this means in terms of the max A-MSDU size which can be transported in a DSSS-format PPDU sent between HT STAs | Change 2^13 to 2^12 at 2175.14, 2176.24, 2188.19 |  | GEN | PHY |  | Proposed Resolution: Accept |  |  |  | 2015-12-09 04:32 | GEN
6304 | RISON, Mark | 1000 | 4 | 7.3.5.10.4 | 551 | 36 | T | Y | 551.36 | 36 | 7.3.5.10.4 |  |  | Vinko Erceg | 11-15/1400r4 |  | "reset the PHY CS/CCA timers" -- what PHY CS/CCA timers | Refer explicitly to the timers being reset |  | GEN | PHY |  | GEN: 2015-12-09 Proposed Resolution: Revise. Incorporate the text edits shown under the heading “Proposed text changes for CID 6304” as found in document 11-15-1400r4. Changes also addresses CID 6281, CID 6241, CID 6225 See 11-15-1420 for discussion. |  |  |  | 2015-12-09 04:26 | GEN
5995 | Kasher, Assaf | 1000 | 4 | 21.3.6.3 | 2406 | 1 | T | Y | 2406.01 | 1 | 21.3.6.3 |  |  | Payam Torab Jahroni |  |  | When the data is sent in OFDM, there is a different channel estimate field, therefore Single Carrier devices cannot use this field to decode the header. Therefore SC only devices cannot decode the header (which is also sent in OFDM) and therefore cannot determine the length of the packet. | We propose to send in the beacons an indication of OFDM intolerance. Details will come in a different presentation. |  | GEN | PHY | Submission Required | GEN: 2015-11-14 - The following resolution is proposed as a default, if no alternative resolution is proposed: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-11-15 01:42 | GEN
5978 | TorabJahromi, Payam | 1000 | 4 | 21.7.2.3.5 | 2441 |  | T | Y | 2441 |  | 21.7.2.3.5 |  |  | Payam Torab Jahroni |  |  | A-PPDU aggrergation is not defined for DMG low-power SC (how adjacent PPDUs are transmitted is undefined) | Define the A-PPDU aggregation; use DMG SC definnition as reference. |  | GEN | PHY | Submission Required | GEN: 2015-11-14 - The following resolution is proposed as a default, if no alternative resolution is proposed: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-11-15 01:42 | GEN
5977 | TorabJahromi, Payam | 1000 | 4 | 21.6.3 | 2428 |  | T | Y | 2428 |  | 21.6.3 |  |  | Payam Torab Jahroni |  |  | A-PPDU aggrergation is not defined for DMG ODFM (how adjacent PPDUs are transmitted is undefined) | Define the A-PPDU aggregation; use DMG SC definnition as reference. |  | GEN | PHY | Submission Required | GEN: 2015-11-14 - The following resolution is proposed as a default, if no alternative resolution is proposed: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-11-15 01:42 | GEN

## PICS
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
6548 | RISON, Mark | 1000 | 4 | B.4 |  |  | T | Y | 2647 | 1 | B.4 |  |  | Carlos Cordeiro |  |  | Why are there duplicate PICS entries for 11ad, e.g. QoS Frame Format | Merge them (being careful with the references, which seem to be different) |  | GEN | PICS | Submission Required | GEN: 2015-12-09 - The following resolution is proposed as a default, if no alternative resolution is proposed: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-12-09 04:52 | GEN
6451 | RISON, Mark | 1000 | 4 | B.4.17.1 | 2753 | 44 | T | Y | 2753.4399 | 44 | B.4.17.1 |  |  | Adrian Stephens |  |  | The Duration/ID rules for TXOPs apply to all STAs, not just HT STAs | Delete "and TXOP" in HTM8 and create a "Duration/ID rules for TXOP" in the QoS section which is CF<qos>:M |  | GEN | PICS | Discuss | GEN: 2015-12-08 - The following resolution is proposed as a default, if no alternative resolution is proposed: REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. |  |  |  | 2015-12-09 04:54 | GEN

## VHT PHY
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
5914 | Schelstraete, Sigurd | 1000 | 4 | 22.2.2 | 2458 | 40 | T | N | 2458.3999 | 40 | 22.2.2 |  |  | Sigurd Schelstraete | 11-15/1090r3 |  | In Table 22-1, sometimes reference is made to Table 20-1 for HT-related values, while sometimes content of Table 20-1 is copied explicitly. | Propose to consistently refer to Table 20-1 when appropriate rather than duplicating text in both Table 22-1 and Table 20-1. |  | GEN | VHT PHY | Submission Required | GEN: 2015-12-09 - Proposed Resolution - REJECTED - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. - The group expressed a preference for not duplicating the content of the Tables. |  |  |  | 2015-12-09 04:47 | GEN
5019 | Seok, Yongho | 1000 | 4 | 22.3.10.6 | 2522 | 23 | T | Y | 2522.23 | 23 | 22.3.10.6 |  |  | Youhan Kim |  |  | In Equation 22-73, there is a minor error on the range of K. k = 0, 1, ..., N_Block*N_ES*s - 1 k = N_Block*N_ES*s, ..., N_CBPSS - 1 's' should be 'S' (capital S). | Replace "N_Block*N_ES*s" with "N_Block*N_ES*S" in Equation 22-73. |  | GEN | VHT PHY | Submission Required | GEN: 2015-12-08 - Proposed Resolution: Accept |  |  |  | 2015-12-09 04:51 | GEN
5018 | Seok, Yongho | 1000 | 4 | 22.3.10.6 | 2522 | 14 | T | Y | 2522.1399 | 14 | 22.3.10.6 |  |  | Youhan Kim |  |  | In Equation 22-72, there is a minor error on the range of K. k = 0, 1, ..., N_Block*N_ES*s - 1 k = N_Block*N_ES*s, ..., N_CBPSS - 1 's' should be 'S' (capital S). | Replace "N_Block*N_ES*s" with "N_Block*N_ES*S" in Equation 22-72. |  | GEN | VHT PHY | Submission Required | GEN: 2015-12-08- Proposed Resolution Accept |  |  |  | 2015-12-09 04:51 | GEN