## Slide 1: NGP SG May 2015 Closing Report
Date: 2015-05-13
Authors:

## Slide 2: Abstract
This document is the NGP SG closing report for the Vancouver meeting, May 2015.

## Slide 3: Work Completed
Review and approval of PAR and CSD documents for WG motion.
Review of proposed use case documents.
Review of technical submissions.
Agenda: See 11-15/499

## Slide 4: Goals for July meeting
Pendent WG approval of PAR and CSD, resolving EC members and 802 WG comments for circulated PAR and CSD.
Continue review and adoption of Use Case to use case work draft document.
Continue review of technical submissions (performance analysis, positioning techniques, challenges etc.).

## Slide 5
Study Group Timeline
Month | Milestone / Plan of Action
January (i) | Formation meeting Initial discussion on PAR and CSD Presentations on use cases, usage models.
March (p) | Continue discussion on PAR and CSD Discussion supporting presentations. Study Group extension
May (i) | SG Final version of PAR and CSD Discussion on supporting presentations Working Group Approval on PAR and CSD PAR circulated amongst other WGs.
July (p) | Presentations. Resolve EC feedback on PAR and CSD. Executive Committee Approval on PAR and CSD Study Group extension
July (i) | NesCom Approval on PAR and CSD
Sep. (targeted) | Task Group formation meeting

## Slide 6: Conference Call Times
July 1st 10:00 AM – 11:00 EST.