## Slide 1: TGaq Closing Report
Date: 2016-05-19
Authors:

## Slide 2: Abstract
Closing report for TGaq (Pre-Association Discovery) for May 2016, Waikoloa.

## Slide 3
LB219 Comment Resolution Analysis
  93% approval, 71 comments
  Comment resolution complete and will request re-circulation letter ballot
Discussion topics
  Solicited PAD
  Service Hash element
Mandatory Draft Review (MDR)
  Will send D4.1 for MDR at the end of May/Early June
  Editor will then prepare D5.0 for letter ballot to complete by the start of the July 2016 face to face meeting
Plans for July 2016
  Work on comment resolutions from D5.0 re-circulation ballot
  Intend to request conditional sponsor ballot at the EC meeting