## Slide 1: TGax May 2016 Closing Report
Date: 2016-05-19
Authors:

## Slide 2: Abstract
This document is the closing report for the TGax for the May 2016 session.

## Slide 3: Work Completed
Received about 70 submissions. Majority of the submission were requesting changes to the TG Specification Framework. Few submission were addressing comment resolution mainly of the PHY clause.
Agreed to terminate the Specification Framework process. The frame of reference is Draft D0.1.
  Future submissions shall bring text to continue developing the TG draft
  The TG Technical Editor is planning to generate draft D0.2 based on outcome of this meeting
Approved the resolutions of about 200 comments, most of them addressing the PHY clause
Revisited the timeline and accepted a new modified timeline – next slide.

## Slide 4: Timeline
Current Timeline
May 2014: start of the TG
Nov. 2014: First draft of the TG SFD was approved
Jan. 2016: proposed TG draft
March 2016: Draft D0.1 was approved and CC started
July 2016: Draft 1.0 and WG letter ballot
March 2017: Draft 2.0 and recirculation
Jan 2018: Sponsor Ballot
Proposed Timeline
May 2014: start of the TG
Nov. 2014: First draft of the TG SFD was approved
Jan. 2016: proposed TG draft
March 2016: Draft D0.1 was approved and CC started
September 2016: Draft 1.0 and WG letter ballot
March 2017: Draft 2.0 and recirculation
July 2017: MDR (Mandatory Document Review)
November 2017: Formation of SB pool
March 2018: Sponsor Ballot
December 2018: RevCom

## Slide 5: July 2016 Goals
Continue with comment resolutions

## Slide 6: Conference Call Times
June (2, 16, 30), July 14 10:00 – 12:00 ET
June 23, July 7, August 4 20:00 – 22:00 ET