## Slide 1: IEEE 802.1 OmniRAN TG Status Report to IEEE 802 WGs
Date: 2016-11-10
Authors:

## Slide 2: IEEE 802.1 OmniRAN TG Resources
OmniRAN TG maintains a Wiki page on mentor to reflect its status and achievements
  https://mentor.ieee.org/omniran/bp/StartPage
  Also showing meeting announcements and conference call dial-in information
OmniRAN filespace on mentor is used for contributions and meeting documents
  https://mentor.ieee.org/omniran/documents
Recent P802.1CF D0.3 draft is available by
  http://www.ieee802.org/1/files/private/cf-drafts/d0/802-1cf-d0-3.pdf
    w/ 802.11 credentials
FYI: OmniRAN P802.1 PAR
  https://development.standards.ieee.org/get-file/P802.1CF.pdf?t=81644900003

## Slide 3: OmniRAN TG Achievements San Antonio meeting, Nov 7th – 10th
Comment resolution of TG ballot recirculation on draft D0.3
  Recirculation took place October 18th – Nov 3rd
  Roughly 50 comments received and 35 resolved during meeting
    Agreement to restructure section 7.1 on network initialization
    Base agreement on concept for network instantiation
    Discussion about ASA vs. TVWS
Discussion on going forward to draft D0.4
  D0.4 should address current flaws in Functional Description chapter
    Description of attributes
    Relation to existing IEEE 802 standards
    Restructuring section 7.1 on network initialization
Slide set for introduction of P802.1CF to IETF in Seoul next week.
Estimated timeline for P802.1CF within current scope:
  Starting WG ballot after March 2017, Sponsor Ballot Nov 2017
Special session on 5G SC Action A on Nov 9th
  Productive session. Progressing towards common understanding of targets
  Achieved (much) better understanding of role and operation of Industry Connections
  Initial draft of ICAID available, but not discussed yet

## Slide 4: Looking forward to next session in Atlanta, GA, Jan 16-19, 2017
Envisioned topics:
  Completion of comment resolution of P802.1CF-D0.3
  Enhancements to Functional Description chapter
    Description of attributes
    Relation to existing IEEE 802 standards
    Restructuring section 7.1 on network initialization
  Special session on progressing the planning for Industry Connections activity on 5G SC Action A
    Progress ICAID
Conference calls:
  Upcoming conference calls
    December 6th , 09:30am ET
      5G SC Action A: Discuss ICAID proposal
    December 13th , 09:30am ET
      P802.1CF: Progress D0.3 comment resolution