## Slide 1: A Proposed Timeline for IEEE 802.11ba TG
Date: 2017-01-16
Authors:

## Slide 2: Abstract
This submission proposes a timeline for the newly formed TG IEEE 802.11ba

## Slide 3: Some Considerations for the Timeline
IEEE 802.11ba is aimed toward IoT applications and there is a need for a timely development of an IEEE 802.11 amendment to address the emerging market.
Other standard development organizations (SDO) have already published their low-power specifications aimed to address IoT applications, e.g. 3GPP and its NB-IoT, LoRa Alliance, etc.
Other non-IEEE 802.11 technologies can be used (and are used) to achieve the WUR function, e.g. bluetooth.

## Slide 4: Some Historical Facts
11-07/1952r21 provides various statistics for different IEEE 802.11 amendments.
  https://mentor.ieee.org/802.11/dcn/07/11-07-1952-21-0000-non-procedural-letter-ballot-results.xls
Of interest is how long it takes between the PAR approval and the initial WG LB (draft D1.0)
  It seems major PHY/MAC amendments require an average of 30 months
    ….and unfortunately these amendments almost always fail the 1st WG LB,
We probably cannot afford to wait 30 months till draft D1.0

## Slide 5: A Proposed Timeline
An aggressive timeline with draft D1.0 be available in about 15 months after the PAR approval
  Sponsor ballot can potentially start in July 2019 with publication date set at March 2020
Therefore:
  Need to keep the function requirements to a bare minimum
  Need to guard against littering the draft with unnecessary features
January 2017
March 2017
July 2017
TG 1st meeting
TG Leadership selection
Start on TG documents
Technical Presentations
Complete TG documents
Start SFD
Technical Presentations
Continue with the SFD development
November 2017
Draft 0.1 and start CC
March 2018
Complete CC comment resolution and prepare draft 1.0
September 2018
Draft 2.0 and Recirculation
Start WG LB

## Slide 6: Straw Poll
Do you agree to adopt the timeline on page 5 as the IEEE 802.11ba TG timeline?
Yes:
No:
Abstain:

## Slide 7: References