## Slide 1: TGax March 2017 Closing Report
Date: 2017-03-16
Authors:

## Slide 2: Abstract
This document is the closing report for the TGax for the March 2017 session.

## Slide 3: Work Completed
Continued with the comment resolution on draft D1.0.
  Very good progress during the ad hoc meeting and this meeting
  The TG Editor is planning to generate a new revision of the TG draft (D1.2) and a new revision of the status of the comment resolution.
Spatial Reuse issues were discussed at length
  Some progress on spatial resource
Agreed to hold an ad hoc meeting in Seoul, Korea, May 3-5.
  PHY ad hoc meeting will be only for one day, Friday May 5
The agenda is available at: https://mentor.ieee.org/802.11/dcn/17/11-17-0199-06-00ax-tgax-march-2017-meeting-agenda.pptx

## Slide 4: Timeline Update
Old Time Line
May 2014: start of the TG
Nov. 2014: First draft of the TG SFD was approved
Jan. 2016: proposed TG draft
March 2016: Draft D0.1 was approved and CC started
November 2016: Draft 1.0 and WG letter ballot
May 2017: Draft 2.0 and recirculation
November 2017: MDR (Mandatory Document Review)
January 2018: Formation of SB pool
March 2018: Sponsor Ballot
December 2018: RevCom
Updated time line
May 2014: start of the TG
Nov. 2014: First draft of the TG SFD was approved
Jan. 2016: proposed TG draft
March 2016: Draft D0.1 was approved and CC started
November 2016: Draft 1.0 and WG letter ballot
September 2017: Draft 2.0 and recirculation
May 2018: MDR (Mandatory Document Review)
May 2018: Formation of SB pool
November 2018: Sponsor Ballot
July 2019: RevCom

## Slide 5: May 2017 Goals
Continue with the resolution of comments on draft D1.0

## Slide 6: Conference Call Times
April 13, 27, May 25 10:00 – 12:00 ET
April 20, May 18 20:00 – 22:00 ET