## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-17/0928r5
Venue Date: | January 2018
First Author: | Jon Rosdahl, Qualcomm
Subject: | REVmc Sponsor Ballot Comments
Full Date: | 2018-01-16
Author(s): | Name(s) | Jon Rosdahl
| Company | Qualcomm Technologies, Inc.
| Address | 10871 N 570 W, Highland, UT 84003
| Phone: | +1-801-492-4023
| email: | jrosdahl@ieee.org
Abstract:
This document contains the GenAdHoc comments received for the REVmd Comment Collection (#25) for P802.11REVmd .D0.1
As comment resolutions are approved, comments are moved to the editor for implementation and this file then will shrink.

## Revision History
Revision | Date | Description
0 | 2017-05-13 | Initial version with Comment Collection comments assigned for Gen AdHoc -
1 | 2017-07-13 | 5 CIDs were approved in Berlin and moved to Editor - Security CIDs moved to PHY
2 | 2017-08-03 | Review 4 CIDs on Review Tab during REVvmd Telecon - updated to ready for motion
3 | 2017-09-14 | CIDS Approved by motion moved to Editor, Updates on Assignment and 4 CIDs moved out to PHY and MAC
4 | 2017-12-08 | Update of CID status through the REVmd AdHoc in Piscataway, NJ
5 | 2018-01-16 | Update of status through Monday's REVmd mtg in Irvine and proposed reject resolutions for Submission required.
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## Dec Telecon
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
324 | Mark RISON | 25 | 0.1 |  |  |  | T | N |  |  |  |  | J |  |  |  | "When this attribute is false, the STA may accept MSDUs that have the Protected Frame subfield of the Frame Control field equal to 0." -- so it might not? What does "accept" mean here, exactly? | Delete this sentence | REJECTED (GEN: 2017-12-01 16:44:25Z) WEP has been deprecated and the task group has determined that they are not making any changes to clauses associated with obsolete/deprecated features. | GEN | Dec Telecon | Ready for Motion | GEN: 2017-12-01 17:59:24Z - status set to: Ready for Motion GEN: 2017-06-30 16:42:48Z - status set to: Discuss |  |  |  | 2017-12-01 18:00 | GEN
76 | Jian Yu | 25 | 0.1 | 3.1 | 141 | 54 | G | Y | 141 | 54 | 3.1 |  | V |  |  |  | There are 236 instances of Nsts and 49 instances of NUM_STS but without a description of what STS is. | Add an abbreviation for space-time stream, e.g., STS, and replace "space-time stream" with the abbreviation throughout the draft. | REVISED (GEN: 2017-12-01 16:27:13Z) page 155 d0.4 L54 - Change “space-time streams: Streams of” to "space-time stream (STS): Stream of” and add "STS space-time stream" to subclause 3.4, if appropriate per our conventions. | GEN | Dec Telecon | Ready for Motion | GEN: 2017-12-01 16:27:46Z - status set to: Ready for Motion GEN: 2017-06-30 17:58:02Z - status set to: Discuss |  |  |  | 2017-12-01 16:38 | GEN
29 | Graham Smith | 25 | 0.1 | 4.3.2 | 188 | 40 | T | N | 188 | 40 | 4.3.2 |  | V |  |  |  | "Because this type of IEEE Std 802.11 LAN is often formed without preplanning, for only as long as the LAN is needed." Something missing? Insert after the comma, "the IBSS is active". | In cited text, insert after the comma, "the IBSS is active". | REVISED (GEN: 2017-12-01 16:11:11Z) - Change cited sentence to "This type of IEEE 802.11 LAN is often formed without preplanning." | GEN | Dec Telecon | Ready for Motion | GEN: 2017-12-01 16:09:37Z - status set to: Ready for Motion GEN: 2017-06-30 17:57:50Z - status set to: Discuss |  |  |  | 2017-12-01 16:12 | GEN

## Gen Motion - Dec Telecon
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
233 | Mark RISON | 25 | 0.1 | 3.2 |  |  | T | N |  |  | 3.2 |  | V | Mark Rison |  |  | "nonaggregate medium access control (MAC) protocol data unit (non-A-MPDU) frame: A frame that is transmitted in a physical layer (PHY) protocol data unit (PPDU) with the TXVECTOR AGGREGATION parameter either absent or equal to NOT_AGGREGATED" -- this definition means that all frames in VHT PPDUs are non-A-MPDU frames, since the TXVECTOR AGGREGATION parameter is absent | Append " and that is not a VHT or TVHT PPDU" to the cited text | REVISED (GEN: 2017-12-15 15:20:21Z) Make the changes shown under “Proposed changes” for CID 233 in 11-17/1243r6 <https://mentor.ieee.org/802.11/dcn/17/11-17-1243-06-000m-resolutions-for-some-comments-on-11md-d0-1-cc25.docx>, which address the issue raised but (a) reduce future maintenance problems and (b) consistently make S-MPDUs a type of non-A-MPDU frame. | GEN | Gen Motion - Dec Telecon | Ready for Motion | GEN: 2017-12-15 15:20:31Z - status set to: Ready for Motion GEN: 2017-12-08 15:48:59Z - status set to: Submission Required and assign to Mark RISON to provide an updated resolution GEN: 2017-06-30 17:06:00Z - status set to: Discuss |  |  |  | 2017-12-15 15:48 | GEN

## Gen Motion - Jan
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
292 | Mark RISON | 25 | 0.1 |  |  |  | T | N |  |  |  |  | V | Carlos Cordiero |  |  | It says "where a PCP doze BI may not start with a BTI or ATI" -- what kind of "may not" is this? | Either change the cited text to "where a PCP doze BI shall not start with a BTI or ATI" or change the sentence at the referenced loction to "In a PBSS, except in PCP power save (PPS) mode, every beacon interval shall start with a BTI or ATI." | REVISED (GEN: 2018-01-15 23:30:10Z) change cited text to "where a PCP doze BI shall not start with a BTI or ATI" | GEN | Gen Motion - Jan | Ready for Motion | GEN: 2018-01-15 23:30:20Z - status set to: Ready for Motion GEN: 2017-06-30 17:41:37Z - status set to: Discuss |  |  |  | 2018-01-16 00:12 | GEN
223 | Mark RISON | 25 | 0.1 |  |  |  | T | N |  |  |  |  | A | Menzo Wentink |  |  | "QSRC[AC] shall be incremented every time transmission of an A-MPDU or frame in a PSDU of length less than or equal to dot11RTSThreshold fails". The behaviour is not clear if the transmission of an A-MPDU with more than one MPDU fails, because it is not clear whether QSRC[AC] is incremented by one ("transmission of an A-MPDU") or by the number of MPDUs ("transmission of [a] frame"). Ditto for QLRC | Delete "n A-MPDU or" (twice) | ACCEPTED (GEN: 2018-01-15 22:27:30Z) | GEN | GEN Motion - Jan | Ready for Motion | GEN: 2018-01-15 22:27:34Z - status set to: Ready for Motion GEN: 2018-01-14 04:58:59Z - status set to: Discuss -- Proposed Resolution: Accept |  |  |  | 2018-01-15 22:28 | GEN
222 | Mark RISON | 25 | 0.1 |  |  |  | T | N |  |  |  |  | A | Menzo Wentink |  |  | "The CW shall be reset to aCWmin after every successful attempt to transmit a frame containing all or part of an MSDU or MMPDU" -- it should also be reset on successful transmission of a QoS Null | Change the cited text "The CW shall be reset to aCWmin after every successful attempt to transmit a Data or Management frame" | ACCEPTED (GEN: 2018-01-15 22:26:57Z) | GEN | Gen Motion - Jan | Ready for Motion | GEN: 2018-01-15 22:27:00Z - status set to: Ready for Motion GEN: 2018-01-14 04:58:39Z - Propose - Accept GEN: 2017-12-08 20:26:05Z - status set to: Discuss |  |  |  | 2018-01-15 22:27 | GEN
108 | Kazuyuki Sakoda | 25 | 0.1 | 4.5.4.9 | 229 | 37 | T | N | 229 | 37 | 4.5.4.9 |  | V | Kazuyuki Sakoda |  |  | 3rd paragraph of 4.5.4.9 (Robust management frame protection) explains how to protect management frames in an MBSS. The paragraph is not reader friendly and incomplete. Suggest to make the description similar to the previous paragraph explaining the case of infrastructure BSS and IBSS and leave pointer to the subclause that has more detailed information. | Replace "Management frame protection protocols in an MBSS apply to individually addressed frames after establishment of the RSNA MTK, and to group addressed frames indicated as "Group Addressed Privacy" in Table 9-47 (Category values). Robust management frame protection is implemented with CCMP and GCMP." with "Management frame protection protocols in an MBSS apply to the following frames: - Individually addressed robust Management frames after establishment of the RSNA MTK, - Group addressed robust Management frames that are specified with "Yes" in the "Group Addressed Privacy" column of Table 9-47 (Category values) after establishment of the RSNA MGTK, and - Rest of the group addressed robust Management frames after establishment of the RSNA IGTK. Robust management frame protection is implemented by CCMP, GCMP, and BIP. See 14.7 (Mesh Security) for details." | REVISED (GEN: 2018-01-16 01:38:23Z) Replace 'Management frame protection protocols in an MBSS apply to individually addressed frames after establishment of the RSNA MTK, and to group addressed frames indicated as "Group Addressed Privacy" in Table 9-47 (Category values).' with 'Management frame protection protocols in an MBSS apply to the following frames: - Individually addressed robust Management frames after establishment of the RSNA MTK, - Group addressed robust Management frames that are specified with "Yes" in the "Group Addressed Privacy" column of Table 9-53 (Category values) after establishment of the RSNA MGTK, and - Group addressed robust Management frames that are specified with "No" in the "Group Addressed Privacy" column of Table 9-53 (Category values) after establishment of the RSNA IGTK. See 14.7 (Mesh Security) for details.' | GEN | Gen Motion - Jan | Ready for Motion | GEN: 2018-01-16 01:38:30Z - status set to: Ready for Motion GEN: 2018-01-16 01:34:07Z - CID 108 - rebased on top of REVmd/D0.5 and cleaned up the proposed changes: REVISED - Replace 'Management frame protection protocols in an MBSS apply to individually addressed frames after establishment of the RSNA MTK, and to group addressed frames indicated as "Group Addressed Privacy" in Table 9-47 (Category values).' with 'Management frame protection protocols in an MBSS apply to the following frames: - Individually addressed robust Management frames after establishment of the RSNA MTK, - Group addressed robust Management frames that are specified with "Yes" in the "Group Addressed Privacy" column of Table 9-53 (Category values) after establishment of the RSNA MGTK, and - Group addressed robust Management frames that are specified with "No" in the "Group Addressed Privacy" column of Table 9-53 (Category values) after establishment of the RSNA IGTK. See 14.7 (Mesh Security) for details.' GEN: 2017-06-30 18:07:44Z - status set to: Discuss |  |  |  | 2018-01-16 01:39 | GEN

## GEN Motion - Oct
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
286 | Mark RISON | 25 | 0.1 | 4.3.14 |  |  | T | N |  |  | 4.3.14 |  | V |  |  |  | "The IEEE Std 802.11 VHT STA operates in frequency bands below 6 GHz excluding the 2.4 GHz band." suggests a VHT STA can be an 11ah, 11af, 11y or 11p STA, but this seems incompatible with or at least confusing w.r.t. "A VHT STA is an HT STA." | Delete the cited text and add ", but does not operate in the 5 GHz band" to the end of the next para, just before the full stop | REVISED (GEN: 2017-10-13 15:29:08Z)Delete the cited text at 200.37 and add at 200.43 ", but does not operate in the 2.4 GHz band" to the end of the next para, just before the full stop | GEN | GEN Motion - Oct | Ready for Motion | GEN: 2017-10-13 15:41:36Z - status set to: Ready for Motion GEN: 2017-06-30 17:03:33Z - status set to: Discuss |  |  |  | 2017-10-13 21:35 | GEN

## Gen Motion AdHoc
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
120 | Mark Hamilton | 25 | 0.1 | 3.1 | 133 | 6 | T | Y | 133 | 6 | 3.1 |  | A |  |  |  | "Distribution service" or "distribution system service"? Distribution system service should be preferred, it shortens to DSS, which avoids confusion. Some "distribution service" uses should be "distribution system", the rest should be spelled out as "distribution system service". | Change "distribution service" to "distribution system" at P194.7, P222.25, and P223.48. Change the rest of the "distribution service(s)" to "distribution system service(s)" | ACCEPTED (GEN: 2017-12-07 21:06:52Z) | GEN | Gen Motion AdHoc | Ready for Motion | GEN: 2017-12-07 21:11:04Z -There are a total of 15 changes that this CID causes. GEN: 2017-12-07 21:06:41Z - status set to: Ready for Motion GEN: 2017-06-30 17:56:13Z - status set to: Discuss |  |  |  | 2017-12-08 20:11 | GEN
320 | Mark RISON | 25 | 0.1 |  |  |  | T | N |  |  |  |  | J | Mark Rison |  |  | There is no reason Action No Acks can't have MICEs. While at the moment it may be the case that such frames carry "information [...] that is of time critical but transient value" (resolution of CID 6343 in mc), this is not a property of Action No Acks per se | Add MICEs to Table 9-39 as in Table 9-38 | REJECTED (GEN: 2017-12-08 19:41:53Z) There is no reason for Action No Ack to carry MIC elements. The Action No Ack currently carries information such as beamforming that is of time critical but transient value. There is no need to cryptographically authenticate such data, until such uses are added, and a MIC element can be added at that time. | GEN | Gen Motion AdHoc | Ready for Motion | GEN: 2017-12-08 19:44:25Z - status set to: Ready for Motion |  |  |  | 2017-12-08 19:47 | GEN
302 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | V |  |  |  | "This format is represented at the PHY data service access point (SAP) by the TXVECTOR/RXVECTOR FORMAT parameter being equal to HT_MF." is superfluous (not done for other cases) | Delete the cited sentence (also for HT_GF and any other similar sentences if they exist) | REVISED (GEN: 2017-12-08 19:31:09Z) make the following changes: 154.33 delete sentence starting “This format is represented at the PHY …“ 154.45 delete sentence starting “This format is represented at the PHY…” 154.59 change definition to “A Clause 19 (High-Throughput (HT) PHY specification) PPDU that is either high-throughput(HT) mixed format(HT-MF) or high-throughput (HT) greenfield format (HT-greenfield) format. This makes a change in the direction suggested by the commentor | GEN | Gen Motion AdHoc | Ready for Motion | GEN: 2017-12-08 19:32:25Z - status set to: Ready for Motion EDITOR2: 2017-06-24 21:28:24Z Transfer to GEN. |  |  |  | 2017-12-08 20:10 | GEN
296 | Mark RISON | 25 | 0.1 |  |  |  | T | N |  |  |  |  | V |  |  |  | "The additional HT capabilities to be advertised for the BSS." -- no, that's not what the parameter carries | Change the cited text to "Provides additional information for operating the HT BSS." | REVISED (GEN: 2017-12-08 15:30:36Z) at p327.50 (D0.1) make the proposed change. | GEN | Gen Motion AdHoc | Ready for Motion | GEN: 2017-12-08 15:30:48Z - status set to: Ready for Motion GEN: 2017-06-30 18:21:07Z - status set to: Discuss |  |  |  | 2017-12-08 20:11 | GEN
295 | Mark RISON | 25 | 0.1 |  |  |  | T | N |  |  |  |  | V | Graham Smith |  |  | What's a "backoff slot" anyway? It kinda makes sense as a slot occurring during backoff, but it does not make sense as a unit of time | Delete "backoff" at 908.8, 1351.8, 1590.32, 1590.33 [in mc/D6.0] | REVISED (GEN: 2017-12-08 16:10:17Z) Incorporate the changes in 11-17/987r10 for CID 294, which clarifies the text identified in the comment. (This Comment and CID 294 are similar). | GEN | Gen Motion AdHoc | Ready for Motion | GEN: 2017-12-08 16:11:21Z - status set to: Ready for Motion GEN: 2017-12-08 15:27:12Z - status set to: Submission Required and assign to Graham. GEN: 2017-06-30 17:51:01Z - status set to: Discuss |  |  |  | 2017-12-08 20:11 | GEN
293 | Mark RISON | 25 | 0.1 |  |  |  | T | N |  |  |  |  | V |  |  |  | "Fine Timing Measurement frames are sent during time windows called burst instances." is not clear. If it's just a general introduction rather than a specification, then where is the normative statement about when FTM frames may and may not be sent? | Change the cited text to "Fine Timing Measurement frames are only sent during time windows called burst instances." | REVISED (GEN: 2017-12-08 19:17:03Z) Change cited sentence at P1916.24 "The time windows during which Fine Timing Measurement frames are sent are known as burst instances." | GEN | Gen Motion AdHoc | Ready for Motion | GEN: 2017-12-08 19:18:18Z - status set to: Ready for Motion GEN: 2017-06-30 17:36:24Z - status set to: Discuss |  |  |  | 2017-12-08 19:18 | GEN
244 | Mark RISON | 25 | 0.1 |  |  |  | T | N |  |  |  |  | J |  |  |  | "The MME of a Vendor-Specific Protected Action frame is located at the end of the frame body. NOTE---It is not necessary to be able to parse the Vendor-Specific Content to locate the MME." is duplication of Clause 9. I'm not even sure it's correct (can't an AMPE follow?) | Delete the cited text | REJECTED (GEN: 2017-12-08 15:15:56Z) The Statement is correct, the note is in the context of parsing Vendor specific frames, and that the MME can be located. | GEN | Gen Motion AdHoc | Ready for Motion | GEN: 2017-12-08 15:16:06Z - status set to: Ready for Motion GEN: 2017-10-13 16:00:45Z - Proposed Resolution: REJECTED (GEN: 2017-10-13 15:57:53Z) The Statement is correct, the note is in the context of parsing Vendor specific frames, and that the MME can be located. GEN: 2017-06-30 18:18:59Z - status set to: Discuss |  |  |  | 2017-12-08 20:11 | GEN
145 | Mark RISON | 25 | 0.1 | 4.3.18.13 | 206 | 15 | T | N | 206 | 15 | 4.3.18.13 |  | V |  |  |  | It is confusing for "proxy ARP" to sometimes include proxy ND, especially since it sometimes but not always says "(including Proxy Neighbor Discovery)" | Change "proxy ARP" to "proxy ARP/ND" throughout the draft; delete "(including Proxy Neighbor Discovery)" throughout the draft; change "dot11ProxyARP" to "dot11ProxyARPND" throughout the draft | REVISED (GEN: 2017-12-07 21:03:27Z) change 4.3.18.13 Proxy ARP "The Proxy ARP service enables an AP to respond to ARP and Neighbor Discovery frames on behalf of associated non-AP STAs. Associated STAs do not receive ARP or IPv6 Neighbor Discovery frames. The Proxy ARP service enables associated STAs to remain in power save for longer periods of time." at p1933.11 delete “(including Proxy Neighbor Discovery” Change 1933.35 change “Neighbor Discovery” to “ARP” Change 2061.58 change “Proxy-ARP” to “the Proxy ARP service” | GEN | Gen Motion AdHoc | Ready for Motion | GEN: 2017-12-07 21:04:53Z - status set to: Ready for Motion GEN: 2017-06-30 17:58:48Z - status set to: Discuss |  |  |  | 2017-12-07 21:05 | GEN

## Minor correction
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
196 | Mark RISON | 25 | 0.1 |  |  |  | T | N | [8 empty] | The antenna ID in the Antenna element is only allowed to be from 1 to 254 (0 (unknown) and 255 (multiple) have special meanings, but maybe they're allowed on receive) | In Table 16-5 change 1-256 to 1-254. In Table 17-2 change 0-255 for ANT_STATE to 1-254 |  | GEN | Minor correction | Discuss | GEN: 2017-06-30 18:20:10Z - status set to: Discuss |  |  |  | 2017-12-08 20:33 | GEN
195 | Mark RISON | 25 | 0.1 |  |  |  | T | N | [8 empty] | The antenna ID in the Antenna element is only allowed to be from 1 to 254 (0 and 255 have special meanings) | Change 256 to 254 in Table 16-1, 15.2.2.7 and Table 16-2; change 255 to 254 in C.3 for dot11CurrentTxAntenna, dot11CurrentRxAntenna and dot11AntennaListIndex |  | GEN | Minor correction | Discuss | GEN: 2017-06-30 18:18:50Z - status set to: Discuss |  |  |  | 2017-12-08 20:33 | GEN
140 | Mark RISON | 25 | 0.1 |  |  |  | T | N | [5 empty] | Jon Rosdahl |  |  | There are about 30 each of "at the antenna" and "at the antenna connector" | Add "connector" after "at the antenna" where not already present | Change "at the antenna" to "at the antenna connector" for the following locations: P984 L17 (in Table 9-119) P2138 L26 (11.11.12) P2677 L4 (15.2.3.3) P2696 L60 (15.4.6.3) P2727 L5 (16.3.8.2) P2727 L45 (16.3.8.5) P2733 L34 (17.2.3.3) P2765 L26 (17.3.10.5) P2781 L24 (18.3.4) P2791 L58 (Table 19-1) P2965 L49 (Table 21-1) P3098 L13 (Table 22-1) P3157 L12 (Table 23-1) P3157 L20 (Table 23-1) P3157 L26 (Table 23-1) P3614 L3 (dot11WirelessMGTEventPeerSTATxPower MIB) P3750 L8 (dot11WNMEventPeerRprtStaTxPower MIB) Also change: P4027L17 change "at the antenna input" to "at the antenna connector" (Table D-3) | GEN | Minor correction | Discuss | GEN: 2018-01-16 17:04:04Z - Proposed Resolution: posted GEN: 2018-01-16 00:50:47Z - status set to: Discuss Counter proposal to change "at the antenna" or "at the antenna connector" with "at the base of the antenna". In hallway discussions, I have found more support for just Accepting the proposed change, but was given a warning that adding "at the connector" is not always correct, for example: P1130,L8. Shouldn't add "connector" since the text is about EIRP. See below. "The STA Tx Power field indicates the target transmit power at the antenna (i.e., EIRP) in dBm with atolerance of ± 5 dB of the lowest basic rate of the reporting STA. " GEN: 2017-12-15 16:30:27Z -Change assignee to Jon. Jon will reach out to those involved in this discussion previously, and ask for a review of the ~ 14 locations without "connector" for correctness to add "connector" GEN: 2017-10-13 15:43:43Z - status set to: Submission Required GEN: 2017-06-30 17:42:00Z - status set to: Discuss |  |  |  | 2018-01-16 17:08 | GEN
78 | John Coffey | 25 | 0.1 | 17.3.10.6 | 2474 | 38 | T | Y | 2474 | 38 | 17.3.10.6 |  |  | Sean Coffey | 11-17/1479r2 |  | The level -82 dBm is far too high and should be revisited, along with the assumption that the level has to be fixed. See 17/0458r1, slides 8-13, for details. We have the slight problem that imposing a stricter requirement will disadvantage newer devices. Even then we would be better off specifying the requirement as a sum of a best realistic value plus some offset advertised by the AP. This would allow us to adapt the requirement over time. | Recalculate the numbers to something reasonable, and restate the requirement so that receivers shall be capable of decoding preambles at the given levels--whether they actually declare medium busy can be a function of additional AP-declared policies. |  | GEN | Minor correction | Submission Required | GEN: 2017-06-30 18:12:38Z - status set to: Submission Required |  |  |  | 2018-01-16 17:22 | GEN

## Submission Required
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
310 | Mark RISON | 25 | 0.1 |  |  |  | T | N | [5 empty] | Mark Rison |  |  | "initiated by the STA" -- so this means that the PM mode cannot be changed during RD. However, only timing distinguishes the last frame of a RD exchange from the first frame of a non-RD exchange, which is awkward to validate | Allow the PM mode to be changed in RD | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | GEN | Submission Required | Submission Required | GEN: 2017-06-30 17:33:55Z - status set to: Submission Required |  |  |  | 2018-01-16 17:25 | GEN
80 | John Coffey | 25 | 0.1 | All | 1 | 1 | T | Y | 1 | 1 | All |  |  | Sean Coffey |  |  | The standard makes effective use of a wide variety of channel access mechanisms, but there is one missing variation that would be widely useful: a variable poll that automatically transfers between different devices if not used. With a straightforward poll, AP transmits poll, specifying a duration. If the polled device has no data to send, or if it is unable to transmit because it senses a busy medium, the time specified by the AP is lost. (Unless the AP sends another frame, cancelling the poll, though this in itself also incurs loss of time.) It would be much more flexible if the AP could transmit a muti-poll, addressed to STAs A and B; A may commence transmission during the first slot time; if it does not do so, then the TXOP automatically transfers to B, without any explicit cancellation of A's opportunity or formal new invitation to B. This removes a great deal of overhead and boils the cost down to the bare minimum, i.e., a single slot time. In this simple form it depends on B being able to hear A, but it's possible to define variants that don't require that (at the cost of some extra overhead). As one motivating example, say we have a large-scale deployment of IoT devices that each transmit only sporadically. Either these devices are 11b-only for cost/complexity/power consumption reasons, or they are scattered at such long ranges that only 1 & 2 Mbps can reach them. Rather than poll them individually (a nightmare of overhead) or run the entire network with DSSS RTS/CTS wrappers, also no bargain, the AP could use the variable multi-poll to scan through them, with great efficiency (in some sense an absolute minimum of overhead). | Add a variable, automatically transferable poll mode of operation. A detailed proposal for how this could work is contained in the documents 15/1115r1, 16/0102r1, and 16/0394r0. (Note: these presentations describe the "roster" mode of operation. In retrospect this is not the right term: it mixes together one particular means (the "roster") for achieving the essential goal (the variable, transferable poll) with the goal itself. The variable, transferable poll is the nub of the concept.) | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | GEN | Submission Required | Submission Required | GEN: 2017-06-30 17:55:22Z - status set to: Submission |  |  |  | 2018-01-16 17:20 | GEN
173 | Mark RISON | 25 | 0.1 | 6.3.3.2.2 | 271 | 37 | T | N | 271 | 37 | 6.3.3.2.2 |  |  | Mark Rison |  |  | OperationalRateSet, HT Capabilities and VHT Capabilities need to be passed in MLME-SCAN.request when ScanType is ACTIVE, since they are in the Probe Request frame | Add the cited arguments to the cited primitive, stating that they are only present if ScanType is ACTIVE |  | GEN | Submission Required | Submission Required | GEN: 2017-06-30 18:13:49Z - status set to: Submission |  |  |  | 2018-01-16 17:21 | GEN
184 | Mark RISON | 25 | 0.1 | 3.2 |  |  | T | N |  |  | 3.2 |  |  | Mark RISON |  |  | There are definitions in 3.2 for DMG PPDU and HT PPDU and VHT PPDU and non-HT PPDU but not other PHYs' PPDUs | Add definitions for every PHY's PPDUs | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | GEN | Submission Required | Submission Required | GEN: 2017-12-08 20:02:09Z - status set to: Submission Required |  |  |  | 2018-01-16 17:20 | GEN
247 | Mark RISON | 25 | 0.1 |  |  |  | T | N | [5 empty] | Mark Rison |  |  | "A non-AP STA shall not transmit an Ack or BlockAck frame in response to a group addressed frame." -- so an AP does potentially ack group-addressed frames (i.e. RA = group)? Why? | Clarify | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | GEN | Submission Required | Submission Required | GEN: 2017-12-08 20:02:32Z - status set to: Submission Required |  |  |  | 2018-01-16 17:20 | GEN
250 | Mark RISON | 25 | 0.1 | 6 |  |  | T | N |  |  | 6 |  |  | Menzo Wentink |  |  | The MLME-TDLS* primitives cheat by saying just "see the frame format" for the contents. This means restrictions on e.g. the rates/MCSes cannot be given | Pass the frame contents separately, with range and description etc. text, as for other primitives | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | GEN | Submission Required | Submission Required | GEN: 2017-12-08 19:19:45Z - status set to: Submission Required |  |  |  | 2018-01-16 17:20 | GEN
303 | Mark RISON | 25 | 0.1 |  |  |  | T | N | [5 empty] | Mark Rison |  |  | The distinctions made in the specification w.r.t. TS/TC/TSID/TID are incomprehensible | Make the definitions comprehensible. E.g. what does "UP for either TC or TS" mean? | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | GEN | Submission Required | Submission Required | GEN: 2017-12-08 20:02:48Z - status set to: Submission Required |  |  |  | 2018-01-16 17:20 | GEN
79 | John Coffey | 25 | 0.1 | All | 1 | 1 | T | Y | 1 | 1 | All |  |  | Sean Coffey |  |  | We would greatly benefit by defining a "speak-only-when-spoken-to" mode of operation, under which a non-AP STA would only be able to transmit to its AP upon invitation (either individual or group) from the AP. (Of course we would have to define other cases and exceptions, such as how a device in such a mode would roam, but the central principle would be that in normal operation, such a non-AP STA would not initiate communication.) For illustration of the utility, here is one example scenario. In the 2.4GHz band, let us suppose that we see large-scale deployments of IoT devices that are, for cost/complexity reasons, DSSS/CCK only, and that individually transmit only sporadically. (During development of mc, it was argued that we may well see such large-scale deployments over the next few years. It's hard to be certain about such matters, but it seems plausible enough.) Now how do we handle a mixed network in the presence of all these non-OFDM devices? At present, not too well: the presence of any non-OFDM (non-ERP) devices requires all traffic to be sent in protected mode, with corresponding increased overhead. Some estimates are that in typical deployments and traffic scenarios, the association of a single non-OFDM device causes an immediate ~30% reduction in network throughput *even if the non-OFDM device itself transmits no data*. But here's where the "speak-only-when-spoken-to" mode would be useful: all such devices could be instructed by the AP upon association that they were in that mode. Then the AP could run OFDM traffic most of the time, without 11b-based protection mechanisms, and could sporadically poll the non-OFDM devices, individually or as a group: all in all, a much more efficient mode of operation that still maintains satisfactory functionality for 11b-only devices. More generally the same principle will allow us to extend to new generations of Wi-Fi indefinitely, without having to suffer longer and longer preambles that trundle through each preceding generation. | Define a "speak-only-when-spoken-to" mode of operation. See forthcoming presentation(s). | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | GEN | Submission Required | Submission Required | GEN: 2017-06-30 17:54:23Z - status set to: Submission |  |  |  | 2018-01-16 17:20 | GEN
309 | Mark RISON | 25 | 0.1 |  |  |  | T | N | [5 empty] | Mark Rison |  |  | Many implementations fail to distinguish between probe reqs to an associated AP and other probe requests (especially since in 802.11-2007 probe reqs did not carry a valid PM bit) | Say that the PM bit is ignored (not reserved, because some implementations do set it to 1) in probe reqs | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | GEN | Submission Required | Submission Required | GEN: 2017-09-19 21:49:40Z - status set to: Submission Required |  |  |  | 2018-01-16 17:25 | GEN
118 | Mark Hamilton | 25 | 0.1 | 5.2.2.2 | 261 | 12 | T | Y | 261 | 12 | 5.2.2.2 |  |  | Mark Hamilton |  |  | MA-UNITDATA doesn't have drop_eligible, to match 802.1AC's ISS. | Add drop_eligible as a parameter to the request and indication primitives, and connect it to the DEI field (and to 802.1's parameter by asking 802.1 to remove the "ignored" statements). | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | GEN | Submission Required | Submission Required | GEN: 2017-06-30 18:09:52Z - status set to: Submission |  |  |  | 2018-01-16 17:20 | GEN
311 | Mark RISON | 25 | 0.1 |  |  |  | T | N | [5 empty] | Mark Rison |  |  | If aCCAtime needs to fit in slot time, does this mean it's necessary to detect a DSSS preamble within a slot time? This only allows about 8 bits of preamble, which seems insufficient. Even worse is "With a valid signal (according to the CCA mode of operation) present at the receiver antenna within 5 us of the start of a MAC slot boundary, the PHY-CCA.indication(BUSY) primitive shall be generated before the end of the slot time.", which seems to require ability to detect a DSSS preamble within 4 us (9 us slots minus 5 us before the valid signal turns up after the start of the slot) for CCA modes 4 or 5, even if the rx-tx turnaround time is 0! | Clarify how aCCAtime works for HR/DSSS | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | GEN | Submission Required | Submission Required | GEN: 2017-06-30 17:44:47Z - status set to: Submission |  |  |  | 2018-01-16 17:20 | GEN
313 | Mark RISON | 25 | 0.1 |  |  |  | T | N | [5 empty] | Mark Rison |  |  | What does "The TX-to-RX turnaround time shall be measured at the air interface from the trailing edge of the last transmitted symbol to valid CCA detection of the incoming signal. The CCA should occur within 25 us (10 us for turnaround time plus 15 us for energy detect) or by the next slot boundary occurring after 25 us has elapsed (refer to 16.3.8.5 (CCA)). A receiver input signal 3 dB above the ED threshold described in 16.3.8.5 (CCA) shall be present at the receiver." mean? Does it mean that an 11b device can be "deaf" to CCA for 25 us after it has transmitted? | Reword to be clear that no, a device can't just skip CCA for 25 us | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | GEN | Submission Required | Submission Required | GEN: 2017-06-30 17:44:10Z - status set to: Submission |  |  |  | 2018-01-16 17:19 | GEN
314 | Mark RISON | 25 | 0.1 |  |  |  | T | N | [5 empty] | Mark Rison |  |  | What does "The TX-to-RX turnaround time shall be measured at the air interface from the trailing edge of the last transmitted symbol to valid CCA detection of the incoming signal. The CCA should occur within 25 us (10 us for turnaround time plus 15 us for energy detect) or by the next slot boundary occurring after 25 us has elapsed (refer to 15.4.6.5 (CCA)). A receiver input signal 3 dB above the ED threshold described in 15.4.6.5 (CCA) shall be present at the receiver." mean? Does it mean that an 11-original device can be "deaf" to CCA for 25 us after it has transmitted? | Reword to be clear that no, a device can't just skip CCA for 25 us | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | GEN | Submission Required | Submission Required | GEN: 2017-12-08 20:02:55Z - status set to: Submission Required |  |  |  | 2018-01-16 17:19 | GEN
315 | Mark RISON | 25 | 0.1 |  |  |  | T | N | [5 empty] | Mark Rison |  |  | The definition of "base channel" is not clear. For example, in an 80 MHz BSS, with a STA that only supports 40 MHz but has sent an Notify Channel Width or Operating Mode Notification specifying 20 MHz, is the "base channel" from that STA's perspective a 20, 40 or 80 MHz channel? | Make it clear whether the "base channel" is the BSS bandwidth, the maximum bandwidth supported by the STA, or the operating bandwidth | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | GEN | Submission Required | Submission Required | GEN: 2017-06-30 17:43:27Z - status set to: Submission Required |  |  |  | 2018-01-16 17:19 | GEN
316 | Mark RISON | 25 | 0.1 |  |  |  | T | N | [5 empty] | Mark Rison |  |  | The definition of "base channel" is not clear. If the "base channel" varies when the STA's operating bandwidth changes (through Notify Channel Width or Operating Mode Notification) then what does that do to any existing TDLS link where one or the other device does not support "TDLS Wider Bandwidth"? | Make it clear whether the "base channel" is the BSS bandwidth, the maximum bandwidth supported by the STA, or the operating bandwidth, and make sure this is compatible with devices that do not support TDLS Wider Bandwidth | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | GEN | Submission Required | Submission Required | GEN: 2017-06-30 17:45:03Z - status set to: Submission |  |  |  | 2018-01-16 17:19 | GEN
117 | Mark Hamilton | 25 | 0.1 | 6.3.2.2.3 | 270 | 39 | T | Y | 270 | 39 | 6.3.2.2.3 |  |  | Mark Hamilton |  |  | The subclauses on "When generated" (in the MLME) generally don't actually say anything about limitations on timing ("when") of using the primitive. | Add description of "timing" (really, mostly sequencing or state requirements) to these subclauses. | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | GEN | Submission Required | Submission Required | GEN: 2017-06-30 18:10:31Z - status set to: Submission |  |  |  | 2018-01-16 17:20 | GEN
308 | Mark RISON | 25 | 0.1 |  |  |  | T | N | [5 empty] | Mark Rison |  |  | There is wide variation in the setting of the PM bit in Control frames | Say that the PM bit is ignored (not reserved, because some implementations do set it to 1) in Control frames | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | GEN | Submission Required | Submission Required | GEN: 2017-06-30 17:53:39Z - status set to: Submission Required |  |  |  | 2018-01-16 17:25 | GEN