## Slide 1
Date: 2017-07-13
Authors:
P802.11aq Report to EC on Approval to forward draft to RevCom

## Slide 2: Introduction
This document contains the report to the IEEE 802 Executive Committee in support of a request for approval to send IEEE P802.11aq Draft 11.0 to RevCom.
This document was approved during the interim session of the 802.11 working group on dd mm 2017.

## Slide 3: Sponsor Ballot Results – P802.11aq
Ballot Close Date | Title | Pool | Return | %Return | Abstain | %Abstain | Approve | Disapprove | %Approve
Nov 4, 2016 | Initial Sponsor Ballot for P802.11aq draft 7.0 | 125 | 105 | 84 | 1 | 1 | 91 | 13 | 88
March 18, 2017 | First Recirculation Sponsor Ballot for P802.11aq draft 8.0 | 125 | 110 | 88 | 2 | 1 | 98 | 10 | 90
June 23, 2017 | Second Recirculation Sponsor Ballot for P802.11aq draft 9.0 | 125 | 111 | 88 | 2 | 1 | 102 | 7 | 93
July 19 -July 29, 2017 | Third Recirculation Sponsor Ballot for P802.11aq draft 10.0 | 125 | xx | xx | xx | x | xx | xx | xx
August 25 – Sept’ 3, 2017 | Fourth Recirculation Sponsor Ballot for P802.11aq draft 11.0 | 125 | xx | xx | xx | x | xx | xx | xx
September 15 – September 25, 2017 | Fifth Recirculation Sponsor Ballot for P802.11aq draft 11.0 | 125 | xx | xx | xx | x | xx | xx | xx

## Slide 4: Sponsor Ballot Comments – P802.11aq
Ballot Close Date | Title | Total Number of Comments received (Yes and No votes)
Nov 4, 2016 | Initial Sponsor Ballot for P802.11aq draft 7.0 | 176 (104 T, 72 E)
March 18, 2017 | First Recirculation Sponsor Ballot for P802.11aq draft 8.0 | 6 (4 T, 2 E)
June 23, 2017 | Second Recirculation Sponsor Ballot for P802.11aq draft 9.0 | 75 (9 T, 26 E)
June 26-July 5, 2017 | Third Recirculation Sponsor Ballot for P802.11aq draft 10.0 | n/a
July 15-July 25, 2017 | Fourth Recirculation Sponsor Ballot for P802.11aq draft 11.0 | n/a

## Slide 5: Unsatisfied comments by commenter
Voter | Initial Sponsor Ballot | 1st Re-circulation | 2nd Re-circulation | 3rd Re-circulation | 4th Re-circulation | Total
#1 | 0 | 10 | 0 | 0 | 0 | 6
#2 | 7 | 0 | 0 | 0 | 0 | 9
#3 | 1 | 19 | 0 | 0 | 0 | 14
#4 | 25 | 0 | 0 | 0 | 0 | 23
#5 | 2 | 0 | 0 | 0 | 0 | 35
Total |  |  |  |  |  | 110
(*) Commenter provided no response when contacted (2016-07-12, 2016-07-28 and 2016-09-13) to ask which comments are satisfied or unsatisfied.
Total number of unsatisfied comments based on feedback from commenter: 39
Total number of unsatisfied comments from unresponsive commenter: 25
Note: the following voters on D11.0 in the 5th Recirc indicated that all of his comments were resolved to their satisfaction but did not update his vote during the ballot: Dan HARKINS

## Slide 6: Unsatisfied comments by topics
Normative references – 6
GAS extension and fragmentation – 2
ANQP – 6
MLME – 9
MAC privacy – x
PAD - x
Other -- x

## Slide 7: Unsatisfied comments
The composite of all unsatisfied comments and the resolutions approved by the comment resolution committee received during sponsor ballot may be found in the embedded document on the right:
  Double click on the icon to the right to open this.
  The file is also available at: https://mentor.ieee.org/802.11/dcn/17/XXXXX

## Slide 8: Mandatory Coordination
Coordination Entity | Draft | Date | Status
IEEE-SA Editorial (MEC) | D4.0 & D10.0 (*) | Feb 2015 & Sep 2015 (*) | “Meets all editorial requirements.” (*)
Quantities, Units and Letter Symbols (SCC14) |  |  | Not required
Terms and Definitions (SCC10) |  |  | Not required
Registration Authority Committee (RAC) |  |  | Not required
(*) Note: IEEE Editor provided a comment as part of 4th Recirculation Ballot (Sep 2016) indicating the “The draft meets all editorial requirements”

## Slide 9: TGaq Timeline
Initial Sponsor Ballot on D7.0 | Open 2016-08-15 | Close 2016-11-04
1st Recirculation Sponsor Ballot on D8.0 | Open 2017-03-15 | Close 2017-03-18
2nd Recirculation Sponsor Ballot on D9.0 | Open 2017-06-28 | Close 2017-06-23
3rd Recirculation Sponsor Ballot on D10.0 | Open 2017-07-27 | Close 2017-08-07
4th Recirculation Sponsor Ballot on D11.0 | Open 2017-08-30 | Close 2017-09-09
5th Recirculation Sponsor Ballot on D11.0 | Open 2017-09-20 | Close 2017-09-30
Report to EC on meeting conditions to proceed to RevCom | 2017-10-04 | 
Posting to RevCom by deadline | 2017-10-17 |